# Change Control Detail

CWP-700 Composite Wing Panel Production Program

Full detail document for each of the 8 changes logged on the Change Control Log.

## CN-001 — Correct Part Marking Specification Reference

| Category | Documentation / Administrative | Requested By | H. Lindgren (Doc Control) |
| --- | --- | --- | --- |
| Date Submitted | 08 Jun 2026 | Date Decided | 15 Jun 2026 |

Approval Authority: Acme Internal (Tier 1) — C. Tyrrell

Description: A drawing reference number in the part marking specification pointed to a superseded engineering revision letter. No change to the physical marking requirement.

Justification: Caught during a routine document-control audit.

Impact: None to cost, schedule, or the physical part.

Status: Approved

## CN-002 — Clarify Edge-Trim Tolerance Callout

| Category | Documentation / Administrative | Requested By | R. Kessler (Quality Eng. Lead) |
| --- | --- | --- | --- |
| Date Submitted | 02 Aug 2026 | Date Decided | 09 Aug 2026 |

Approval Authority: Acme Internal (Tier 1) — R. Kessler

Description: FAI found the edge-trim tolerance callout ambiguous between two adjacent drawing views. Wording clarified; tolerance value unchanged.

Justification: Ambiguous callouts risk inconsistent interpretation between inspectors on different shifts.

Impact: None to cost or schedule.

Status: Approved

## CN-003 — Revise FAI Checklist Acceptance Criteria Wording

| Category | Documentation / Administrative | Requested By | R. Kessler (Quality Eng. Lead) |
| --- | --- | --- | --- |
| Date Submitted | 12 Aug 2026 | Date Decided | 19 Aug 2026 |

Approval Authority: Acme Internal (Tier 1) — R. Kessler

Description: Customer source-inspection auditor flagged 2 acceptance criteria as ambiguous (RAIDD I-04); checklist reworded with unambiguous pass/fail criteria.

Justification: Ambiguous acceptance criteria risk inconsistent FAI results across future units.

Impact: None to cost or schedule.

Status: Approved

## CN-004 — Update Program Baseline for Corrected Staffing Model

| Category | Schedule / Resource | Requested By | C. Tyrrell (Program Manager) |
| --- | --- | --- | --- |
| Date Submitted | 21 Sep 2026 | Date Decided | 28 Sep 2026 |

Approval Authority: Executive Sponsor (Tier 2) — G. Talmadge

Description: Formalized the correction of the delivery team from a 14-person, single-shift estimate to a 25-person, two-shift team into the program's standing baseline.

Justification: The original staffing estimate was insufficient for real steady-state two-shift production (RAIDD R-07, D-05).

Impact: Program budget corrected from $3,500,000 to $5,200,000.

Status: Approved

## CN-005 — Approve Immersion Ultrasonic Testing as Alternate NDT Method

| Category | Engineering Change (ECN) | Requested By | L. Vance (Materials/NDT Eng.) |
| --- | --- | --- | --- |
| Date Submitted | 25 Sep 2026 | Date Decided | 07 Oct 2026 |

Approval Authority: Meridian Program Office (Tier 3)

Description: Added immersion ultrasonic testing as a Meridian-approved alternate inspection method to contact UT, no change to acceptance criteria.

Justification: Supports the corrected two-shift NDT staffing model; addresses RAIDD Issue I-02.

Impact: No cost change. Requires Meridian approval since NDT method is a drawing callout.

Status: Approved

## CN-006 — Revise Layup Fixture Preventive Maintenance Schedule

| Category | Process / Tooling | Requested By | M. Osei (Manufacturing Eng.) |
| --- | --- | --- | --- |
| Date Submitted | 02 Dec 2026 | Date Decided | 11 Dec 2026 |

Approval Authority: Acme Internal (Tier 2) — Program Review Board

Description: Root cause corrective action following MRB-004 (ply misalignment traced to fixture wear) — added a standing preventive-maintenance schedule.

Justification: Prevents recurrence of the same root cause on future production runs.

Impact: Minor recurring maintenance cost, absorbed within existing budget lines.

Status: Approved

## CN-007 — Add Repair Limits Table for Oversized Fastener Holes

| Category | Engineering Change (ECN) | Requested By | R. Kessler (Quality Eng. Lead) |
| --- | --- | --- | --- |
| Date Submitted | 15 Dec 2026 | Date Decided | 05 Jan 2027 |

Approval Authority: Meridian Program Office (Tier 3)

Description: Formalized the rework disposition used in MRB-001 and MRB-003 into a standing repair-limits table on the engineering drawing.

Justification: Reduces repeat MRB cycle time for a known, bounded, already-precedented finding.

Impact: No cost impact; requires Meridian approval since it changes the accepted repair envelope.

Status: Approved

## CN-008 — Add Second Approved Source for Composite Prepreg Material

| Category | Supplier / Material | Requested By | S. Pham (Supplier Quality Eng.) |
| --- | --- | --- | --- |
| Date Submitted | 28 Oct 2026 | Date Decided | 19 Nov 2026 |

Approval Authority: Meridian Program Office (Tier 3)

Description: Added a second qualified supplier to the approved-source list for the primary composite prepreg material.

Justification: Closes out the single-source schedule exposure recorded as RAIDD Risk R-01 (RAIDD Decision D-03).

Impact: No change to current program budget; qualification cost scoped separately.

Status: Approved

Illustrative program data — created to demonstrate AS9100-aligned aerospace program management practice, not a real supplier engagement.