## Slide 1
PROGRAM KICKOFF · PHASE 1, DAY 1
CWP-700 Composite Wing
Panel Production Program
Eighteen months. Twenty-five people across two phases. One First Article Meridian will actually accept.
May 15, 2026
Kickoff Date
C. Tyrrell
Program Manager
25
Team Members (Both Phases)
1

## Slide 2
AGENDA
What We'll Cover Today
1
Welcome & Program Context
2
Why This Program Matters
3
Success Criteria
4
Scope: In and Out
5
The Program Team
6
Milestone Timeline
7
Budget Overview
8
How We'll Work Together
9
Risks We're Watching
10
Next Steps & Q&A
2

## Slide 3
WELCOME
Glad You're Here
Nine of us are in the room today. Sixteen more join as we ramp to two-shift production — every one of them is on this deck too.
Acme's delivery team and Meridian's Program Office are aligning today on program scope, the staged qualification approach, and working cadence before Phase 1 begins. Quick round of introductions: name, role, and what you're most excited (or nervous) about.
25
NAMED TEAM, BOTH PHASES
18
MONTHS, PHASE 1 + 2
2
PRODUCTION SHIFTS
3

## Slide 4
THE BUSINESS CASE
Why We're Doing This
A Tier 1 composite supplier's quality history is a leading indicator of First Article outcomes on a new part number — and Meridian was watching ours closely.
This is Acme's first dedicated production contract for the M7 platform, awarded after a competitive source-selection process. Full detail lives in the Program Charter.
$5.2M
TOTAL PROGRAM BUDGET
Month 8
PRODUCTION RAMP BEGINS
4

## Slide 5
SUCCESS CRITERIA
What Success Looks Like
1
First Article Inspection accepted by Meridian within the Phase 1 schedule
2
Phase 2 ramps to full contracted rate with on-time delivery performance
3
Program closes within the $5.2M budget, $0 variance to baseline
4
All MRB dispositions closed with documented root cause and corrective action
5
Zero nonconformances reach Meridian undetected
5

## Slide 6
SCOPE
Where the Lines Are
IN SCOPE
Design-to-print manufacture of composite trailing-edge wing panels
Tooling design, fabrication, and qualification
First Article Inspection per AS9102
Steady-state production at contracted rate
MRB support, supplier quality, and lot-level traceability
OUT OF SCOPE
Engineering design of the wing panel itself (Meridian-owned)
Final aircraft assembly and flight test
Any ITAR-controlled defense-article work (commercial program)
Tooling design beyond the CWP-700 panel family
6

## Slide 7
THE PROGRAM TEAM
Everyone Who's Building This
C. Tyrrell
Program Manager
R. Kessler
Quality Engineering Lead (AS9100 Owner)
M. Osei
Manufacturing Engineer
ENGINEERING
L. Vance
Materials / NDT Engineer
A. Whitfield
Phase 1 · Tooling Engineer
J. Ferraro
Phase 2 · MRB Chair / Sr. QE
QUALITY & SUPPLY CHAIN
S. Pham
Supplier Quality Engineer
D. Okafor
Program Coordinator
R. Bianchi
Phase 2 · Buyer / Procurement
H. Lindgren
Phase 2 · Doc Control / CM
V. Castellanos
Phase 2 · EHS & Facilities
PRODUCTION — SHIFT 1
K. Rutherford
Layup Tech, Shift 1 Lead
T. Alvarado
Phase 2 · Layup Tech
M. Vartan
Phase 2 · Autoclave / Cure Tech
D. Halvorsen
Phase 2 · Trim & Drill Tech
R. Achebe
Phase 2 · NDT Technician
B. Solis
Quality Inspector
PRODUCTION — SHIFT 2
C. Okwuosa
Phase 2 · Layup Tech, Shift 2 Lead
P. Mensah
Phase 2 · Layup Tech
A. Delacroix
Phase 2 · Layup Tech
J. Whitby
Phase 2 · Layup Tech
S. Okoro
Phase 2 · Autoclave / Cure Tech
L. Fontaine
Phase 2 · Trim & Drill Tech
K. Sorensen
Phase 2 · NDT Technician
N. Vasquez
Phase 2 · Quality Inspector
All 25, same as the Resource Plan and Org Chart. Phase 2 tags mark the 16 who join as we ramp to two-shift production — not omitted, just not onboarded yet.
7

## Slide 8
TIMELINE
The Road to Full Rate
Kickoff
May 15
Tooling Qualified
Month 3
First Article Accepted
Month 6
Production Ramp Begins
Month 7
Full Rate Achieved
Month 12
Program Closeout
Month 18
Full interactive schedule: WBS/Gantt Console
8

## Slide 9
BUDGET
Where the Money Goes
Chart: 
| Labor — 25-Person Team | Tooling, Fixtures & FAI Testing | Materials & Travel | PM Reserve
Budget | 4344 | 265 | 375 | 216
$5.2M
TOTAL BUDGET
This is a fixed-price contract — Acme bears the internal cost risk of scrap or rework, not Meridian. Getting this budget right matters.
Full detail and the 25-person rate card: Resource Plan
9

## Slide 10
WORKING TOGETHER
How We'll Stay in Sync
Cadence | Forum | Purpose
Weekly | Program Status Review | Schedule, budget, RAIDD review
Bi-weekly (weekly Phase 2) | Quality Review Board | Open MRB cases, FAI status, supplier quality
Monthly | Joint Program Review with Meridian | Delivery performance, open issues, schedule
Once, end of Phase 1 | FAI Gate Review | Formal go/no-go for Phase 2 production release
Full governance model and decision rights: Program Governance Model
10

## Slide 11
EYES OPEN
Risks We're Watching From Day One
!
Single-source composite material lead time
!
NDT capacity sized for the wrong production phase
!
Tight tooling-qualification schedule
!
Customer source-inspection scheduling
Full risk register: RAIDD Log
11

## Slide 12
NEXT STEPS
What Happens Next
1
Tooling concept design begins immediately (layup mandrel, trim/drill fixture)
2
Supplier quality kickoff with raw material sources this week
3
First Weekly Program Status Review scheduled for next week
12

## Slide 13
Let's Build a First Article Meridian Accepts the First Time.
C. Tyrrell, Program Manager
CWP-700 Composite Wing Panel Production Program
13