## MRB Log
ID | Date | Nonconformance | Disposition | Owner | Status
MRB-001 | 2026-02-11 | Edge-trim dimension out of tolerance, 2 of 8 panel positions, S/N 0001 (FAI unit) | Rework | R. Kessler / J. Ferraro (Chair, ad hoc for FAI) | Closed — reworked panel passed re-inspection
MRB-002 | 2026-04-03 | Minor surface porosity within cosmetic (non-structural) zone, S/N 0034 | Use-as-is | J. Ferraro | Closed — engineering disposition, no structural impact
MRB-003 | 2026-05-19 | Fastener hole diameter 0.003in over tolerance, single hole, S/N 0058 | Rework | J. Ferraro | Closed — oversized fastener installed per engineering approval
MRB-004 | 2026-06-02 | Composite ply misalignment detected via NDT, S/N 0071 | Scrap | J. Ferraro | Closed — part scrapped, root cause traced to layup fixture wear
MRB-005 | 2026-06-20 | Raw material certification missing batch traceability code, incoming lot | Return-to-Supplier | S. Pham | Closed — lot returned, replacement lot certs verified before use