# Program Management Plan

CWP-700 Composite Wing Panel Production Program — Acme Aerostructures

## 1. Introduction & Purpose

This Program Management Plan describes how the CWP-700 program will be executed, monitored, and controlled. It is the integrating document across every specialized artifact in this suite — the Program Charter, Program Budget, Resource Plan, RAIDD Log, and Program Governance Model each cover one discipline in depth; this plan ties them together.

## 2. Program Overview

Acme Aerostructures, a Tier 1 supplier, is delivering composite trailing-edge wing panels to Meridian Aircraft Co. for the Meridian M7 narrowbody under an 18-month fixed-price production contract: Phase 1 (6 months, Qualification & First Article) and Phase 2 (12 months, Production Ramp & Steady-State). See the Program Charter for full scope and business case.

## 3. Program Management Approach

This program follows a stage-gated approach: each phase transition is governed by a formal gate (Critical Design Review, Tooling Qualification, First Article Inspection) rather than a purely iterative cadence, since physical tooling and FAI cannot be revisited cheaply.

## 4. Scope Management

Scope is defined by Meridian's baselined engineering drawings, established at the Critical Design Review gate. Any change to form, fit, or function requires a Meridian-approved Engineering Change Notice (see Section 14).

## 5. Schedule Management

The program schedule is maintained in the Work Breakdown Structure (79 line items across 2 phases). Schedule status is reported weekly internally and monthly to Meridian via the Steering Deck.

## 6. Cost Management

The program's total budget is $5,200,000, corrected from an original $3,500,000 estimate once real two-shift staffing needs became clear (RAIDD Decision D-05). This is a fixed-unit-price contract; internal cost tracking is how Acme manages margin, not a figure reported to the customer line-item by line-item.

## 7. Quality Management

Quality is managed under Acme's corporate AS9100 QMS: First Article Inspection (requiring Meridian source-inspection witness), Material Review Board disposition of nonconformances, supplier PPAP qualification, and the AS9100 QMS documentation and internal audit function.

## 8. Configuration & Traceability Management

Every panel is marked with part number, serial number, and lot-traceable material batch code, maintained from raw material receipt through delivery — the traceability backbone the MRB process depends on.

## 9. Resource Management

The delivery team stands at 25 people across two shifts, corrected from an original 14-person, single-shift estimate (RAIDD Decision D-05) — the original had only 3 layup technicians, one NDT resource, and no dedicated Autoclave/Cure, Trim & Drill, Document Control, or EHS roles.

## 10. Communications Management

Internal and customer-facing communication cadences are defined in the Communications Plan. Standing forums (Program Status Review, Quality Review Board, Joint Program Review with Meridian) are summarized in the Program Governance Model.

## 11. Risk Management

All risks, assumptions, issues, dependencies, and decisions are tracked in a single RAIDD Log, scored 1-9. Escalation authority by risk score is defined in the Program Governance Model.

## 12. Supplier & Procurement Management

Raw-material and tooling suppliers are qualified via PPAP prior to use, with quarterly performance reviews. The single-source composite prepreg material (R-01) is the subject of an approved dual-sourcing initiative (D-03).

## 13. Customer Stakeholder Engagement

Meridian's Program Office holds real, contractual acceptance authority over FAI and major MRB dispositions. Engagement cadence is defined in the Program Governance Model.

## 14. Engineering Change Management

Any change affecting form, fit, or function requires a Meridian-approved Engineering Change Notice (ECN) — a Tier 3 governance decision regardless of cost impact. A dedicated ECN log for this suite is a planned addition.

## 15. Governance & Decision Authority

Full decision-rights tiering, escalation thresholds, and the Program Review Board roster are defined in the Program Governance Model — the authoritative reference this plan defers to.

## 16. Lessons Learned & Continuous Improvement

Lessons from this program — including the NDT staffing miscalibration that drove Decision D-05 — are captured in the Lessons Learned register as they occur, not only at closeout.

## 17. Assumptions, Constraints & Dependencies

Meridian's engineering source data is final and baselined at contract start. Composite autoclave capacity is sufficient for the planned Phase 2 rate. Raw-material suppliers will deliver PPAP submissions on schedule. The corrected 25-person team remains available at planned allocation through Phase 2.

## 18. Baselines Summary

| Baseline | Current Value | Reference |
| --- | --- | --- |
| Schedule | 18 months (Phase 1: 6 mo. / Phase 2: 12 mo.) | WBS |
| Cost | $5,200,000 (corrected from $3,500,000) | Program Budget |
| Staffing | 25 people (corrected from 14) | Resource Plan |
| Quality | AS9100 QMS, 5 of 5 MRB cases closed to date | Material Review Board |

## 19. Approval

This Program Management Plan is approved for use across the CWP-700 program.

____________________________

G. Talmadge, Executive Sponsor (VP of Operations)

____________________________

C. Tyrrell, Program Manager

Illustrative program data — created to demonstrate AS9100-aligned aerospace program management practice, not a real supplier engagement.