## WBS
CWP-700 Composite Wing Panel Production Program — Work Breakdown Structure
Full export from the program schedule — 21 line items across 2 phases, 14 named assignees.
WBS ID | Task Name | Start | Finish | Duration (d) | % Complete | Assigned To | Milestone
1 | Phase 1: Qualification & First Article | 2026-02-02 | 2026-06-09 | 0 | 100
1.1 | Production tooling design | 2026-02-02 | 2026-03-09 | 26 | 100 | A. Whitfield
1.2 | Production tooling fabrication | 2026-03-10 | 2026-04-22 | 32 | 100 | A. Whitfield
1.3 | Raw material qualification (PPAP) | 2026-02-02 | 2026-02-25 | 18 | 100 | S. Pham
1.4 | Initial composite layup (tooling qualification run, S/N 0001) | 2026-04-23 | 2026-04-30 | 6 | 100 | K. Rutherford
1.5 | NDT ultrasonic scan (initial run) | 2026-05-01 | 2026-05-05 | 3 | 100 | L. Vance
1.6 | Quality inspection (initial run, dimensional + visual) | 2026-05-06 | 2026-05-11 | 4 | 100 | B. Solis
1.7 | FAI full dimensional layout | 2026-05-12 | 2026-05-18 | 5 | 100 | M. Osei
1.8 | FAI documentation (AS9102 Form 1/2/3 package) | 2026-05-19 | 2026-05-22 | 4 | 100 | R. Kessler
1.9 | MRB-001 disposition (edge-trim rework) | 2026-05-25 | 2026-05-29 | 5 | 100 | R. Kessler
1.10 | Rework and FAI re-inspection | 2026-06-01 | 2026-06-08 | 6 | 100 | K. Rutherford, B. Solis
1.11 | Milestone Gate: FAI Accepted, Customer Source Inspection Witness | 2026-06-09 | 2026-06-09 | 0 | 100 | C. Tyrrell | Yes
2 | Phase 2: Production Ramp & Steady-State | 2026-06-10 | 2027-06-14 | 0 | 52
2.1 | Production release authorization | 2026-06-10 | 2026-06-10 | 1 | 100 | C. Tyrrell
2.2 | Composite layup production ramp (3-technician rotation) | 2026-06-11 | 2027-06-07 | 258 | 55 | K. Rutherford, T. Alvarado, C. Okwuosa
2.3 | NDT inspection (production rate) | 2026-06-11 | 2027-05-24 | 248 | 55 | L. Vance
2.4 | Quality inspection (production rate, 2-inspector rotation) | 2026-06-11 | 2027-05-24 | 248 | 55 | B. Solis, N. Vasquez
2.5 | MRB case management (MRB-002 through MRB-005) | 2026-06-11 | 2027-03-17 | 200 | 55 | J. Ferraro
2.6 | Supplier PPAP maintenance & incoming lot verification | 2026-06-11 | 2027-05-31 | 253 | 55 | S. Pham
2.7 | Purchase order execution & supplier scheduling | 2026-06-11 | 2027-03-17 | 200 | 55 | R. Bianchi
2.8 | Preventive maintenance program (layup fixture, post MRB-004) | 2026-06-11 | 2026-06-24 | 10 | 40 | M. Osei
2.9 | Program status reporting & RAIDD log maintenance | 2026-06-11 | 2027-05-31 | 253 | 55 | D. Okafor
2.10 | Milestone: Program Closeout | 2027-06-08 | 2027-06-14 | 5 | 0 | C. Tyrrell