# Program Status Report

Weekly status report snapshot for the CWP-700 Composite Wing Panel Production Program, taken mid-Phase 2
(Production Ramp & Steady-State), showing overall program health, budget, schedule, and open
quality items.

## Program Health

| Dimension | Status | Comment |
| --- | --- | --- |
| Schedule | Green | Phase 2 production rate on track; Phase 1 FAI 3-week buffer was fully consumed but did not slip the overall program end date. |
| Budget | Green | Actuals tracking to the $3,500,000 total program budget; no reserve draw to date. |
| Quality | Yellow | NDT queue backlog (RAIDD I-02) added ~4 days to panel release cycle time; mitigation (second NDT technician) in place. |
| Scope | Green | No engineering changes from Meridian Aircraft Co. since contract baseline (RAIDD A-01 holding). |

## This Period

- Production running at planned rate following the FAI gate and Phase 2 ramp-up.

- MRB-003 (oversized fastener hole) and MRB-004 (ply misalignment, scrap) dispositioned and closed.

- Second NDT technician onboarded and qualified, addressing the inspection queue backlog.

## Next Period

- Continue monitoring NDT cycle time now that the second technician is fully ramped.

- Preventive-maintenance schedule for the layup fixture (root cause of MRB-004) to be finalized.

- Monthly Joint Program Review with Meridian Aircraft Co. to confirm delivery performance against schedule.