## Slide 1
PROGRAM STEERING COMMITTEE REVIEW
CWP-700 Composite Wing Panel
Production Program
Acme Aerostructures · Meridian Aircraft Co. · Fixed-Price Production Contract
Program Manager: C. Tyrrell

## Slide 2
EXECUTIVE SUMMARY
Program Health
TOTAL BUDGET
$2,500,000
ACTUAL COST
$2,350,000
SCHEDULE
Month 14 of 18
MRB CASES
5 closed, 0 open
Schedule
On track — Phase 2 production ramp proceeding at planned rate
Budget
On track — undrawn reserve; no cost overruns
Quality
Managed — NDT capacity issue identified and resolved (2nd technician onboarded)
Scope
Stable — no engineering changes from customer since baseline

## Slide 3
QUALITY PERFORMANCE
AS9100 / FAI / MRB Summary
Chart: MRB Dispositions (5 cases)
| Rework | Use-as-is | Scrap | Return-to-Supplier
MRB Dispositions | 2 | 1 | 1 | 1
First Article Inspection accepted after one rework cycle (MRB-001), inside the 3-week schedule buffer
Zero nonconformances reached the customer undetected across the program
Root cause of the one scrap event (MRB-004, layup fixture wear) resolved via a new preventive-maintenance schedule
Supplier material traceability gap (MRB-005) caught at incoming inspection before it touched production

## Slide 4
FINANCIAL SUMMARY
Program Budget vs. Actuals
Chart: Budget vs. Actual by Category ($)
| Labor | Non-Labor | Reserve
Budget | 2710000 | 640000 | 150000
Actual | 2710000 | 640000 | 0

## Slide 5
LOOKING AHEAD
Next Steps & Asks
Continue monitoring NDT cycle time now that the second technician is fully ramped
Finalize the preventive-maintenance schedule for the composite layup fixture
Hold the monthly Joint Program Review with Meridian to confirm delivery performance
No steering-committee asks this period — program tracking to budget and schedule