## Agile RACI
Agile RACI — MedConnect Mobile (R=Responsible A=Accountable C=Consulted I=Informed; *=only when story touches PHI/clinical workflow)
Activity | C. Tyrrell (PO/Lead) | Scrum Masters | Eng. Leads | Dev Teams | M. Delacroix (Sponsor) | Dr. Nguyen (CMIO) | T. Brannigan (Compliance)
Backlog prioritization | A/R | I | C | I | C | C | I
Writing acceptance criteria | R | I | C | C |  | C | C
Sprint Planning facilitation | C | A/R | R | R
Daily Standup facilitation | I | A/R | C | R
Scrum-of-Scrums facilitation | A/R | R | R |  | I
Sprint Review/Demo | A | R | R | R | I | I | I
Sprint Retrospective | I | A/R | C | R
Definition of Done sign-off | A | C | R | R |  | C* | C*
Clinical workflow sign-off | I |  | C |  | I | A/R
PHI/compliance review | I |  | C |  | I |  | A/R
Release/go-live decision | R | C | C |  | A | C | C
Steering Committee reporting | A/R |  |  |  | I | I | I
Cross-team dependency resolution | A | R | R