## Change Requests
Change Control Log — MedConnect Mobile (3 CRs, all Implemented)
CR ID | Title | Category | Raised | Approved By | Cost Impact | Schedule Impact | Scope Impact | Status
CR-01 | Additional Staging/Load-Test Environment | Cost | Sprint 4 | M. Delacroix | +$18,000 | None | None | Implemented
CR-02 | Contractor Support for Sprint 7 Migration Remediation | Cost | Sprint 6 | M. Delacroix | +$42,000 | None (absorbed) | None | Implemented
CR-03 | Extend Pre-Cutover Compliance Review Window (2 to 5 days) | Schedule | Sprint 7 | M. Delacroix + T. Brannigan | None | Internal only, no program-end slip | None | Implemented