## Board Snapshots
Sprint Board — 3 Point-in-Time Snapshots (Sprint 2/5/8)
Sprint | Snapshot Date | Column | ID | Story | Team | Pts | Note
Sprint 2 | Feb 9 (Day 6/10) | Backlog | MCM-113 | Add appointment to calendar | Falcon | 2
Sprint 2 | Feb 9 (Day 6/10) | Backlog | MCM-114 | Pre-visit intake questionnaire | Falcon | 5
Sprint 2 | Feb 9 (Day 6/10) | Backlog | MCM-120 | Join video visit with one tap | Falcon | 8
Sprint 2 | Feb 9 (Day 6/10) | Backlog | MCM-121 | Video SDK integration | Anchor | 13
Sprint 2 | Feb 9 (Day 6/10) | To Do | MCM-112 | Reminder notifications | Falcon | 5
Sprint 2 | Feb 9 (Day 6/10) | To Do | MCM-106 | First-run tutorial | Falcon | 2
Sprint 2 | Feb 9 (Day 6/10) | In Progress | MCM-111 | Book/reschedule/cancel appointment | Falcon | 8 | Blocked — waiting on MCM-160
Sprint 2 | Feb 9 (Day 6/10) | In Progress | MCM-161 | Reminder notification service | Anchor | 4
Sprint 2 | Feb 9 (Day 6/10) | In Review | MCM-110 | Search appointment by provider | Falcon | 8
Sprint 2 | Feb 9 (Day 6/10) | Done | MCM-105 | Password reset flow | Falcon | 3
Sprint 2 | Feb 9 (Day 6/10) | Done | MCM-140b | Migration pipeline hardening | Anchor | 8
Sprint 2 | Feb 9 (Day 6/10) | Done | MCM-160 | Availability engine | Anchor | 8
Sprint 5 | Mar 25 (Day 8/10) | Backlog | MCM-150 | Secure messaging | Both | 8
Sprint 5 | Mar 25 (Day 8/10) | Backlog | MCM-152 | Prescription refill request | Both | 8
Sprint 5 | Mar 25 (Day 8/10) | To Do | MCM-181 | Rollback runbook | Anchor | 2
Sprint 5 | Mar 25 (Day 8/10) | In Progress | MCM-180 | Production infra scaling | Anchor | 7
Sprint 5 | Mar 25 (Day 8/10) | In Review | MCM-172 | Monitoring & crash reporting | Falcon | 3
Sprint 5 | Mar 25 (Day 8/10) | In Review | MCM-141b | Migration final validation | Anchor | 8
Sprint 5 | Mar 25 (Day 8/10) | Done | MCM-125 | 5-min rejoin grace window | Falcon | 5
Sprint 5 | Mar 25 (Day 8/10) | Done | MCM-170 | MVP defect triage | Falcon | 13
Sprint 5 | Mar 25 (Day 8/10) | Done | MCM-171 | App/Play Store release build | Falcon | 5
Sprint 5 | Mar 25 (Day 8/10) | Done | MCM-142 | Pre-cutover validation report | Anchor | 5
Sprint 8 | May 6 (Day 9/10) | In Progress | MCM-144 | Decommission CareLink Classic | Anchor | 8
Sprint 8 | May 6 (Day 9/10) | In Review | MCM-193 | Final cutover sign-off | Anchor | 4
Sprint 8 | May 6 (Day 9/10) | In Review | MCM-145 | Archival export | Anchor | 5
Sprint 8 | May 6 (Day 9/10) | Done | MCM-154 | Refill status notifications | Falcon | 2
Sprint 8 | May 6 (Day 9/10) | Done | MCM-190 | Release 2 regression pass | Falcon | 10
Sprint 8 | May 6 (Day 9/10) | Done | MCM-191 | Support FAQ & help content | Falcon | 3
Sprint 8 | May 6 (Day 9/10) | Done | MCM-192 | Release notes & listing update | Falcon | 3
Sprint 8 | May 6 (Day 9/10) | Done | MCM-143 | Full historical migration | Anchor | 13