## Slide 1
PROGRAM KICKOFF · SPRINT 0, DAY 1
MedConnect Mobile
Two teams. Eight sprints. One telehealth platform patients will actually want to use.
January 5, 2026
Kickoff Date
C. Tyrrell
Product Owner & Agile Delivery Lead
13
Team Members
1

## Slide 2
AGENDA
What We'll Cover Today
1
Welcome & Program Context
2
Why This Program Matters
3
Success Metrics & OKRs
4
Scope: In and Out
5
Teams & Delivery Model
6
Sprint Timeline & Releases
7
Budget Overview
8
How We'll Work Together
9
Risks We're Watching
10
Next Steps & Q&A
2

## Slide 3
WELCOME
Glad You're Here
Thirteen people across two teams become one Scrum-of-Scrums today — and Sprint 1 starts in two weeks.
Over the next 18 weeks, Team Falcon (Mobile) and Team Anchor (Platform) will replace CareLink Classic with a native patient app, a provider web console, and a clean historical data migration — coordinated through a lightweight Scrum-of-Scrums, not a heavyweight SAFe model. Quick round of introductions: name, team, and what you're most excited (or nervous) about.
13
NAMED TEAM MEMBERS
8
SPRINTS TO FULL CUTOVER
2
COORDINATING TEAMS
3

## Slide 4
THE BUSINESS CASE
Why We're Doing This
CareLink Classic's vendor end-of-support date is fixed — there's no mobile roadmap coming, and no extension available.
The current telehealth platform has an announced end-of-support date 18 months out, no mobile roadmap ever delivered, and renewal pricing that rose 34% at last cycle. This program replaces it with a native mobile app and provider console — full detail lives in the Program Charter and Cost-Benefit Analysis.
$1.85M
APPROVED BUDGET
May '26
TARGET FULL CUTOVER
4

## Slide 5
SUCCESS METRICS
What Success Looks Like
1
60% of visits booked via mobile app within 60 days of Release 1
2
Login-to-visit-start time cut from ~6 min to under 2 min
3
Telehealth support tickets down from ~410/mo to under 150/mo
4
100% of active patient records migrated, zero critical data-integrity defects
5
≥ 85% of scheduled providers using the console daily by week 4
Full OKR detail and release roadmap: Vision & Roadmap
5

## Slide 6
SCOPE
Where the Lines Are
IN SCOPE
Patient mobile app (iOS/Android) and provider web console
Video visit integration (PulseConnect SDK)
Full patient-record migration; CareLink Classic decommission
Secure messaging and prescription refill requests
OUT OF SCOPE (CANDIDATE BACKLOG)
Remote patient monitoring device integration
Multi-language patient app support
Group/family visit scheduling
Provider analytics dashboard
6

## Slide 7
TEAMS
Everyone Who's Building This
C. Tyrrell
Product Owner & Agile Delivery Lead
J. Marsh
Scrum Master, Team Falcon
R. Okafor
Scrum Master, Team Anchor
TEAM FALCON — MOBILE
5 FTE
D. Whitfield
Engineering Lead
K. Alvarez
iOS Developer
S. Park
Android Developer
T. Nguyen
Backend Developer
E. Marchetti
QA Lead — Falcon
TEAM ANCHOR — PLATFORM
5 FTE
A. Singh
Engineering Lead
R. Kim
Backend Developer
N. Osei
QA Lead (Onshore)
M. Chen
Offshore QA Analyst
P. Kumar
Offshore QA Analyst
All 13, same as the Resource Plan and Org Chart — nobody on this program is a name you'll only find in a spreadsheet.
7

## Slide 8
TIMELINE
Eight Sprints to Full Cutover
Sprint 0
Kickoff
Jan 5
Sprint 2
Scheduling Core
Feb 2
Sprint 5
Release 1 (MVP)
Mar 27
Sprint 7
Full Data Migration
Apr 24
Sprint 8
Release 2 (Full Cutover)
May 8
Program
Closeout
May 15
Full sprint-by-sprint schedule: Release Schedule
8

## Slide 9
BUDGET
Where the Money Goes
Chart: 
| Team Labor (Falcon + Anchor) | PO + Scrum Masters | Vendor/Infrastructure | Contingency Reserve
Budget | 1068 | 294 | 361 | 127
$1.85M
APPROVED BUDGET
A 10% contingency reserve is built in from day one — drawn only through a formal Change Request, not spent by default.
Full detail and the 13-person rate card: Program Budget
9

## Slide 10
WORKING TOGETHER
How We'll Stay in Sync
Cadence | Forum | Purpose
Daily | Team Standup | Day-to-day coordination, blockers
2x/week | Scrum-of-Scrums | Cross-team dependency sync
Per sprint | Sprint Review + Retrospective | Stakeholder demo/feedback; team-only improvement
Monthly | Steering Committee | Formal program-health review
Full governance model, decision rights, and escalation path: Program Governance Model
10

## Slide 11
EYES OPEN
Risks We're Watching From Day One
!
Data-quality issues in legacy archive records could complicate historical migration
Highest-attention risk heading into Sprint 7
!
Third-party video SDK vendor configuration/entitlement gaps
Could affect the visit experience if not caught in spike/refinement
!
Cross-team dependencies could surface late without disciplined tracking
Why Scrum-of-Scrums runs twice a week, not once
Full risk register: Agile RAIDD Log
11

## Slide 12
NEXT STEPS
What Happens Next
1
Sprint 0 continues through Jan 16 — environment setup, tooling access, backlog seeding
2
First Backlog Refinement session on Jan 8
3
Sprint 1 Planning on Jan 19 — Auth & onboarding work begins
12

## Slide 13
Let's Ship Something Patients Will Actually Use.
C. Tyrrell, Product Owner & Agile Delivery Lead
MedConnect Mobile
13