Agile/Scrum Methodology Guide

MedConnect Mobile

This guide explains how Agile/Scrum program delivery actually works, using MedConnect Mobile's real sprint history as a running example.

Why adaptive delivery for this program: a native mobile rebuild competing against unknown adoption pace and platform-store review cycles benefits from shipping incrementally and adjusting based on real usage — the opposite bet from a program where the end state is already fully known.

# 1. Methodology at a Glance

Scrum is adaptive: instead of baselining scope up front, the team commits to a fixed-length sprint and re-prioritizes the Product Backlog before every one. What's fixed is the timebox and the process; what flexes is which backlog items get built next.

This only works because of a reliable sprint cadence and a velocity number the team trusts enough to forecast with — both earned through repetition, not declared on day one.

# 2. The Sprint Cadence

Sprint 0 — Kickoff / Foundation

No feature work ships in Sprint 0 — it's for environment setup, backlog seeding, and team formation. Kickoff/Sprint 0 was Jan 5, 2026.

Sprints 1-5 — Toward Release 1 (MVP)

Each sprint delivers a working increment; velocity is tracked from Sprint 1 onward. Release 1 (MVP) shipped at the end of Sprint 5, Mar 27, 2026.

Sprints 6-8 — Toward Release 2 (Full Cutover)

By this point velocity has stabilized enough to forecast the remaining scope with real confidence. Release 2 (Full Cutover from CareLink Classic) shipped at the end of Sprint 8, May 8, 2026, with Program Closeout on May 15, 2026.

# 3. The Four Ceremonies (Plus Refinement)

| Ceremony | Cadence | Purpose |
| --- | --- | --- |
| Sprint Planning | Start of every sprint | Team commits to backlog items based on velocity and Definition of Ready |
| Daily Standup | Daily | 15-minute sync on progress and blockers |
| Sprint Review | End of every sprint | Demo completed work to stakeholders; gather feedback |
| Sprint Retrospective | End of every sprint | Team-only reflection — Agile's continuous version of Lessons Learned |
| Backlog Refinement | Ongoing | Keeps upcoming items sized and meeting Definition of Ready |

The Retrospective is worth calling out specifically: it happens every single sprint, not once at program closeout, so lessons get applied within weeks instead of being filed away.

# 4. Key Disciplines vs. PMBOK Delivery

| Discipline | Agile / Scrum | PMBOK / Predictive |
| --- | --- | --- |
| Scope | Reprioritized every sprint via Product Backlog | Fixed at Planning baseline; formal Change Control |
| Schedule | Fixed-length sprints; scope flexes | Single baseline schedule tracked to completion |
| Progress measurement | Velocity and burndown | % complete against baseline schedule/budget |
| Retrospective | Every sprint — continuous | Captured at Closeout, or as issues arise |

# 5. Change Handling in Agile

A common misconception is that Agile has no change control. MedConnect Mobile's own Change Handling in Agile page draws the line: ordinary reprioritization is free — the Product Owner just reorders the backlog. A formal Change Request is only raised when something affects a baselined commitment — approved budget or a fixed release date.

- CR-01 — Additional Staging/Load-Test Environment. Raised Sprint 4, +$18,000 cost impact, no schedule impact, approved by M. Delacroix (Sponsor). Needed to load-test video visit infrastructure at realistic patient volume.

This needed formal approval specifically because it touched the approved budget — the same reason a PMBOK program would route it through formal Change Control. Agile reserves that formal weight for baselined commitments, not ordinary scope decisions.

# 6. MedConnect Mobile by the Numbers

| Figure | Value |
| --- | --- |
| Approved Program Budget | $1,850,000 |
| Actual Program Cost (at Closeout) | $1,810,000 |
| Total Reconciled Delivery Labor | $1,362,000 |
| Program Duration | Sprint 0 (Jan 5, 2026) to Closeout (May 15, 2026) — 8 delivery sprints |
| Release 1 (MVP) | End of Sprint 5, Mar 27, 2026 |
| Release 2 (Full Cutover) | End of Sprint 8, May 8, 2026 |
| Average Velocity (Sprints 2-8) | 43 points/sprint |
| Formal Change Requests | 3 (all approved) |

# 7. Roles at a Glance

Scrum defines fewer formal roles than PMBOK, on purpose. C. Tyrrell (Product Owner & Agile Delivery Lead) owns backlog prioritization and release scope; J. Marsh and R. Okafor (Scrum Masters, Falcon/Anchor) remove blockers and facilitate ceremonies; M. Delacroix (Executive Sponsor) holds funding authority; Dr. L. Nguyen (CMIO) and T. Brannigan (Compliance & Security Director) are matrixed advisory roles at ~10% allocation each.

# 8. Questions & Answers

What are the core Scrum ceremonies? Sprint Planning, Daily Standup, Sprint Review, and Sprint Retrospective, every sprint, plus ongoing Backlog Refinement.

Does Agile really have no change control? No — a narrower one. Ordinary reprioritization is free; formal Change Requests are reserved for changes touching a baselined budget or schedule commitment.

Why does velocity fluctuate? It reflects real team capacity. MedConnect Mobile's velocity ranged from 34 to 46 delivered points across 8 sprints, which is why the team used a multi-sprint average (43) to forecast, not any single sprint's number.

What's the difference between Definition of Ready and Definition of Done? Ready gates entry into a sprint; Done gates exit.

# 9. Related Reading

Agile Glossary (glossary.html) — plain-English definitions of Scrum terms used across this suite.

Sprint Retrospective (sprint-retro.html) — the Agile equivalent of a Lessons Learned register, refreshed every sprint.

Compare methodologies — see how this differs from PMBOK/predictive delivery and federal civilian contracting in the other two suites.