## Product Backlog
Product Backlog — MedConnect Mobile (34 stories, 241 pts shown)
Epic | ID | Story | Priority | Pts | Sprint | Team
EPIC-1 Patient Identity & Onboarding | MCM-101 | New patient can create account with email/phone verification | Must | 5 | 1 | Falcon
| MCM-102 | Biometric login after initial setup | Should | 3 | 1 | Falcon
| MCM-103 | Link existing ACME Health record via secure identity match | Must | 8 | 1 | Falcon
| MCM-104 | Set up and manage patient profile | Must | 5 | 1 | Falcon
| MCM-105 | Password reset self-service flow | Should | 3 | 2 | Falcon
| MCM-106 | Guided first-run tutorial | Could | 2 | 2 | Falcon
EPIC-2 Appointment Scheduling & Reminders | MCM-110 | Search appointment by provider/specialty | Must | 8 | 2 | Falcon
| MCM-111 | Book/reschedule/cancel appointment | Must | 8 | 2 | Falcon
| MCM-112 | 24hr/15min reminder notifications | Must | 5 | 2 | Falcon
| MCM-113 | Add appointment to native calendar | Could | 2 | 3 | Falcon
| MCM-114 | Pre-visit intake questionnaire | Should | 5 | 3 | Falcon
EPIC-3 Video Visit Experience | MCM-120 | Join video visit with one tap | Must | 8 | 3 | Falcon
| MCM-121 | Video SDK integration w/ audio fallback | Must | 13 | 3 | Anchor
| MCM-122 | Waiting room state with estimated wait | Should | 3 | 4 | Falcon
| MCM-123 | Provider screen-share of lab results/images | Should | 8 | 4 | Falcon
| MCM-124 | Encrypt session metadata for HIPAA audit | Must | 8 | 4 | Anchor
| MCM-125 | 5-min rejoin grace window on dropped connection | Must | 5 | 5 | Falcon
EPIC-4 Provider Console | MCM-130 | Provider daily schedule, unified view | Must | 8 | 3 | Anchor
| MCM-131 | Launch visit directly from schedule | Must | 5 | 4 | Anchor
| MCM-132 | View patient intake questionnaire pre-visit | Should | 5 | 4 | Anchor
| MCM-133 | Visit notes push to EHR without re-entry | Must | 13 | 6 | Anchor
| MCM-134 | Flag patient case for follow-up/referral | Could | 3 | 6 | Anchor
EPIC-5 Data Migration & Decommission | MCM-140 | Build migration pipeline & field-mapping | Must | 13 | 1 | Anchor
| MCM-141 | Migrate active-patient records + validation | Must | 13 | 4 | Anchor
| MCM-142 | Pre-cutover data-integrity validation report | Must | 5 | 4 | Anchor
| MCM-143 | Migrate full historical records | Must | 13 | 7 | Anchor
| MCM-144 | Decommission CareLink Classic infrastructure | Must | 8 | 8 | Anchor
| MCM-145 | Read-only archival export per retention policy | Must | 5 | 8 | Anchor
EPIC-6 Messaging & Prescription Refills | MCM-150 | Secure patient-to-care-team messaging | Must | 8 | 6 | Both
| MCM-151 | Provider templated-reply messaging | Should | 5 | 6 | Both
| MCM-152 | Prescription refill request | Must | 8 | 7 | Both
| MCM-153 | Refill requests routed to e-prescribing | Must | 8 | 7 | Both
| MCM-154 | Push notification status on refill requests | Could | 2 | 7 | Falcon