## Cost by Category
Program Budget — MedConnect Mobile (Final, May 15 2026 Closeout)
Category | Baseline ($) | Actual ($) | Variance ($)
Internal Labor — Team Falcon (5 FTE) | 520000 | 512000 | -8000
Internal Labor — Team Anchor (5 FTE) | 540000 | 556000 | 16000
Product Owner / Agile Delivery Lead | 126000 | 126000 | 0
Scrum Masters (2) | 168000 | 168000 | 0
Video SDK Vendor License & Support (PulseConnect) | 210000 | 210000 | 0
Cloud Infrastructure | 96000 | 114000 | 18000
Data Migration Contractor Support | 0 | 42000 | 42000
Legacy Vendor Offboarding Fees (Vantix) | 45000 | 45000 | 0
App Store/Play Store Fees & Compliance Tooling | 18000 | 16000 | -2000
Subtotal (Base Budget) | 1660000 | 1728000 | 68000
Contingency Reserve | 127000 | 21000 | -106000
TOTAL PROGRAM BUDGET | 63000 | 61000 | -2000

## Rate Card
Resource Rate Card (Named Roster)
Resource | Role | Blended Rate ($/hr) | Est. Labor Cost ($)
C. Tyrrell | Product Owner & Agile Delivery Lead | 175 | 126000
J. Marsh | Scrum Master, Falcon | 140 | 100800
R. Okafor | Scrum Master, Anchor | 140 | 100800
D. Whitfield | Engineering Lead, Falcon | 165 | 118800
A. Singh | Engineering Lead, Anchor | 165 | 118800
K. Alvarez | iOS Developer | 135 | 97200
S. Park | Android Developer | 135 | 97200
R. Kim | Backend/API Developer | 135 | 97200
N. Osei | QA Engineer, Falcon | 110 | 79200
4 additional Anchor engineers | Backend/Platform Developers | 130 | 374400
Dr. L. Nguyen | CMIO (advisory, ~10%) | 210 | 15120
T. Brannigan | Compliance Director (advisory, ~10%) | 180 | 12960
TOTAL |  |  | 1310400

## Budget Reconciliation
Budget Baseline History — MedConnect Mobile
Item | Amount ($)
Original program budget (pre-CR) | 1790000
CR-01 — Additional Staging/Load-Test Environment (Cloud Infrastructure) | 18000
CR-02 — Contractor Support for Sprint 7 Migration Remediation | 42000
Current Baseline (approved, used for closeout reporting) | 1808000
Note: CR-03 (extending the pre-cutover compliance review window) was schedule-only and carried no budget impact.