## Summary
Cost-Benefit Analysis — MedConnect Mobile
Recommendation: Approve
Positive 7-year NPV of ~$394,000 at 8% discount rate; investment is partly non-discretionary given CareLink Classic vendor end-of-support.
Metric | Value
Initial Investment | 1850000
Annual Net Benefit (Steady State) | 530000
7-Year Simple ROI | 0.7
7-Year NPV @ 8% | 393978.3262

## Benefits Detail
Quantified Annual Benefits (Full Realization)
Category | Annual Value | Basis
Legacy Vendor License Elimination | 340000 | CareLink Classic (Vantix) annual license retired at cutover
Provider Throughput / Visit Capacity Gains | 250000 | Faster visit setup (~6 min to under 2 min) frees provider capacity
Reduced Patient No-Show Rate | 220000 | Mobile reminders reduce missed appointments
Patient Retention / Satisfaction | 180000 | Mobile-first experience reduces churn to competitor telehealth apps
Reduced IT/Help Desk Support Burden | 140000 | Support tickets: ~410/mo to under 150/mo
TOTAL ANNUAL BENEFIT | 1130000

## Costs Detail
Cost Summary
Category | Amount
One-Time Implementation Cost (Year 0) | 1850000
PulseConnect Video SDK License & Support | 210000
Cloud Infrastructure (Hosting) | 114000
Internal Sustainment Team | 220000
Periodic Feature Enhancements | 56000
TOTAL ANNUAL ONGOING COST (Year 1+) | 600000

## Cash Flow
Year | Realization % | Net Cash Flow | Cumulative (Undiscounted) | Cumulative (Discounted)
0 |  | -1850000 | -1850000 | -1850000
1 | 0.6 | 78000 | -1772000 | -1777777.7778
2 | 0.9 | 417000 | -1355000 | -1420267.4897
3 | 1 | 530000 | -825000 | -999536.402
4 | 1 | 530000 | -295000 | -609970.58
5 | 1 | 530000 | 235000 | -249261.4856
6 | 1 | 530000 | 765000 | 84728.4167
7 | 1 | 530000 | 1295000 | 393978.3262