00 · PROGRAM SETUP

Program Charter

MedConnect Mobile

1. Purpose & Business Case

This charter formally authorizes the MedConnect Mobile program and grants C. Tyrrell authority as Product Owner & Agile Delivery Lead to apply ACME Health resources to it. CareLink Classic's vendor announced end-of-support 18 months out, with no mobile roadmap ever delivered and a 34% renewal price increase at last cycle. Full business case in the companion Cost-Benefit Analysis.

2. Objectives & Success Criteria

3. High-Level Scope

In scope: patient mobile app (iOS/Android), provider web console, video visit integration, full patient-record migration, CareLink Classic decommission, secure messaging and prescription refills.

Out of scope (candidate backlog): remote patient monitoring integration, multi-language support, group/family visit scheduling, provider analytics dashboard.

4. Delivery Approach

Scrum, two coordinating teams (Falcon/Mobile, Anchor/Platform) via a lightweight Scrum-of-Scrums — not full SAFe, which this program's size doesn't warrant.

5. High-Level Risks

6. Summary Milestone Schedule

| Milestone | Target |
| --- | --- |
| Program Kickoff / Sprint 0 | Jan 5, 2026 |
| Release 1 (MVP) | Mar 27, 2026 (Sprint 5) |
| Release 2 (Full Cutover) | May 8, 2026 (Sprint 8) |
| Program Closeout | May 15, 2026 |

7. Summary Budget

Approved baseline: $1,850,000. Full detail in the Program Budget.

8. Key Stakeholders

| Name | Role |
| --- | --- |
| M. Delacroix | Executive Sponsor, VP Digital Health |
| C. Tyrrell | Product Owner & Agile Delivery Lead |
| Dr. L. Nguyen | Chief Medical Information Officer |
| T. Brannigan | Director, Information Security & Compliance |

9. Product Owner Authority

C. Tyrrell has authority to prioritize/re-prioritize the backlog within approved scope and budget, facilitate the Scrum-of-Scrums, and represent the program to the Steering Committee. Baseline changes require Sponsor approval via formal Change Request.

10. Assumptions & Constraints

11. Approval

Approved: M. Delacroix, Executive Sponsor  |  C. Tyrrell, Product Owner & Agile Delivery Lead