METRICS & REPORTING

Program Dashboard

MedConnect Mobile   |   Closed — Complete   |   As of May 15, 2026

Program Health

| Dimension | Status |
| --- | --- |
| Overall | Green — Closed on target |
| Schedule | Green — On time |
| Scope | Green — 98.5% delivered |
| Budget | Green — -2.2% to baseline |
| Quality | Green — 0 critical defects |

Release Timeline

Kickoff (Jan 5) -> Release 1/MVP (Mar 27) -> Release 2/Cutover (May 8) -> Closeout (May 15). All milestones met on original target dates.

Budget

Spend to date: $1.81M of $1.85M (97.8%). Contingency remaining: $106K of $127K. Variance to baseline: -2.2%. 3 approved CRs, all Implemented.

RAIDD Summary

| Category | Count | Note |
| --- | --- | --- |
| Risks | 4 | All closed |
| Assumptions | 3 | All held true |
| Issues | 2 | 1 closed, 1 accepted |
| Dependencies | 3 | All resolved |
| Decisions | 5 | All approved |

Vendor Readiness

| Vendor | Status |
| --- | --- |
| PulseConnect (video SDK) | SLA met, renewal recommended |
| Vantix (legacy, offboarded) | Decommissioned, deletion cert. pending |