GOVERNANCE & STAKEHOLDER

Program Governance Model

MedConnect Mobile

1. Purpose & Principles

Defines who has authority to decide and how exceptions are resolved — lighter than a PMBOK governance model, sized to a two-team, 18-week program.

2. Governance Structure

Executive Sponsor (M. Delacroix) -> Product Owner & Agile Delivery Lead (C. Tyrrell) -> two Scrum teams, with matrixed advisory lines to Clinical (Dr. Nguyen) and Compliance (T. Brannigan). Full detail in the Organizational Chart.

3. Decision Rights

| Tier | Decision Type | Authority |
| --- | --- | --- |
| 1 | Backlog prioritization, re-estimation, story splits | Product Owner |
| 2 | Cost/schedule/scope-boundary change | Executive Sponsor (formal CR) |
| 3 | Clinical workflow or PHI/compliance exception | CMIO / Compliance Director |

4. Escalation Process

Scrum Master resolves within team -> Scrum-of-Scrums for cross-team blockers -> Product Owner escalates to Sponsor/Clinical/Compliance -> Sponsor decision if scope/budget/timeline affected.

5. Meeting Cadence & Reporting

| Cadence | Forum | Purpose |
| --- | --- | --- |
| Daily | Team Standup | Coordination, blockers |
| 2x/week | Scrum-of-Scrums | Cross-team dependency sync |
| Per sprint | Review + Retrospective | Stakeholder demo; team improvement |
| Monthly | Steering Committee | Formal program-health review |

6. Change Control Governance

Formal budget/schedule baseline changes are logged on the Change Control Log. Backlog reprioritization within approved scope does not require this process.

7. Vendor Governance

Two vendors, two models: PulseConnect (active, ongoing SLA management) and Vantix Health Systems (outgoing, checklist-driven offboarding). Vendor contract changes with cost impact require Sponsor approval.

8. Release Gates

| Gate | Go/No-Go Criteria | Approval |
| --- | --- | --- |
| Release 1 (MVP) | All acceptance criteria met; zero P1/P2; Compliance/Clinical sign-off | Executive Sponsor |
| Release 2 (Cutover) | Full migration validated; decommission-ready; Compliance sign-off | Executive Sponsor |

9. Compliance & Clinical Oversight

Any PHI or clinical-workflow story cannot be marked Done, and no release can go live, without sign-off from Compliance (and Clinical for workflow changes) — regardless of schedule pressure. A standing exception to normal Product Owner decision rights.

10. Performance Monitoring

Monitored via the Velocity Chart and Release Burnup, reported monthly via the Steering Committee Deck. Thresholds: predictability >= 90%, zero open P1/P2 at release gates, budget variance within Contingency Reserve.

11. Approval

Approved: M. Delacroix, Executive Sponsor  |  C. Tyrrell, Product Owner & Agile Delivery Lead