## WBS
MedConnect Mobile — Work Breakdown Structure
Full export from the program schedule — 102 line items across 6 phases, 13 named assignees.
WBS ID | Task Name | Duration (d) | Assigned To | Milestone
1 | Program Setup & Release 1 Planning (Sprints 1-2) | 20 | C. Tyrrell
1.1 | Program foundations | 8 | C. Tyrrell
1.1.1 | Vision & Roadmap workshop — patient-facing goals | 1 | C. Tyrrell
1.1.2 | Vision & Roadmap workshop — provider-facing goals | 1 | C. Tyrrell
1.1.3 | Team Charter & Working Agreement — Falcon | 1 | J. Marsh
1.1.4 | Team Charter & Working Agreement — Anchor | 1 | R. Okafor
1.1.5 | Definition of Ready drafting | 1 | C. Tyrrell
1.1.6 | Definition of Done drafting — incl. PHI/clinical review gate | 1 | C. Tyrrell
1.1.7 | Program Kickoff meeting (both teams + stakeholders) | 2 | C. Tyrrell
1.2 | Sprint 1 — Foundation work | 10 | J. Marsh
1.2.1 | Falcon: iOS app scaffolding & CI setup | 5 | K. Alvarez
1.2.2 | Falcon: Android app scaffolding & CI setup | 5 | S. Park
1.2.3 | Falcon: authentication flow — login screen | 3 | K. Alvarez
1.2.4 | Falcon: authentication flow — session/token handling | 3 | S. Park
1.2.5 | Anchor: video SDK integration spike — PulseConnect API eval | 5 | R. Kim
1.2.6 | Anchor: video SDK integration spike — BAA/compliance review | 2 | R. Kim
1.2.7 | Anchor: legacy data schema analysis — patient records | 5 | A. Singh
1.2.8 | Anchor: legacy data schema analysis — appointment history | 3 | A. Singh
1.3 | Sprint 2 — Backlog refinement & estimation | 2 | J. Marsh
1.3.1 | Release 1 backlog refinement — Falcon stories | 1 | C. Tyrrell
1.3.2 | Release 1 backlog refinement — Anchor stories | 1 | C. Tyrrell
1.3.3 | Story estimation — Falcon (planning poker) | 1 | J. Marsh
1.3.4 | Story estimation — Anchor (planning poker) | 1 | R. Okafor
1.4 | Technical Design Review (pre-build gate) | 2 | D. Whitfield
1.4.1 | Architecture spike review — mobile app + video SDK integration | 1 | D. Whitfield
1.4.2 | Architecture spike review — data migration approach | 1 | A. Singh
1.4.3 | Compliance/Security sign-off on technical approach (PHI handling) | 1 | M. Delacroix
2 | Release 1 (MVP) Build — Sprints 2-4 | 30 | D. Whitfield
2.1 | Team Falcon: mobile booking flow | 30 | D. Whitfield
2.1.1 | Search appointment by provider — iOS | 4 | K. Alvarez
2.1.2 | Search appointment by specialty — iOS | 4 | K. Alvarez
2.1.3 | Search appointment by provider/specialty — Android | 8 | S. Park
2.1.4 | Book appointment flow — iOS | 4 | K. Alvarez
2.1.5 | Reschedule/cancel appointment flow — iOS | 4 | K. Alvarez
2.1.6 | Book/reschedule/cancel appointment — Android | 8 | S. Park
2.1.7 | Password reset self-service flow — iOS | 3 | K. Alvarez
2.1.8 | Password reset self-service flow — Android | 3 | S. Park
2.1.9 | First-run guided tutorial — iOS | 2 | K. Alvarez
2.1.10 | First-run guided tutorial — Android | 4 | S. Park
2.1.11 | 24hr reminder notification logic | 3 | T. Nguyen
2.1.12 | 15min reminder notification logic | 2 | T. Nguyen
2.2 | Team Anchor: platform & integration | 30 | A. Singh
2.2.1 | Availability engine — provider schedule model | 5 | R. Kim
2.2.2 | Availability engine — conflict detection logic | 5 | R. Kim
2.2.3 | Reminder notification service — backend queue | 3 | R. Kim
2.2.4 | Reminder notification service — delivery integration | 3 | R. Kim
2.2.5 | Video SDK integration — call setup/teardown | 4 | R. Kim
2.2.6 | Video SDK integration — screen share & recording controls | 4 | R. Kim
2.2.7 | Migration pipeline — field-mapping spec | 3 | A. Singh
2.2.8 | Migration pipeline — QA & dry-run | 3 | N. Osei
2.3 | QA — Release 1 | 30 | E. Marchetti
2.3.1 | Falcon regression test pass — Sprint 2 | 10 | E. Marchetti
2.3.2 | Falcon regression test pass — Sprint 3 | 10 | E. Marchetti
2.3.3 | Falcon regression test pass — Sprint 4 | 10 | E. Marchetti
2.3.4 | Anchor regression test pass — Sprint 2 | 10 | N. Osei
2.3.5 | Anchor regression test pass — Sprint 3 | 10 | N. Osei
2.3.6 | Anchor regression test pass — Sprint 4 | 10 | N. Osei
2.3.7 | Offshore QA support — migration validation | 10 | M. Chen
2.3.8 | Offshore QA support — scheduling engine validation | 10 | P. Kumar
3 | Release 1 Hardening & Launch — Sprint 5 | 10 | C. Tyrrell
3.1 | MVP defect triage — P1 fixes | 3 | S. Park
3.2 | MVP defect triage — P2 fixes | 2 | K. Alvarez
3.3 | 5-min rejoin grace window (video visits) — iOS | 2 | K. Alvarez
3.4 | 5-min rejoin grace window (video visits) — Android | 2 | S. Park
3.5 | Pre-cutover compliance review — initial pass | 3 | M. Delacroix
3.6 | Pre-cutover compliance review — extended window (CR-03) | 2 | M. Delacroix
3.7 | App Store submission build & review | 2 | S. Park
3.8 | Play Store submission build & review | 2 | S. Park
3.9 | Milestone Gate: Release 1 Go/No-Go | 1 | M. Delacroix
3.10 | Release 1 launch to pilot cohort | 1 | C. Tyrrell
4 | Release 2 (Cutover) Build — Sprints 6-7 | 20 | A. Singh
4.1 | Team Falcon: Release 2 features | 20 | D. Whitfield
4.1.1 | SMS notification vendor integration (CR-06) | 4 | T. Nguyen
4.1.2 | Push notification vendor integration (CR-06) | 4 | T. Nguyen
4.1.3 | Production monitoring — crash reporting setup | 3 | T. Nguyen
4.1.4 | Production monitoring — alerting & dashboards | 3 | T. Nguyen
4.1.5 | WCAG accessibility audit — iOS remediation (CR-08) | 3 | K. Alvarez
4.1.6 | WCAG accessibility audit — Android remediation (CR-08) | 3 | S. Park
4.2 | Team Anchor: full data migration | 20 | A. Singh
4.2.1 | Full historical record migration — patient records | 5 | R. Kim
4.2.2 | Full historical record migration — appointment history | 5 | R. Kim
4.2.3 | Pre-cutover data-integrity validation — automated checks | 3 | N. Osei
4.2.4 | Pre-cutover data-integrity validation — manual spot-check | 3 | N. Osei
4.2.5 | Production infrastructure scaling | 2 | R. Kim
4.2.6 | Production load test — full cutover simulation | 2 | R. Kim
4.3 | Family Caregiver Proxy Access deferred to backlog (CR-09) | 1 | C. Tyrrell
5 | Release 2 Cutover & Decommission — Sprint 8 | 10 | C. Tyrrell
5.1 | Final cutover verification — Compliance review | 2 | N. Osei
5.2 | Final cutover verification — Clinical workflow sign-off | 1 | N. Osei
5.3 | Cutover execution — data freeze & final sync | 1 | R. Kim
5.4 | Cutover execution — DNS/traffic switchover | 1 | R. Kim
5.5 | Decommission CareLink Classic — data archival export | 2 | A. Singh
5.6 | Decommission CareLink Classic — vendor offboarding certification | 1 | A. Singh
5.7 | Final release notes & app store listing update | 3 | S. Park
5.8 | Milestone Gate: Release 2 Go/No-Go — Full Cutover | 1 | M. Delacroix
6 | Post-Cutover Hypercare & Closeout | 15 | C. Tyrrell
6.1 | Full-team hypercare support — week 1-2 (CR-10) | 10 | J. Marsh
6.2 | Full-team hypercare support — offshore QA coverage | 10 | M. Chen
6.3 | Sprint Retrospective — program closeout | 2 | J. Marsh
6.4 | Program Closeout Report — draft | 2 | C. Tyrrell
6.5 | Lessons Learned Register — compile & finalize | 3 | C. Tyrrell
6.6 | Milestone: Program Closed | 0 | C. Tyrrell | Yes