## Risks
Agile RAIDD Log — Risks
ID | Risk | Severity | Mitigation | Status
R-01 | Historical migration (Sprint 7) could surface data-quality issues | Medium | Pre-cutover validation + spot-check process | Closed
R-02 | Video SDK screen-share may need additional vendor configuration | Medium | Spike performed Sprint 3; re-estimated MCM-123 | Closed
R-03 | Cross-team dependencies surfacing too late in a sprint | Medium | Sprint 2 retro actions — dependency owner, standing SoS item | Closed
R-04 | Team cost run-rate tracking ahead of planned burn | Medium | Monitored weekly; no contractor hours added beyond CR-02 | Closed

## Assumptions
Assumptions
ID | Assumption | Validated?
A-01 | PulseConnect's existing BAA covers the telehealth use case | Confirmed, Sprint 3 Planning
A-02 | Both teams sustain 2-week cadence without disruption | Held true
A-03 | Pilot cohort representative enough to surface usability issues | Held true

## Issues
Issues
ID | Issue | Severity | Resolution | Status
I-01 | MCM-111 blocked waiting on MCM-160 review | Medium | Same-day escalation between Eng Leads | Closed, Sprint 2
I-02 | MCM-181 descoped from formal board tracking | Low | Accepted, one-off, no recurrence | Accepted

## Dependencies
Dependencies
ID | Dependency | Owner | Status
D-01 | Falcon booking UI depends on Anchor availability API | A. Singh | Resolved, Sprint 2
D-02 | Falcon video join depends on Anchor SDK integration | A. Singh | Resolved, Sprint 3-4
D-03 | Release 2 cutover depends on Compliance sign-off | T. Brannigan | Resolved, Sprint 8

## Decisions
Decisions
ID | Decision | Made At | Made By
DEC-01 | DoD requires clinical sign-off for workflow-changing stories | Program Kickoff | Dr. Nguyen
DEC-02 | Compliance checkpoint before both Release 1 and Release 2 | Program Kickoff | T. Brannigan
DEC-03 | Split MCM-133 into data-mapping + UI stories | Sprint 3 Refinement | C. Tyrrell + teams
DEC-04 | Hold Release 1 to pilot cohort, not full rollout | Sprint 5 Review | M. Delacroix
DEC-05 | Release 2 Go/No-Go: GO | Sprint 8 Review | M. Delacroix