## Release Burnup
Release Burnup — MedConnect Mobile, All 8 Sprints
Sprint | Cumulative Delivered (pts) | Total Scope (pts) | Note
Sprint 0 | 0 | 339
Sprint 1 | 34 | 339
Sprint 2 | 75 | 339
Sprint 3 | 115 | 342 | Scope re-estimation (+3, MCM-123)
Sprint 4 | 159 | 342
Sprint 5 | 205 | 342 | Release 1 (MVP) milestone
Sprint 6 | 247 | 342
Sprint 7 | 291 | 342
Sprint 8 | 337 | 342 | Release 2 (Cutover) milestone