Team Resource Plan

MedConnect Mobile · Agile/Scrum Program Suite

| Program | MedConnect Mobile |
| --- | --- |
| Duration | 18.5 weeks — Jan 5, 2026 to May 15, 2026 (Closeout) |
| Delivery Lead | C. Tyrrell |
| Named Team Members | 13 (11 onshore, 2 offshore) |
| Total Reconciled Delivery Labor | $1,362,000 |

1. Purpose

This Resource Plan names the full MedConnect Mobile delivery roster across Teams Falcon and Anchor, showing FTE allocation, location, blended hourly rate, and program cost — reconciled line-for-line to the Internal Labor entries in the Program Budget.

2. Delivery Leadership & Scrum Masters

| Name | Role | Location | FTE % | Blended Rate | Program | Cost |
| --- | --- | --- | --- | --- | --- | --- |
| C. Tyrrell | Product Owner / Agile Delivery Lead | Onshore (US) | 100% | $170.27 | 740 hrs | $126,000 |
| J. Marsh | Scrum Master — Falcon | Onshore (US) | 100% | $114.86 | 740 hrs | $85,000 |
| R. Okafor | Scrum Master — Anchor | Onshore (US) | 100% | $112.16 | 740 hrs | $83,000 |

| Subtotal (PO + Scrum Masters) |  |  |  |  |  | $294,000 |
| --- | --- | --- | --- | --- | --- | --- |

3. Team Falcon — Mobile (5 FTE)

| Name | Role | Location | FTE % | Blended Rate | Program | Cost |
| --- | --- | --- | --- | --- | --- | --- |
| D. Whitfield | Engineering Lead | Onshore (US) | 100% | $240.54 | 740 hrs | $178,000 |
| K. Alvarez | iOS Developer | Onshore (US) | 100% | $151.35 | 740 hrs | $112,000 |
| S. Park | Android Developer | Onshore (US) | 100% | $151.35 | 740 hrs | $112,000 |
| T. Nguyen | Backend Developer | Onshore (US) | 50% | $183.78 | 370 hrs | $68,000 |
| E. Marchetti | QA Lead — Falcon | Onshore (US) | 50% | $113.51 | 370 hrs | $42,000 |

| Subtotal — Team Falcon (5 FTE) |  |  |  |  |  | $512,000 |
| --- | --- | --- | --- | --- | --- | --- |

4. Team Anchor — Platform (5 FTE)

Anchor is the program's only team with offshore capacity — both manual QA analysts are based in India.

| Name | Role | Location | FTE % | Blended Rate | Program | Cost |
| --- | --- | --- | --- | --- | --- | --- |
| A. Singh | Engineering Lead | Onshore (US) | 100% | $267.57 | 740 hrs | $198,000 |
| R. Kim | Backend Developer | Onshore (US) | 100% | $218.92 | 740 hrs | $162,000 |
| N. Osei | QA Lead (Onshore) | Onshore (US) | 100% | $154.05 | 740 hrs | $114,000 |
| M. Chen | QA Analyst (Manual) | Offshore (India) | 100% | $55.41 | 740 hrs | $41,000 |
| P. Kumar | QA Analyst (Manual) | Offshore (India) | 100% | $55.41 | 740 hrs | $41,000 |

| Subtotal — Team Anchor (5 FTE) |  |  |  |  |  | $556,000 |
| --- | --- | --- | --- | --- | --- | --- |

5. Reconciliation to Program Budget

| Budget Line | Resource Plan Total | Program Budget Actual | Variance |
| --- | --- | --- | --- |
| PO / Delivery Lead (C. Tyrrell) | $126,000 | $126,000 | $0 |
| Scrum Masters (2) | $168,000 | $168,000 | $0 |
| Team Falcon (5 FTE) | $512,000 | $512,000 | $0 |
| Team Anchor (5 FTE) | $556,000 | $556,000 | $0 |

| Total Reconciled Delivery Labor | $1,362,000 | $1,362,000 | $0 |
| --- | --- | --- | --- |

6. Notes

Blended Hourly Rate is a fully loaded internal cost-recovery rate (salary, benefits, overhead allocation, and program margin), consistent with the Internal Labor lines in the Program Budget. Figures are illustrative for portfolio demonstration purposes.