## Resource Plan
MedConnect Mobile — Team Resource Plan (18.5-Week Program, Jan 5 – May 15, 2026) | [7 empty] | Program Hours (18.5 wks x 40 hrs, 100% FTE): | 740
Team | Name | Role | Location | FTE % | Program Hours | Blended Hourly Rate ($) | Program Cost ($)
Delivery Leadership | C. Tyrrell | Product Owner / Agile Delivery Lead | Onshore (US) | 100% | 740 | 170.2703 | 126000
Scrum Masters | J. Marsh | Scrum Master — Team Falcon | Onshore (US) | 100% | 740 | 114.8649 | 85000
Scrum Masters | R. Okafor | Scrum Master — Team Anchor | Onshore (US) | 100% | 740 | 112.1622 | 83000
Team Falcon | D. Whitfield | Engineering Lead | Onshore (US) | 100% | 740 | 240.5405 | 178000
Team Falcon | K. Alvarez | iOS Developer | Onshore (US) | 100% | 740 | 151.3514 | 112000
Team Falcon | S. Park | Android Developer | Onshore (US) | 100% | 740 | 151.3514 | 112000
Team Falcon | T. Nguyen | Backend Developer | Onshore (US) | 50% | 370 | 183.7838 | 68000
Team Falcon | E. Marchetti | QA Lead — Falcon | Onshore (US) | 50% | 370 | 113.5135 | 42000
Team Anchor | A. Singh | Engineering Lead | Onshore (US) | 100% | 740 | 267.5676 | 198000
Team Anchor | R. Kim | Backend Developer | Onshore (US) | 100% | 740 | 218.9189 | 162000
Team Anchor | N. Osei | QA Lead — Anchor (Onshore) | Onshore (US) | 100% | 740 | 154.0541 | 114000
Team Anchor | M. Chen | QA Analyst (Manual) | Offshore (India) | 100% | 740 | 55.4054 | 41000
Team Anchor | P. Kumar | QA Analyst (Manual) | Offshore (India) | 100% | 740 | 55.4054 | 41000
Reconciliation to Program Budget (Actual Labor Lines)
Budget Line | Resource Plan Total ($) | Program Budget Actual ($) | Variance ($)
PO / Delivery Lead (C. Tyrrell) | 126000 | 126000 | 0
Scrum Masters (2) | 168000 | 168000 | 0
Team Falcon (5 FTE) | 512000 | 512000 | 0
Team Anchor (5 FTE) | 556000 | 556000 | 0
Total Reconciled Delivery Labor | 1362000 | 1362000
Note: Blended Hourly Rate is a fully loaded internal cost-recovery rate (salary, benefits, overhead allocation, and program margin), consistent with the Internal Labor lines in the Program Budget — not a raw take-home wage. Figures are illustrative for portfolio demonstration purposes.