## Sprint 2
Sprint 2 — Feb 2-13, 2026 ¦ Goal: Patients can search, book, and receive a reminder end-to-end
ID | Story | Team | Pts | Status
MCM-105 | Password reset self-service flow | Falcon | 3 | Done
MCM-106 | First-run guided tutorial | Falcon | 2 | Carried to Sprint 3
MCM-110 | Search appointment by provider/specialty | Falcon | 8 | Done
MCM-111 | Book/reschedule/cancel appointment | Falcon | 8 | Done
MCM-112 | 24hr/15min reminder notifications | Falcon | 5 | Carried to Sprint 3
MCM-140b | Migration pipeline hardening (spillover) | Anchor | 8 | Done
MCM-160 | Availability engine & conflict detection | Anchor | 8 | Done
MCM-161 | Reminder notification service | Anchor | 4 | Done

## Sprint 5
Sprint 5 — Mar 16-27, 2026 ¦ Goal: Release 1 hardened, zero P1/P2, live to pilot cohort
ID | Story | Team | Pts | Status
MCM-125 | 5-min rejoin grace window | Falcon | 5 | Done
MCM-170 | MVP defect triage: P1/P2 fixes | Falcon | 13 | Done
MCM-171 | App Store/Play Store release build | Falcon | 5 | Done
MCM-172 | Production monitoring & crash reporting | Falcon | 3 | Done
MCM-142 | Pre-cutover data-integrity validation report | Anchor | 5 | Done
MCM-141b | Active-patient migration final validation | Anchor | 8 | Done
MCM-180 | Production infra scaling & load test | Anchor | 7 | Done
MCM-181 | Rollback runbook & go-live checklist | Anchor | 2 | Descoped, done manually

## Sprint 8
Sprint 8 — Apr 27-May 8, 2026 ¦ Goal: Full migration complete, decommission, Release 2 live
ID | Story | Team | Pts | Status
MCM-154 | Refill request status push notifications | Falcon | 2 | Done
MCM-190 | Release 2 full regression pass | Falcon | 10 | Done
MCM-191 | Post-launch support FAQ & help content | Falcon | 3 | Done
MCM-192 | Release notes & app store listing update | Falcon | 3 | Done
MCM-143 | Full historical record migration | Anchor | 13 | Done
MCM-144 | Decommission CareLink Classic infrastructure | Anchor | 8 | Done
MCM-145 | Read-only archival export | Anchor | 5 | Carried to post-program
MCM-193 | Final cutover verification & sign-off | Anchor | 4 | Done