## Slide 1
MONTHLY STEERING COMMITTEE UPDATE
MedConnect Mobile
Sprint 6 Checkpoint · Apr 10, 2026 · Presented by C. Tyrrell · ACME Health

## Slide 2
1 / 7
Program Status at a Glance
OVERALL
Green
SCHEDULE
Green
SCOPE
Green
BUDGET
Amber
QUALITY
Green
Release 1 (MVP) is live with the pilot patient cohort since Sprint 5, zero critical defects. Release 2 (full cutover) remains on track for Sprint 8, May 8.

## Slide 3
2 / 7
Delivery Progress
Sprints Complete
6 of 8
Avg. Velocity
43 pts/sprint
Predictability
~94%
Scope Delivered
247 / 342 pts
See the Velocity Chart and Release Burnup pages for full detail.

## Slide 4
3 / 7
Release Timeline
Milestone | Date | Status
Release 1 (MVP) — pilot cohort go-live | Mar 27, 2026 | Complete
Full historical data migration | Apr 24, 2026 | On track
Release 2 — full cutover & decommission | May 8, 2026 | On track

## Slide 5
4 / 7
Top Risks
MEDIUM Full historical migration (Sprint 7) is the largest remaining story — limited slack if legacy data-quality issues surface
MEDIUM Budget run-rate tracking slightly ahead of plan heading into the highest-effort remaining sprint — monitored, no action needed yet
Full detail in the Agile RAIDD Log.

## Slide 6
5 / 7
Budget
TOTAL PROGRAM BUDGET
$1.85M
SPENT TO DATE (76.8%)
$1.42M
77.8% of program duration elapsed — effectively on track.

## Slide 7
6 / 7
Team Health
● Both teams maintained consistent velocity and predictability across the program — no burnout indicators, no unplanned attrition
● Sprint 2's cross-team dependency friction was identified and resolved by the team itself (Sprint 2 Retrospective) — a good sign of team maturity

## Slide 8
7 / 7
Decision Requested / Next Steps
No Sponsor decision required this cycle.
Program remains within approved scope, schedule, and budget tolerance. Next Steering Committee update will include the Release 2 Go/No-Go outcome following Sprint 8 Review.