01 · SPRINT 0 · PROGRAM SETUP

Vision & Roadmap

MedConnect Mobile   |   ACME Health

## Vision

"Every ACME Health patient can find, book, and complete a video visit with their provider from their phone in under two minutes — and every provider can run their telehealth day from one console, without the workarounds CareLink Classic forces on them today."

## Business Drivers

| Driver | Why It Matters Now |
| --- | --- |
| Vendor end-of-life | CareLink Classic vendor announced end-of-support in 18 months; renewal pricing increased 34% last cycle. |
| Patient experience gap | Desktop-only web portal; competitor telehealth apps are mobile-first. |
| Provider efficiency | Providers toggle between CareLink Classic and the EHR; ~6 min visit setup time. |
| Scalability | CareLink Classic is priced per-desktop-seat, doesn't scale for telehealth-only contractors. |

## Success Metrics (Program-Level OKRs)

| Objective | Key Result | Baseline → Target |
| --- | --- | --- |
| Patients self-serve mobile visits | % of visits booked via mobile app | 0% → 60% within 60 days live |
| Reduce provider setup friction | Avg. time login to visit start | ~6 min → under 2 min |
| Cut legacy support burden | Support tickets/month | ~410/mo → under 150/mo |
| Safe cutover | Records migrated, zero critical defects | 100% validated pre-cutover |
| Provider adoption | Console DAU, week 4 post-launch | ≥ 85% of scheduled providers |

## Release Roadmap

| Release | Sprints | Scope |
| --- | --- | --- |
| Now — Release 1 (MVP) | 1–5 | Patient login, scheduling, video visit parity, provider console core, active-patient migration |
| Next — Release 2 (Full Cutover) | 6–8 | Messaging, refills, full historical migration + legacy decommission, EHR notes handoff |
| Later — Candidate Backlog | Post-program | Remote monitoring integration, multi-language, group visits, analytics dashboard |

## Program Timeline

| Sprint | Dates | Focus |
| --- | --- | --- |
| Sprint 0 | Jan 5–16 | Setup, environments, backlog seeding |
| Sprint 1 | Jan 19–30 | Auth & onboarding |
| Sprint 2 | Feb 2–13 | Scheduling core |
| Sprint 3 | Feb 16–27 | Video visit integration |
| Sprint 4 | Mar 2–13 | Provider console v1 |
| Sprint 5 | Mar 16–27 | MVP hardening & Release 1 launch |
| Sprint 6 | Mar 30–Apr 10 | Messaging & refills |
| Sprint 7 | Apr 13–24 | Full data migration |
| Sprint 8 | Apr 27–May 8 | Release 2 cutover & decommission |