## WBS
Project Catalyst — Resource-Loaded WBS
ACME Highland Health / Pulaski Advisory Group — status date 11 Sep 2026 — illustrative program data
Line items |  |  | Work tasks
WBS | Task Name | Level | Type | Start | Finish | Dur (d) | % Comp | Predecessors | Accountable Owner | Contributors (named) | Team (group activity) | Effort (hrs)
1.0 | Program Management & PMO | 1 | Summary | 2026-08-17 | 2029-07-27 | 770 | 6%
1.0.1 | Program Initiation & Mobilization | 2 | Summary | 2026-08-17 | 2026-10-22 | 49 | 41%
1.0.1.1 | Charter finalization & approval | 3 | Task | 2026-08-17 | 2026-08-24 | 6 | 100% |  | C. Tyrrell | M. Kavanagh |  | 55
1.0.1.2 | Program kickoff & team mobilization | 3 | Task | 2026-08-25 | 2026-08-31 | 5 | 100% | 1.0.1.1 | T. Valdez | K. Anderson, M. Kavanagh |  | 86
1.0.1.3 | PMO stand-up & tooling setup | 3 | Summary | 2026-09-01 | 2026-09-10 | 8 | 100%
1.0.1.3.1 | Schedule & EVM tooling | 4 | Task | 2026-09-01 | 2026-09-04 | 4 | 100% | 1.0.1.2 | K. Anderson | J. Wright |  | 64
1.0.1.3.2 | Collaboration & RAIDD tooling | 4 | Task | 2026-09-07 | 2026-09-10 | 4 | 100% | 1.0.1.3.1 | J. Wright | D. Lee |  | 64
1.0.1.4 | Staffing ramp & onboarding | 3 | Summary | 2026-09-11 | 2026-09-24 | 10 | 10%
1.0.1.4.1 | Onshore staffing & onboarding | 4 | Group task | 2026-09-11 | 2026-09-17 | 5 | 20% | 1.0.1.3 | D. Ferraro | F. Bianchi, E. Marsh, G. Solberg, C. Johnson | HR / Workforce Planning & Org Design (6) | 156
1.0.1.4.2 | Offshore staffing & onboarding | 4 | Group task | 2026-09-18 | 2026-09-24 | 5 | 0% | 1.0.1.4.1 | D. Ferraro | E. Marsh, G. Solberg, H. Rutherford, C. Johnson | HR / Workforce Planning & Org Design (6) | 144
1.0.1.5 | Integrated baseline schedule & budget | 3 | Task | 2026-09-25 | 2026-10-06 | 8 | 0% | 1.0.1.4 | D. Lee | M. Torres, P. Davis |  | 192
1.0.1.6 | Communications & stakeholder plan | 3 | Task | 2026-10-07 | 2026-10-14 | 6 | 0% | 1.0.1.5 | R. Castellanos | B. Sullivan |  | 57
1.0.1.7 | RAIDD register & risk baseline | 3 | Task | 2026-10-15 | 2026-10-22 | 6 | 0% | 1.0.1.6 | P. Davis | S. Chen |  | 96
1.0.2 | Steering & Governance Reporting | 2 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
1.0.2.1 | Steering board prep & reporting — Y1 Q1 | 3 | Task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | S. Chen | R. Johnson |  | 240
1.0.2.2 | Steering board prep & reporting — Y1 Q2 | 3 | Task | 2026-12-01 | 2026-12-28 | 20 | 0% |  | N. Gupta | R. Johnson |  | 240
1.0.2.3 | Steering board prep & reporting — Y1 Q3 | 3 | Task | 2027-03-01 | 2027-03-26 | 20 | 0% |  | N. Gupta | L. Martinez |  | 288
1.0.2.4 | Steering board prep & reporting — Y1 Q4 | 3 | Task | 2027-06-01 | 2027-06-28 | 20 | 0% |  | H. Kim | L. Martinez |  | 288
1.0.2.5 | Steering board prep & reporting — Y2 Q1 | 3 | Task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | H. Kim | V. Patel |  | 288
1.0.2.6 | Steering board prep & reporting — Y2 Q2 | 3 | Task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | V. Patel | G. Brown |  | 224
1.0.2.7 | Steering board prep & reporting — Y2 Q3 | 3 | Task | 2028-04-03 | 2028-04-28 | 20 | 0% |  | Q. Wilson | G. Brown |  | 224
1.0.2.8 | Steering board prep & reporting — Y2 Q4 | 3 | Task | 2028-07-03 | 2028-07-28 | 20 | 0% |  | C. Tyrrell | Q. Wilson |  | 288
1.0.2.9 | Steering board prep & reporting — Y3 Q1 | 3 | Task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | C. Tyrrell | M. Kavanagh |  | 184
1.0.2.10 | Steering board prep & reporting — Y3 Q2 | 3 | Task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | T. Valdez | M. Kavanagh |  | 184
1.0.2.11 | Steering board prep & reporting — Y3 Q3 | 3 | Task | 2029-04-02 | 2029-04-27 | 20 | 0% |  | T. Valdez | K. Anderson |  | 320
1.0.2.12 | Steering board prep & reporting — Y3 Q4 | 3 | Task | 2029-07-02 | 2029-07-27 | 20 | 0% |  | K. Anderson | J. Wright |  | 320
1.0.3 | EVM, Forecasting & Financial Management | 2 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
1.0.3.1 | EVM, forecast & financial reporting — Y1 Q1 | 3 | Task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | A. Rodriguez | B. Halvorsen |  | 320
1.0.3.2 | EVM, forecast & financial reporting — Y1 Q2 | 3 | Task | 2026-12-01 | 2026-12-28 | 20 | 0% |  | B. Halvorsen | C. Restrepo |  | 320
1.0.3.3 | EVM, forecast & financial reporting — Y1 Q3 | 3 | Task | 2027-03-01 | 2027-03-26 | 20 | 0% |  | C. Restrepo | D. Vartan |  | 320
1.0.3.4 | EVM, forecast & financial reporting — Y1 Q4 | 3 | Task | 2027-06-01 | 2027-06-28 | 20 | 0% |  | D. Vartan | E. Talbot |  | 304
1.0.3.5 | EVM, forecast & financial reporting — Y2 Q1 | 3 | Task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | E. Talbot | F. Sondheim |  | 272
1.0.3.6 | EVM, forecast & financial reporting — Y2 Q2 | 3 | Task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | A. Rodriguez | F. Sondheim |  | 288
1.0.3.7 | EVM, forecast & financial reporting — Y2 Q3 | 3 | Task | 2028-04-03 | 2028-04-28 | 20 | 0% |  | A. Rodriguez | B. Halvorsen |  | 320
1.0.3.8 | EVM, forecast & financial reporting — Y2 Q4 | 3 | Task | 2028-07-03 | 2028-07-28 | 20 | 0% |  | B. Halvorsen | C. Restrepo |  | 320
1.0.3.9 | EVM, forecast & financial reporting — Y3 Q1 | 3 | Task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | C. Restrepo | D. Vartan |  | 320
1.0.3.10 | EVM, forecast & financial reporting — Y3 Q2 | 3 | Task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | D. Vartan | E. Talbot |  | 304
1.0.3.11 | EVM, forecast & financial reporting — Y3 Q3 | 3 | Task | 2029-04-02 | 2029-04-27 | 20 | 0% |  | E. Talbot | F. Sondheim |  | 272
1.0.3.12 | EVM, forecast & financial reporting — Y3 Q4 | 3 | Task | 2029-07-02 | 2029-07-27 | 20 | 0% |  | A. Rodriguez | F. Sondheim |  | 288
1.0.4 | RAIDD & Change Control Operations | 2 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
1.0.4.1 | RAIDD review & change-control operations — Y1 Q1 | 3 | Task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | J. Wright | D. Lee |  | 320
1.0.4.2 | RAIDD review & change-control operations — Y1 Q2 | 3 | Task | 2026-12-01 | 2026-12-28 | 20 | 0% |  | D. Lee | M. Torres |  | 320
1.0.4.3 | RAIDD review & change-control operations — Y1 Q3 | 3 | Task | 2027-03-01 | 2027-03-26 | 20 | 0% |  | M. Torres | P. Davis |  | 320
1.0.4.4 | RAIDD review & change-control operations — Y1 Q4 | 3 | Task | 2027-06-01 | 2027-06-28 | 20 | 0% |  | P. Davis | S. Chen |  | 320
1.0.4.5 | RAIDD review & change-control operations — Y2 Q1 | 3 | Task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | S. Chen | R. Johnson |  | 240
1.0.4.6 | RAIDD review & change-control operations — Y2 Q2 | 3 | Task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | N. Gupta | R. Johnson |  | 240
1.0.4.7 | RAIDD review & change-control operations — Y2 Q3 | 3 | Task | 2028-04-03 | 2028-04-28 | 20 | 0% |  | N. Gupta | L. Martinez |  | 288
1.0.4.8 | RAIDD review & change-control operations — Y2 Q4 | 3 | Task | 2028-07-03 | 2028-07-28 | 20 | 0% |  | H. Kim | L. Martinez |  | 288
1.0.4.9 | RAIDD review & change-control operations — Y3 Q1 | 3 | Task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | H. Kim | V. Patel |  | 288
1.0.4.10 | RAIDD review & change-control operations — Y3 Q2 | 3 | Task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | V. Patel | G. Brown |  | 224
1.0.4.11 | RAIDD review & change-control operations — Y3 Q3 | 3 | Task | 2029-04-02 | 2029-04-27 | 20 | 0% |  | Q. Wilson | G. Brown |  | 224
1.0.4.12 | RAIDD review & change-control operations — Y3 Q4 | 3 | Task | 2029-07-02 | 2029-07-27 | 20 | 0% |  | C. Tyrrell | Q. Wilson |  | 288
1.0.5 | Schedule & Performance Management | 2 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
1.0.5.1 | Schedule maintenance & critical-path analysis — Y1 Q1 | 3 | Task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | C. Tyrrell | M. Kavanagh |  | 184
1.0.5.2 | Schedule maintenance & critical-path analysis — Y1 Q2 | 3 | Task | 2026-12-01 | 2026-12-28 | 20 | 0% |  | T. Valdez | M. Kavanagh |  | 184
1.0.5.3 | Schedule maintenance & critical-path analysis — Y1 Q3 | 3 | Task | 2027-03-01 | 2027-03-26 | 20 | 0% |  | T. Valdez | K. Anderson |  | 320
1.0.5.4 | Schedule maintenance & critical-path analysis — Y1 Q4 | 3 | Task | 2027-06-01 | 2027-06-28 | 20 | 0% |  | K. Anderson | J. Wright |  | 320
1.0.5.5 | Schedule maintenance & critical-path analysis — Y2 Q1 | 3 | Task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | J. Wright | D. Lee |  | 320
1.0.5.6 | Schedule maintenance & critical-path analysis — Y2 Q2 | 3 | Task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | D. Lee | M. Torres |  | 320
1.0.5.7 | Schedule maintenance & critical-path analysis — Y2 Q3 | 3 | Task | 2028-04-03 | 2028-04-28 | 20 | 0% |  | M. Torres | P. Davis |  | 320
1.0.5.8 | Schedule maintenance & critical-path analysis — Y2 Q4 | 3 | Task | 2028-07-03 | 2028-07-28 | 20 | 0% |  | P. Davis | S. Chen |  | 320
1.0.5.9 | Schedule maintenance & critical-path analysis — Y3 Q1 | 3 | Task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | S. Chen | R. Johnson |  | 240
1.0.5.10 | Schedule maintenance & critical-path analysis — Y3 Q2 | 3 | Task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | N. Gupta | R. Johnson |  | 240
1.0.5.11 | Schedule maintenance & critical-path analysis — Y3 Q3 | 3 | Task | 2029-04-02 | 2029-04-27 | 20 | 0% |  | N. Gupta | L. Martinez |  | 288
1.0.5.12 | Schedule maintenance & critical-path analysis — Y3 Q4 | 3 | Task | 2029-07-02 | 2029-07-27 | 20 | 0% |  | H. Kim | L. Martinez |  | 288
1.0.6 | Legal & Contract Management | 2 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
1.0.6.1 | Legal counsel, contracts & IP review — Y1 Q1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | K. Okonkwo | M. Bernstein, D. Flores, R. Thorne | Legal (6) | 480
1.0.6.2 | Legal counsel, contracts & IP review — Y1 Q2 | 3 | Group task | 2026-12-01 | 2026-12-28 | 20 | 0% |  | N. Harris | S. Patel, D. Flores, R. Thorne | Legal (6) | 464
1.0.6.3 | Legal counsel, contracts & IP review — Y1 Q3 | 3 | Group task | 2027-03-01 | 2027-03-26 | 20 | 0% |  | K. Okonkwo | M. Bernstein, D. Flores, R. Thorne | Legal (6) | 480
1.0.6.4 | Legal counsel, contracts & IP review — Y1 Q4 | 3 | Group task | 2027-06-01 | 2027-06-28 | 20 | 0% |  | N. Harris | S. Patel, D. Flores, R. Thorne | Legal (6) | 464
1.0.6.5 | Legal counsel, contracts & IP review — Y2 Q1 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | K. Okonkwo | M. Bernstein, D. Flores, R. Thorne | Legal (6) | 480
1.0.6.6 | Legal counsel, contracts & IP review — Y2 Q2 | 3 | Group task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | N. Harris | S. Patel, D. Flores, R. Thorne | Legal (6) | 464
1.0.6.7 | Legal counsel, contracts & IP review — Y2 Q3 | 3 | Group task | 2028-04-03 | 2028-04-28 | 20 | 0% |  | K. Okonkwo | M. Bernstein, D. Flores, R. Thorne | Legal (6) | 480
1.0.6.8 | Legal counsel, contracts & IP review — Y2 Q4 | 3 | Group task | 2028-07-03 | 2028-07-28 | 20 | 0% |  | N. Harris | S. Patel, D. Flores, R. Thorne | Legal (6) | 464
1.0.6.9 | Legal counsel, contracts & IP review — Y3 Q1 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | K. Okonkwo | M. Bernstein, D. Flores, R. Thorne | Legal (6) | 480
1.0.6.10 | Legal counsel, contracts & IP review — Y3 Q2 | 3 | Group task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | N. Harris | S. Patel, D. Flores, R. Thorne | Legal (6) | 464
1.0.6.11 | Legal counsel, contracts & IP review — Y3 Q3 | 3 | Group task | 2029-04-02 | 2029-04-27 | 20 | 0% |  | K. Okonkwo | M. Bernstein, D. Flores, R. Thorne | Legal (6) | 480
1.0.6.12 | Legal counsel, contracts & IP review — Y3 Q4 | 3 | Group task | 2029-07-02 | 2029-07-27 | 20 | 0% |  | N. Harris | S. Patel, D. Flores, R. Thorne | Legal (6) | 464
1.0.7 | Compliance & Regulatory Assurance | 2 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
1.0.7.1 | Compliance monitoring & regulatory liaison — Y1 Q1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | L. Huang | R. Kimani, C. Morrison, J. Martinez | Compliance (7) | 480
1.0.7.2 | Compliance monitoring & regulatory liaison — Y1 Q2 | 3 | Group task | 2026-12-01 | 2026-12-28 | 20 | 0% |  | T. Jackson | B. Cho, C. Morrison, U. Kowalski | Compliance (7) | 552
1.0.7.3 | Compliance monitoring & regulatory liaison — Y1 Q3 | 3 | Group task | 2027-03-01 | 2027-03-26 | 20 | 0% |  | L. Huang | R. Kimani, U. Kowalski, J. Martinez | Compliance (7) | 480
1.0.7.4 | Compliance monitoring & regulatory liaison — Y1 Q4 | 3 | Group task | 2027-06-01 | 2027-06-28 | 20 | 0% |  | T. Jackson | R. Kimani, B. Cho, C. Morrison | Compliance (7) | 568
1.0.7.5 | Compliance monitoring & regulatory liaison — Y2 Q1 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | T. Jackson | L. Huang, U. Kowalski, J. Martinez | Compliance (7) | 496
1.0.7.6 | Compliance monitoring & regulatory liaison — Y2 Q2 | 3 | Group task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | L. Huang | R. Kimani, B. Cho, C. Morrison | Compliance (7) | 568
1.0.7.7 | Compliance monitoring & regulatory liaison — Y2 Q3 | 3 | Group task | 2028-04-03 | 2028-04-28 | 20 | 0% |  | T. Jackson | B. Cho, U. Kowalski, J. Martinez | Compliance (7) | 472
1.0.7.8 | Compliance monitoring & regulatory liaison — Y2 Q4 | 3 | Group task | 2028-07-03 | 2028-07-28 | 20 | 0% |  | L. Huang | R. Kimani, C. Morrison, J. Martinez | Compliance (7) | 480
1.0.7.9 | Compliance monitoring & regulatory liaison — Y3 Q1 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | T. Jackson | B. Cho, C. Morrison, U. Kowalski | Compliance (7) | 552
1.0.7.10 | Compliance monitoring & regulatory liaison — Y3 Q2 | 3 | Group task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | L. Huang | R. Kimani, U. Kowalski, J. Martinez | Compliance (7) | 480
1.0.7.11 | Compliance monitoring & regulatory liaison — Y3 Q3 | 3 | Group task | 2029-04-02 | 2029-04-27 | 20 | 0% |  | T. Jackson | R. Kimani, B. Cho, C. Morrison | Compliance (7) | 568
1.0.7.12 | Compliance monitoring & regulatory liaison — Y3 Q4 | 3 | Group task | 2029-07-02 | 2029-07-27 | 20 | 0% |  | T. Jackson | L. Huang, U. Kowalski, J. Martinez | Compliance (7) | 496
1.0.8 | SOX & Financial Controls Assurance | 2 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
1.0.8.1 | SOX controls testing & audit support — Y1 Q1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | M. Osei | N. Brennan, O. Fairweather, K. Williams | SOX / Financial Controls (6) | 504
1.0.8.2 | SOX controls testing & audit support — Y1 Q2 | 3 | Group task | 2026-12-01 | 2026-12-28 | 20 | 0% |  | P. Whitcomb | O. Fairweather, Q. Marchetti, K. Williams | SOX / Financial Controls (6) | 472
1.0.8.3 | SOX controls testing & audit support — Y1 Q3 | 3 | Group task | 2027-03-01 | 2027-03-26 | 20 | 0% |  | M. Osei | N. Brennan, O. Fairweather, K. Williams | SOX / Financial Controls (6) | 504
1.0.8.4 | SOX controls testing & audit support — Y1 Q4 | 3 | Group task | 2027-06-01 | 2027-06-28 | 20 | 0% |  | P. Whitcomb | O. Fairweather, Q. Marchetti, K. Williams | SOX / Financial Controls (6) | 472
1.0.8.5 | SOX controls testing & audit support — Y2 Q1 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | M. Osei | N. Brennan, O. Fairweather, K. Williams | SOX / Financial Controls (6) | 504
1.0.8.6 | SOX controls testing & audit support — Y2 Q2 | 3 | Group task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | P. Whitcomb | O. Fairweather, Q. Marchetti, K. Williams | SOX / Financial Controls (6) | 472
1.0.8.7 | SOX controls testing & audit support — Y2 Q3 | 3 | Group task | 2028-04-03 | 2028-04-28 | 20 | 0% |  | M. Osei | N. Brennan, O. Fairweather, K. Williams | SOX / Financial Controls (6) | 504
1.0.8.8 | SOX controls testing & audit support — Y2 Q4 | 3 | Group task | 2028-07-03 | 2028-07-28 | 20 | 0% |  | P. Whitcomb | O. Fairweather, Q. Marchetti, K. Williams | SOX / Financial Controls (6) | 472
1.0.8.9 | SOX controls testing & audit support — Y3 Q1 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | M. Osei | N. Brennan, O. Fairweather, K. Williams | SOX / Financial Controls (6) | 504
1.0.8.10 | SOX controls testing & audit support — Y3 Q2 | 3 | Group task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | P. Whitcomb | O. Fairweather, Q. Marchetti, K. Williams | SOX / Financial Controls (6) | 472
1.0.8.11 | SOX controls testing & audit support — Y3 Q3 | 3 | Group task | 2029-04-02 | 2029-04-27 | 20 | 0% |  | M. Osei | N. Brennan, O. Fairweather, K. Williams | SOX / Financial Controls (6) | 504
1.0.8.12 | SOX controls testing & audit support — Y3 Q4 | 3 | Group task | 2029-07-02 | 2029-07-27 | 20 | 0% |  | P. Whitcomb | O. Fairweather, Q. Marchetti, K. Williams | SOX / Financial Controls (6) | 472
1.0.9 | Workforce Planning & Org Design | 2 | Summary | 2026-09-01 | 2028-10-27 | 564 | 15%
1.0.9.1 | Workforce planning, ramp & retention — Year 1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | F. Bianchi | E. Marsh, G. Solberg, H. Rutherford, C. Johnson | HR / Workforce Planning & Org Design (6) | 576
1.0.9.2 | Workforce planning, ramp & retention — Year 2 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | D. Ferraro | F. Bianchi, E. Marsh, G. Solberg, C. Johnson | HR / Workforce Planning & Org Design (6) | 624
1.0.9.3 | Workforce planning, ramp & retention — Year 3 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | D. Ferraro | E. Marsh, G. Solberg, H. Rutherford, C. Johnson | HR / Workforce Planning & Org Design (6) | 576
1.0.10 | Vendor & SaaS Partner Management | 2 | Summary | 2026-09-01 | 2028-10-27 | 564 | 15%
1.0.10.1 | Vendor performance, SLA & renewal management — Year 1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | G. Ainsley | H. Prescott, L. Park, I. Merchant | Vendor / SaaS Partner Management (4) | 560
1.0.10.2 | Vendor performance, SLA & renewal management — Year 2 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | G. Ainsley | H. Prescott, I. Merchant, L. Park | Vendor / SaaS Partner Management (4) | 560
1.0.10.3 | Vendor performance, SLA & renewal management — Year 3 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | G. Ainsley | H. Prescott, I. Merchant, L. Park | Vendor / SaaS Partner Management (4) | 560
1.0.11 | Program Communications | 2 | Summary | 2026-09-01 | 2028-10-27 | 564 | 15%
1.0.11.1 | Program communications & executive messaging — Year 1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | R. Castellanos | S. Halloway, T. Ainslie, B. Sullivan | Corporate Communications / PR (4) | 432
1.0.11.2 | Program communications & executive messaging — Year 2 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | R. Castellanos | S. Halloway, T. Ainslie, B. Sullivan | Corporate Communications / PR (4) | 432
1.0.11.3 | Program communications & executive messaging — Year 3 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | R. Castellanos | S. Halloway, T. Ainslie, B. Sullivan | Corporate Communications / PR (4) | 432
2.0 | Data & Cloud AI Platform | 1 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
2.0.1 | Platform Architecture & Vendor Selection | 2 | Summary | 2026-09-01 | 2026-10-29 | 43 | 21%
2.0.1.1 | Platform requirements & reference architecture | 3 | Task | 2026-09-01 | 2026-09-16 | 12 | 75% |  | W. Kumar | J. Restrepo, K. Vartan |  | 288
2.0.1.2 | Cloud & AI platform vendor evaluation | 3 | Summary | 2026-09-17 | 2026-10-07 | 15 | 0%
2.0.1.2.1 | RFP issuance & vendor scoring | 4 | Task | 2026-09-17 | 2026-09-25 | 7 | 0% | 2.0.1.1 | G. Ainsley | H. Prescott |  | 106
2.0.1.2.2 | Security & BAA review | 4 | Group task | 2026-09-28 | 2026-10-07 | 8 | 0% | 2.0.1.2.1 | N. Winthrop | O. Castillo, P. Halstead, Q. Beaumont, M. Hassan | Cybersecurity / InfoSec (10) | 269
2.0.1.3 | Total cost & FinOps modelling | 3 | Task | 2026-10-08 | 2026-10-19 | 8 | 0% | 2.0.1.2 | A. Rodriguez | B. Halvorsen |  | 128
2.0.1.4 | Vendor selection & contracting | 3 | Task | 2026-10-20 | 2026-10-29 | 8 | 0% | 2.0.1.3 | H. Prescott | I. Merchant |  | 109
2.0.2 | Cloud Foundation Build | 2 | Summary | 2026-11-06 | 2027-01-20 | 54 | 0%
2.0.2.1 | Landing zone & network foundation | 3 | Summary | 2026-11-06 | 2026-11-26 | 15 | 0%
2.0.2.1.1 | Network & connectivity | 4 | Group task | 2026-11-06 | 2026-11-16 | 7 | 0% |  | A. Prescott | B. Fairweather, C. Sondheim, D. Marchetti, H. Nakamura | IT Operations / Infrastructure (10) | 241
2.0.2.1.2 | Core cloud services setup | 4 | Group task | 2026-11-17 | 2026-11-26 | 8 | 0% | 2.0.2.1.1 | D. Marchetti | E. Whitcomb, F. Talbot, G. Restrepo, H. Vartan | IT Operations / Infrastructure (10) | 320
2.0.2.2 | Identity & access management build | 3 | Group task | 2026-11-27 | 2026-12-10 | 10 | 0% | 2.0.2.1 | Q. Beaumont | R. Fontaine, S. Vasquez, T. Delvecchio, U. Kandel | Cybersecurity / InfoSec (10) | 392
2.0.2.3 | Security controls & encryption baseline | 3 | Group task | 2026-12-11 | 2026-12-28 | 12 | 0% | 2.0.2.2 | N. Winthrop | O. Castillo, U. Kandel, V. Redmond, M. Hassan | Cybersecurity / InfoSec (10) | 374
2.0.2.4 | Environment provisioning (dev/test/stage/prod) | 3 | Group task | 2026-12-29 | 2027-01-13 | 12 | 0% | 2.0.2.3 | H. Vartan | A. Prescott, B. Fairweather, I. Halvorsen, H. Nakamura | IT Operations / Infrastructure (10) | 394
2.0.2.5 | Platform Foundation go-live | 3 | Task | 2027-01-14 | 2027-01-20 | 5 | 0% | 2.0.2.4 | K. Vartan | L. Sondheim, M. Marchetti |  | 120
2.0.3 | Data Lake & Governance Layer | 2 | Summary | 2027-01-13 | 2027-05-18 | 90 | 0%
2.0.3.1 | Data lake storage & zone design | 3 | Task | 2027-01-13 | 2027-01-26 | 10 | 0% |  | M. Marchetti | N. Whitcomb, O. Talbot |  | 240
2.0.3.2 | Data cataloguing & metadata management | 3 | Group task | 2027-01-27 | 2027-02-11 | 12 | 0% | 2.0.3.1 | O. Talbot | P. Restrepo2, Q. Halvorsen2, R. Bianchi, S. Fitzgerald | Data & Cloud AI Platform Foundation (20) | 480
2.0.3.3 | Data lineage & quality framework | 3 | Task | 2027-02-12 | 2027-03-01 | 12 | 0% | 2.0.3.2 | S. Fitzgerald | T. Andersen, U. Kowalczyk2 |  | 288
2.0.3.4 | Master data & reference data services | 3 | Task | 2027-03-02 | 2027-03-15 | 10 | 0% | 2.0.3.3 | U. Kowalczyk2 | V. Delvecchio2 |  | 160
2.0.3.5 | Data domain onboarding — claims | 3 | Group task | 2027-03-16 | 2027-03-31 | 12 | 0% | 2.0.3.4 | V. Delvecchio2 | W. Solberg2, X. Nakashima2, Y. Winfield2, Z. Achebe2 | Data & Cloud AI Platform Foundation (20) | 480
2.0.3.6 | Data domain onboarding — member & provider | 3 | Group task | 2027-04-01 | 2027-04-16 | 12 | 0% | 2.0.3.5 | Z. Achebe2 | W. Kumar, J. Restrepo, A. Larsen2, B. Sorensen2 | Data & Cloud AI Platform Foundation (20) | 460
2.0.3.7 | Data domain onboarding — underwriting & risk | 3 | Group task | 2027-04-19 | 2027-05-04 | 12 | 0% | 2.0.3.6 | J. Restrepo | K. Vartan, L. Sondheim, M. Marchetti, N. Whitcomb | Data & Cloud AI Platform Foundation (20) | 480
2.0.3.8 | Privacy controls & PHI segregation | 3 | Group task | 2027-05-05 | 2027-05-18 | 10 | 0% | 2.0.3.7 | N. Achterberg | O. Whitlock, P. Sandoval, Q. Beckham, E. Sato | Data Privacy Office (5) | 328
2.0.4 | MLOps Pipeline & Tooling | 2 | Summary | 2027-03-22 | 2027-06-29 | 72 | 0%
2.0.4.1 | CI/CD pipeline for models & code | 3 | Summary | 2027-03-22 | 2027-04-09 | 15 | 0%
2.0.4.1.1 | Build & release automation | 4 | Group task | 2027-03-22 | 2027-03-30 | 7 | 0% |  | N. Whitcomb | O. Talbot, P. Restrepo2, Q. Halvorsen2, R. Bianchi | Data & Cloud AI Platform Foundation (20) | 280
2.0.4.1.2 | Automated test integration | 4 | Task | 2027-03-31 | 2027-04-09 | 8 | 0% | 2.0.4.1.1 | R. Bianchi | S. Fitzgerald |  | 128
2.0.4.2 | Feature store implementation | 3 | Task | 2027-04-12 | 2027-04-27 | 12 | 0% | 2.0.4.1 | S. Fitzgerald | T. Andersen, U. Kowalczyk2 |  | 288
2.0.4.3 | Model registry & versioning | 3 | Task | 2027-04-28 | 2027-05-11 | 10 | 0% | 2.0.4.2 | U. Kowalczyk2 | V. Delvecchio2 |  | 160
2.0.4.4 | Monitoring, drift detection & alerting | 3 | Group task | 2027-05-12 | 2027-06-01 | 15 | 0% | 2.0.4.3 | V. Delvecchio2 | W. Solberg2, X. Nakashima2, Y. Winfield2, Z. Achebe2 | Data & Cloud AI Platform Foundation (20) | 600
2.0.4.5 | FinOps guardrails & cost telemetry | 3 | Task | 2027-06-02 | 2027-06-15 | 10 | 0% | 2.0.4.4 | W. Kumar | J. Restrepo, K. Vartan |  | 240
2.0.4.6 | Platform security hardening & pen-test | 3 | Group task | 2027-06-16 | 2027-06-29 | 10 | 0% | 2.0.4.5 | O. Castillo | P. Halstead, Q. Beaumont, R. Fontaine, S. Vasquez | Cybersecurity / InfoSec (10) | 400
2.0.5 | Platform Scaling & Reliability | 2 | Summary | 2027-05-27 | 2027-08-20 | 62 | 0%
2.0.5.1 | Platform scaling for BRD-02/03 workloads | 3 | Group task | 2027-05-27 | 2027-06-23 | 20 | 0% |  | Z. Achebe2 | W. Kumar, J. Restrepo, A. Larsen2, B. Sorensen2 | Data & Cloud AI Platform Foundation (20) | 768
2.0.5.2 | High-availability & disaster-recovery build | 3 | Group task | 2027-06-24 | 2027-07-14 | 15 | 0% | 2.0.5.1 | B. Fairweather | C. Sondheim, D. Marchetti, E. Whitcomb, F. Talbot | IT Operations / Infrastructure (10) | 600
2.0.5.3 | Performance tuning & capacity management | 3 | Group task | 2027-07-15 | 2027-08-04 | 15 | 0% | 2.0.5.2 | F. Talbot | G. Restrepo, H. Vartan, I. Halvorsen, H. Nakamura | IT Operations / Infrastructure (10) | 492
2.0.5.4 | Observability & SRE practice rollout | 3 | Group task | 2027-08-05 | 2027-08-20 | 12 | 0% | 2.0.5.3 | A. Prescott | B. Fairweather, C. Sondheim, D. Marchetti, H. Nakamura | IT Operations / Infrastructure (10) | 413
2.0.6 | Integration & API Services | 2 | Summary | 2027-08-03 | 2027-10-15 | 54 | 0%
2.0.6.1 | Enterprise integration layer build | 3 | Group task | 2027-08-03 | 2027-08-23 | 15 | 0% |  | J. Restrepo | K. Vartan, L. Sondheim, M. Marchetti, N. Whitcomb | Data & Cloud AI Platform Foundation (20) | 600
2.0.6.2 | API gateway & service mesh | 3 | Group task | 2027-08-24 | 2027-09-08 | 12 | 0% | 2.0.6.1 | D. Marchetti | E. Whitcomb, F. Talbot, G. Restrepo, H. Vartan | IT Operations / Infrastructure (10) | 480
2.0.6.3 | Event streaming & real-time services | 3 | Group task | 2027-09-09 | 2027-09-24 | 12 | 0% | 2.0.6.2 | N. Whitcomb | O. Talbot, P. Restrepo2, Q. Halvorsen2, R. Bianchi | Data & Cloud AI Platform Foundation (20) | 480
2.0.6.4 | Legacy system adapters | 3 | Group task | 2027-09-27 | 2027-10-15 | 15 | 0% | 2.0.6.3 | R. Bianchi | S. Fitzgerald, T. Andersen, U. Kowalczyk2, V. Delvecchio2 | Data & Cloud AI Platform Foundation (20) | 600
2.0.7 | Data Quality & Stewardship | 2 | Summary | 2027-10-08 | 2029-01-29 | 342 | 0%
2.0.7.1 | Data quality rules engine | 3 | Group task | 2027-10-08 | 2027-10-25 | 12 | 0% |  | V. Delvecchio2 | W. Solberg2, X. Nakashima2, Y. Winfield2, Z. Achebe2 | Data & Cloud AI Platform Foundation (20) | 480
2.0.7.2 | Data stewardship operating model | 3 | Task | 2027-10-26 | 2027-11-08 | 10 | 0% | 2.0.7.1 | W. Kumar | J. Restrepo |  | 160
2.0.7.3 | Ongoing data quality monitoring — Year 2 | 3 | Group task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | Z. Achebe2 | W. Kumar, J. Restrepo, A. Larsen2, B. Sorensen2 | Data & Cloud AI Platform Foundation (20) | 768
2.0.7.4 | Ongoing data quality monitoring — Year 3 | 3 | Group task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | J. Restrepo | K. Vartan, L. Sondheim, M. Marchetti, N. Whitcomb | Data & Cloud AI Platform Foundation (20) | 800
2.0.8 | Platform Operations (Run) | 2 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
2.0.8.1 | Platform run, patching & support — Y1 Q1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | H. Vartan | A. Prescott, B. Fairweather, I. Halvorsen, H. Nakamura | IT Operations / Infrastructure (10) | 656
2.0.8.2 | Platform run, patching & support — Y1 Q2 | 3 | Group task | 2026-12-01 | 2026-12-28 | 20 | 0% |  | B. Fairweather | C. Sondheim, D. Marchetti, E. Whitcomb, F. Talbot | IT Operations / Infrastructure (10) | 800
2.0.8.3 | Platform run, patching & support — Y1 Q3 | 3 | Group task | 2027-03-01 | 2027-03-26 | 20 | 0% |  | F. Talbot | G. Restrepo, H. Vartan, I. Halvorsen, H. Nakamura | IT Operations / Infrastructure (10) | 656
2.0.8.4 | Platform run, patching & support — Y1 Q4 | 3 | Group task | 2027-06-01 | 2027-06-28 | 20 | 0% |  | A. Prescott | B. Fairweather, C. Sondheim, D. Marchetti, H. Nakamura | IT Operations / Infrastructure (10) | 688
2.0.8.5 | Platform run, patching & support — Y2 Q1 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | D. Marchetti | E. Whitcomb, F. Talbot, G. Restrepo, H. Vartan | IT Operations / Infrastructure (10) | 800
2.0.8.6 | Platform run, patching & support — Y2 Q2 | 3 | Group task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | H. Vartan | A. Prescott, B. Fairweather, I. Halvorsen, H. Nakamura | IT Operations / Infrastructure (10) | 656
2.0.8.7 | Platform run, patching & support — Y2 Q3 | 3 | Group task | 2028-04-03 | 2028-04-28 | 20 | 0% |  | B. Fairweather | C. Sondheim, D. Marchetti, E. Whitcomb, F. Talbot | IT Operations / Infrastructure (10) | 800
2.0.8.8 | Platform run, patching & support — Y2 Q4 | 3 | Group task | 2028-07-03 | 2028-07-28 | 20 | 0% |  | F. Talbot | G. Restrepo, H. Vartan, I. Halvorsen, H. Nakamura | IT Operations / Infrastructure (10) | 656
2.0.8.9 | Platform run, patching & support — Y3 Q1 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | A. Prescott | B. Fairweather, C. Sondheim, D. Marchetti, H. Nakamura | IT Operations / Infrastructure (10) | 688
2.0.8.10 | Platform run, patching & support — Y3 Q2 | 3 | Group task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | D. Marchetti | E. Whitcomb, F. Talbot, G. Restrepo, H. Vartan | IT Operations / Infrastructure (10) | 800
2.0.8.11 | Platform run, patching & support — Y3 Q3 | 3 | Group task | 2029-04-02 | 2029-04-27 | 20 | 0% |  | H. Vartan | A. Prescott, B. Fairweather, I. Halvorsen, H. Nakamura | IT Operations / Infrastructure (10) | 656
2.0.8.12 | Platform run, patching & support — Y3 Q4 | 3 | Group task | 2029-07-02 | 2029-07-27 | 20 | 0% |  | B. Fairweather | C. Sondheim, D. Marchetti, E. Whitcomb, F. Talbot | IT Operations / Infrastructure (10) | 800
2.0.9 | Service Desk & Production Support | 2 | Summary | 2026-09-01 | 2028-10-27 | 564 | 15%
2.0.9.1 | AI service desk & production support — Year 1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | N. Alvarado4 | O. Whitby7, P. Okoro7, Q. Beaumont5, M. Washington (CustOps) | Customer Service Operations (12) | 672
2.0.9.2 | AI service desk & production support — Year 2 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | Q. Beaumont5 | S. Delvecchio6, T. Solberg6, R. Kowalczyk6, U. Nakashima6 | Customer Service Operations (12) | 752
2.0.9.3 | AI service desk & production support — Year 3 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | X. Larsen6 | U. Nakashima6, V. Winfield6, W. Achebe6, M. Washington (CustOps) | Customer Service Operations (12) | 560
2.0.10 | Infrastructure & Cloud Cost Management | 2 | Summary | 2026-09-01 | 2028-10-27 | 564 | 15%
2.0.10.1 | Cloud cost optimization & FinOps review — Year 1 | 3 | Task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | K. Vartan | L. Sondheim |  | 320
2.0.10.2 | Cloud cost optimization & FinOps review — Year 2 | 3 | Task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | L. Sondheim | M. Marchetti |  | 320
2.0.10.3 | Cloud cost optimization & FinOps review — Year 3 | 3 | Task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | M. Marchetti | N. Whitcomb |  | 320
2.0.11 | Steady-State Transition | 2 | Summary | 2028-07-04 | 2028-08-25 | 39 | 0%
2.0.11.1 | Operations runbook & knowledge base | 3 | Group task | 2028-07-04 | 2028-07-19 | 12 | 0% |  | F. Talbot | G. Restrepo, H. Vartan, I. Halvorsen, H. Nakamura | IT Operations / Infrastructure (10) | 394
2.0.11.2 | Platform handover to ACME operations | 3 | Task | 2028-07-20 | 2028-08-09 | 15 | 0% | 2.0.11.1 | N. Whitcomb | O. Talbot, P. Restrepo2 |  | 360
2.0.11.3 | Post-transition support & assurance | 3 | Task | 2028-08-10 | 2028-08-25 | 12 | 0% | 2.0.11.2 | A. Prescott | H. Nakamura |  | 125
3.0 | AI Governance & Center of Excellence | 1 | Summary | 2026-08-24 | 2029-07-27 | 765 | 6%
3.0.1 | CoE Charter & Operating Model | 2 | Summary | 2026-08-24 | 2026-10-09 | 35 | 43%
3.0.1.1 | AI Center of Excellence charter | 3 | Task | 2026-08-24 | 2026-09-02 | 8 | 100% |  | S. Khurana | A. Reyes, J. Ferraro |  | 192
3.0.1.2 | Hub-and-spoke operating model design | 3 | Task | 2026-09-03 | 2026-09-14 | 8 | 88% | 3.0.1.1 | J. Ferraro | M. Delacroix |  | 128
3.0.1.3 | CoE role definition & staffing model | 3 | Task | 2026-09-15 | 2026-09-23 | 7 | 0% | 3.0.1.2 | S. Khurana | A. Reyes |  | 112
3.0.1.4 | AI Readiness Assessment | 3 | Summary | 2026-09-24 | 2026-10-09 | 12 | 0%
3.0.1.4.1 | Capability & data readiness review | 4 | Group task | 2026-09-24 | 2026-10-01 | 6 | 0% | 3.0.1.3 | M. Delacroix | C. Alvarez, T. Nakamura, R. Osei, P. Singh | AI Governance & CoE (12) | 235
3.0.1.4.2 | Readiness report & roadmap | 4 | Task | 2026-10-02 | 2026-10-09 | 6 | 0% | 3.0.1.4.1 | R. Osei | V. Castellano |  | 96
3.0.2 | Governance Framework (NIST AI RMF / ISO 42001) | 2 | Summary | 2026-11-13 | 2027-02-09 | 63 | 0%
3.0.2.1 | AI governance framework v1 | 3 | Task | 2026-11-13 | 2026-11-30 | 12 | 0% |  | V. Castellano | L. Whitfield, K. Novak |  | 269
3.0.2.2 | Responsible-AI standards & policies | 3 | Group task | 2026-12-01 | 2026-12-14 | 10 | 0% | 3.0.2.1 | D. Ibrahim | S. Khurana, A. Reyes, J. Ferraro, K. Novak | AI Governance & CoE (12) | 384
3.0.2.3 | Model risk management & two-line-of-defense process | 3 | Task | 2026-12-15 | 2026-12-28 | 10 | 0% | 3.0.2.2 | S. Khurana | A. Reyes, J. Ferraro |  | 240
3.0.2.4 | AI Governance Board & EARB stand-up | 3 | Task | 2026-12-29 | 2027-01-05 | 6 | 0% | 3.0.2.3 | J. Ferraro | M. Delacroix |  | 96
3.0.2.5 | Model-card standards & registry governance | 3 | Task | 2027-01-06 | 2027-01-19 | 10 | 0% | 3.0.2.4 | M. Delacroix | P. Singh |  | 152
3.0.2.6 | AI use-case intake & triage process | 3 | Task | 2027-01-20 | 2027-01-29 | 8 | 0% | 3.0.2.5 | C. Alvarez | P. Singh |  | 122
3.0.2.7 | Ethics review & escalation protocol | 3 | Task | 2027-02-01 | 2027-02-09 | 7 | 0% | 3.0.2.6 | C. Alvarez | T. Nakamura |  | 112
3.0.3 | Governance Board Operations | 2 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
3.0.3.1 | AI Governance Board & EARB operations — Y1 Q1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | T. Nakamura | R. Osei, V. Castellano, L. Whitfield, K. Novak | AI Governance & CoE (12) | 768
3.0.3.2 | AI Governance Board & EARB operations — Y1 Q2 | 3 | Group task | 2026-12-01 | 2026-12-28 | 20 | 0% |  | D. Ibrahim | S. Khurana, A. Reyes, J. Ferraro, K. Novak | AI Governance & CoE (12) | 768
3.0.3.3 | AI Governance Board & EARB operations — Y1 Q3 | 3 | Group task | 2027-03-01 | 2027-03-26 | 20 | 0% |  | J. Ferraro | M. Delacroix, C. Alvarez, T. Nakamura, P. Singh | AI Governance & CoE (12) | 784
3.0.3.4 | AI Governance Board & EARB operations — Y1 Q4 | 3 | Group task | 2027-06-01 | 2027-06-28 | 20 | 0% |  | T. Nakamura | R. Osei, V. Castellano, L. Whitfield, K. Novak | AI Governance & CoE (12) | 768
3.0.3.5 | AI Governance Board & EARB operations — Y2 Q1 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | D. Ibrahim | S. Khurana, A. Reyes, J. Ferraro, K. Novak | AI Governance & CoE (12) | 768
3.0.3.6 | AI Governance Board & EARB operations — Y2 Q2 | 3 | Group task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | J. Ferraro | M. Delacroix, C. Alvarez, T. Nakamura, P. Singh | AI Governance & CoE (12) | 784
3.0.3.7 | AI Governance Board & EARB operations — Y2 Q3 | 3 | Group task | 2028-04-03 | 2028-04-28 | 20 | 0% |  | T. Nakamura | R. Osei, V. Castellano, L. Whitfield, K. Novak | AI Governance & CoE (12) | 768
3.0.3.8 | AI Governance Board & EARB operations — Y2 Q4 | 3 | Group task | 2028-07-03 | 2028-07-28 | 20 | 0% |  | D. Ibrahim | S. Khurana, A. Reyes, J. Ferraro, K. Novak | AI Governance & CoE (12) | 768
3.0.3.9 | AI Governance Board & EARB operations — Y3 Q1 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | J. Ferraro | M. Delacroix, C. Alvarez, T. Nakamura, P. Singh | AI Governance & CoE (12) | 784
3.0.3.10 | AI Governance Board & EARB operations — Y3 Q2 | 3 | Group task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | T. Nakamura | R. Osei, V. Castellano, L. Whitfield, K. Novak | AI Governance & CoE (12) | 768
3.0.3.11 | AI Governance Board & EARB operations — Y3 Q3 | 3 | Group task | 2029-04-02 | 2029-04-27 | 20 | 0% |  | D. Ibrahim | S. Khurana, A. Reyes, J. Ferraro, K. Novak | AI Governance & CoE (12) | 768
3.0.3.12 | AI Governance Board & EARB operations — Y3 Q4 | 3 | Group task | 2029-07-02 | 2029-07-27 | 20 | 0% |  | J. Ferraro | M. Delacroix, C. Alvarez, T. Nakamura, P. Singh | AI Governance & CoE (12) | 784
3.0.4 | Enterprise Architecture Governance | 2 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
3.0.4.1 | Architecture review, standards & roadmap governance — Y1 Q1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | F. Okonkwo | G. Petrova, H. Delgado, I. Suzuki, D. Chen | Enterprise Architecture (8) | 680
3.0.4.2 | Architecture review, standards & roadmap governance — Y1 Q2 | 3 | Group task | 2026-12-01 | 2026-12-28 | 20 | 0% |  | I. Suzuki | J. Kowalczyk, L. Fitzgerald, K. Andersen, D. Chen | Enterprise Architecture (8) | 648
3.0.4.3 | Architecture review, standards & roadmap governance — Y1 Q3 | 3 | Group task | 2027-03-01 | 2027-03-26 | 20 | 0% |  | F. Okonkwo | G. Petrova, H. Delgado, I. Suzuki, D. Chen | Enterprise Architecture (8) | 680
3.0.4.4 | Architecture review, standards & roadmap governance — Y1 Q4 | 3 | Group task | 2027-06-01 | 2027-06-28 | 20 | 0% |  | I. Suzuki | J. Kowalczyk, L. Fitzgerald, K. Andersen, D. Chen | Enterprise Architecture (8) | 648
3.0.4.5 | Architecture review, standards & roadmap governance — Y2 Q1 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | F. Okonkwo | G. Petrova, H. Delgado, I. Suzuki, D. Chen | Enterprise Architecture (8) | 680
3.0.4.6 | Architecture review, standards & roadmap governance — Y2 Q2 | 3 | Group task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | I. Suzuki | J. Kowalczyk, L. Fitzgerald, K. Andersen, D. Chen | Enterprise Architecture (8) | 648
3.0.4.7 | Architecture review, standards & roadmap governance — Y2 Q3 | 3 | Group task | 2028-04-03 | 2028-04-28 | 20 | 0% |  | F. Okonkwo | G. Petrova, H. Delgado, I. Suzuki, D. Chen | Enterprise Architecture (8) | 680
3.0.4.8 | Architecture review, standards & roadmap governance — Y2 Q4 | 3 | Group task | 2028-07-03 | 2028-07-28 | 20 | 0% |  | I. Suzuki | J. Kowalczyk, L. Fitzgerald, K. Andersen, D. Chen | Enterprise Architecture (8) | 648
3.0.4.9 | Architecture review, standards & roadmap governance — Y3 Q1 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | F. Okonkwo | G. Petrova, H. Delgado, I. Suzuki, D. Chen | Enterprise Architecture (8) | 680
3.0.4.10 | Architecture review, standards & roadmap governance — Y3 Q2 | 3 | Group task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | I. Suzuki | J. Kowalczyk, L. Fitzgerald, K. Andersen, D. Chen | Enterprise Architecture (8) | 648
3.0.4.11 | Architecture review, standards & roadmap governance — Y3 Q3 | 3 | Group task | 2029-04-02 | 2029-04-27 | 20 | 0% |  | F. Okonkwo | G. Petrova, H. Delgado, I. Suzuki, D. Chen | Enterprise Architecture (8) | 680
3.0.4.12 | Architecture review, standards & roadmap governance — Y3 Q4 | 3 | Group task | 2029-07-02 | 2029-07-27 | 20 | 0% |  | I. Suzuki | J. Kowalczyk, L. Fitzgerald, K. Andersen, D. Chen | Enterprise Architecture (8) | 648
3.0.5 | Security & Privacy Assurance | 2 | Summary | 2026-09-01 | 2029-07-27 | 759 | 4%
3.0.5.1 | Security architecture review & privacy assurance — Y1 Q1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | N. Winthrop | O. Castillo, P. Halstead, Q. Beaumont, M. Hassan | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 672
3.0.5.2 | Security architecture review & privacy assurance — Y1 Q2 | 3 | Group task | 2026-12-01 | 2026-12-28 | 20 | 0% |  | Q. Beaumont | R. Fontaine, S. Vasquez, T. Delvecchio, U. Kandel | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 784
3.0.5.3 | Security architecture review & privacy assurance — Y1 Q3 | 3 | Group task | 2027-03-01 | 2027-03-26 | 20 | 0% |  | N. Achterberg | O. Whitlock, U. Kandel, V. Redmond, E. Sato | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 656
3.0.5.4 | Security architecture review & privacy assurance — Y1 Q4 | 3 | Group task | 2027-06-01 | 2027-06-28 | 20 | 0% |  | O. Whitlock | N. Winthrop, P. Sandoval, Q. Beckham, M. Hassan | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 624
3.0.5.5 | Security architecture review & privacy assurance — Y2 Q1 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | N. Winthrop | O. Castillo, P. Halstead, Q. Beaumont, R. Fontaine | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 800
3.0.5.6 | Security architecture review & privacy assurance — Y2 Q2 | 3 | Group task | 2028-01-03 | 2028-01-28 | 20 | 0% |  | R. Fontaine | S. Vasquez, T. Delvecchio, U. Kandel, V. Redmond | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 752
3.0.5.7 | Security architecture review & privacy assurance — Y2 Q3 | 3 | Group task | 2028-04-03 | 2028-04-28 | 20 | 0% |  | N. Achterberg | O. Whitlock, P. Sandoval, V. Redmond, E. Sato | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 656
3.0.5.8 | Security architecture review & privacy assurance — Y2 Q4 | 3 | Group task | 2028-07-03 | 2028-07-28 | 20 | 0% |  | N. Winthrop | O. Castillo, P. Sandoval, Q. Beckham, M. Hassan | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 624
3.0.5.9 | Security architecture review & privacy assurance — Y3 Q1 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | O. Castillo | P. Halstead, Q. Beaumont, R. Fontaine, S. Vasquez | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 800
3.0.5.10 | Security architecture review & privacy assurance — Y3 Q2 | 3 | Group task | 2029-01-02 | 2029-01-29 | 20 | 0% |  | S. Vasquez | T. Delvecchio, U. Kandel, V. Redmond, E. Sato | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 656
3.0.5.11 | Security architecture review & privacy assurance — Y3 Q3 | 3 | Group task | 2029-04-02 | 2029-04-27 | 20 | 0% |  | N. Achterberg | O. Whitlock, P. Sandoval, Q. Beckham, E. Sato | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 656
3.0.5.12 | Security architecture review & privacy assurance — Y3 Q4 | 3 | Group task | 2029-07-02 | 2029-07-27 | 20 | 0% |  | N. Winthrop | O. Castillo, P. Halstead, Q. Beckham, M. Hassan | Cybersecurity / InfoSec (10) + Data Privacy Office (5) | 640
3.0.6 | Independent Model Validation Practice | 2 | Summary | 2027-10-11 | 2029-02-28 | 363 | 0%
3.0.6.1 | IMV methodology & standards | 3 | Task | 2027-10-11 | 2027-10-22 | 10 | 0% |  | P. Okafor | W. Achebe, X. Sorensen |  | 240
3.0.6.2 | Validation tooling & test harness | 3 | Task | 2027-10-25 | 2027-11-05 | 10 | 0% | 3.0.6.1 | X. Sorensen | Y. Larsen |  | 160
3.0.6.3 | IMV capacity planning & queue management | 3 | Task | 2027-11-08 | 2027-11-17 | 8 | 0% | 3.0.6.2 | Y. Larsen | Z. Winfield (IMV) |  | 128
3.0.6.4 | Annual model re-validation cycle — Year 2 | 3 | Group task | 2028-02-01 | 2028-02-28 | 20 | 0% |  | Z. Winfield (IMV) | P. Okafor, W. Achebe, X. Sorensen, A. Kessler | Independent Model Validation (6) | 784
3.0.6.5 | Annual model re-validation cycle — Year 3 | 3 | Group task | 2029-02-01 | 2029-02-28 | 20 | 0% |  | X. Sorensen | Y. Larsen, Z. Winfield (IMV), P. Okafor, A. Kessler | Independent Model Validation (6) | 784
3.0.7 | Regulatory & Policy Monitoring | 2 | Summary | 2026-09-01 | 2028-10-27 | 564 | 15%
3.0.7.1 | Regulatory horizon scanning (NAIC / state AI law) — Year 1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | K. Okonkwo | M. Bernstein, D. Flores, R. Thorne | Legal (6) + Compliance (7) | 480
3.0.7.2 | Regulatory horizon scanning (NAIC / state AI law) — Year 2 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | N. Harris | S. Patel, D. Flores, J. Martinez | Legal (6) + Compliance (7) | 480
3.0.7.3 | Regulatory horizon scanning (NAIC / state AI law) — Year 3 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | L. Huang | R. Kimani, C. Morrison, J. Martinez | Legal (6) + Compliance (7) | 480
3.0.8 | AI Literacy & Enablement | 2 | Summary | 2028-03-23 | 2028-05-26 | 47 | 0%
3.0.8.1 | AI literacy curriculum for business stakeholders | 3 | Task | 2028-03-23 | 2028-04-07 | 12 | 0% |  | S. Khurana | A. Reyes, J. Ferraro |  | 288
3.0.8.2 | Responsible-AI training rollout | 3 | Group task | 2028-04-10 | 2028-04-28 | 15 | 0% | 3.0.8.1 | G. Okonkwo | B. Prescott, C. Whitfield, D. Solis, E. Winthrop | Change Management & Training (8) | 588
3.0.8.3 | CoE community of practice & office hours | 3 | Group task | 2028-05-01 | 2028-05-26 | 20 | 0% | 3.0.8.2 | T. Nakamura | R. Osei, V. Castellano, L. Whitfield, K. Novak | AI Governance & CoE (12) | 768
3.0.9 | Governance Audit & Assurance | 2 | Summary | 2026-09-01 | 2028-10-27 | 564 | 15%
3.0.9.1 | Internal AI governance audit & remediation — Year 1 | 3 | Group task | 2026-09-01 | 2026-09-28 | 20 | 45% |  | L. Huang | R. Kimani, C. Morrison, J. Martinez | Compliance (7) + AI Governance & CoE (12) | 480
3.0.9.2 | Internal AI governance audit & remediation — Year 2 | 3 | Group task | 2027-10-01 | 2027-10-28 | 20 | 0% |  | T. Jackson | B. Cho, C. Morrison, U. Kowalski | Compliance (7) + AI Governance & CoE (12) | 552
3.0.9.3 | Internal AI governance audit & remediation — Year 3 | 3 | Group task | 2028-10-02 | 2028-10-27 | 20 | 0% |  | S. Khurana | A. Reyes, J. Ferraro, U. Kowalski | Compliance (7) + AI Governance & CoE (12) | 608
4.0 | BRD-01 · Claims & Prior Authorization AI | 1 | Summary | 2026-10-05 | 2027-08-02 | 216 | 0%
4.0.1 | Requirements & JAD | 2 | Summary | 2026-10-05 | 2026-12-28 | 61 | 0%
4.0.1.1 | Requirements elicitation workshops (JAD series) | 3 | Summary | 2026-10-05 | 2026-10-27 | 17 | 0%
4.0.1.1.1 | Current-state process mapping | 4 | Task | 2026-10-05 | 2026-10-12 | 6 | 0% |  | F. Bennett | C. Garcia2 |  | 96
4.0.1.1.2 | Use-case & user-story definition | 4 | Group task | 2026-10-13 | 2026-10-20 | 6 | 0% | 4.0.1.1.1 | C. Garcia2 | D. Thompson2, E. Washington2, F. Ferraro2, G. Delacroix2 | Claims & Prior Authorization AI (BRD-01) (28) | 240
4.0.1.1.3 | Non-functional & compliance requirements | 4 | Task | 2026-10-21 | 2026-10-27 | 5 | 0% | 4.0.1.1.2 | F. Bennett | C. Garcia2 |  | 80
4.0.1.2 | Data & source-system requirements | 3 | Summary | 2026-10-28 | 2026-11-06 | 8 | 0%
4.0.1.2.1 | Source-system inventory | 4 | Task | 2026-10-28 | 2026-11-02 | 4 | 0% | 4.0.1.1 | P. Restrepo2 | Q. Halvorsen2 |  | 64
4.0.1.2.2 | Data availability & quality requirements | 4 | Task | 2026-11-03 | 2026-11-06 | 4 | 0% | 4.0.1.2.1 | Q. Halvorsen2 | R. Bianchi |  | 64
4.0.1.3 | Model & decision-logic requirements | 3 | Task | 2026-11-09 | 2026-11-18 | 8 | 0% | 4.0.1.2 | G. Delacroix2 | H. Vartan2 |  | 128
4.0.1.4 | Business rules & policy catalogue | 3 | Task | 2026-11-19 | 2026-11-27 | 7 | 0% | 4.0.1.3 | F. Bennett | C. Garcia2 |  | 112
4.0.1.5 | Clinical / actuarial SME requirements review | 3 | Group task | 2026-11-30 | 2026-12-07 | 6 | 0% | 4.0.1.4 | K. Okoro | L. Delacroix, Dr. J. Whitby, Dr. I. Alvarado, Dr. N. Patel | Clinical / Medical Policy & Informatics (6) | 165
4.0.1.6 | Requirements traceability matrix baseline | 3 | Task | 2026-12-08 | 2026-12-14 | 5 | 0% | 4.0.1.5 | H. Vartan2 | I. Halvorsen2 |  | 80
4.0.1.7 | Requirements review & BRD authoring | 3 | Task | 2026-12-15 | 2026-12-23 | 7 | 0% | 4.0.1.6 | I. Halvorsen2 | J. Nakamura2 |  | 112
4.0.1.8 | BRD sign-off (JAD close, AI Governance Board) | 3 | Task | 2026-12-24 | 2026-12-28 | 3 | 0% | 4.0.1.7 | J. Nakamura2 | K. Okoro2 |  | 48
4.0.2 | Architecture & Design | 2 | Summary | 2026-10-21 | 2027-01-07 | 57 | 0%
4.0.2.1 | Solution architecture & integration design | 3 | Summary | 2026-10-21 | 2026-11-05 | 12 | 0%
4.0.2.1.1 | Target-state architecture | 4 | Task | 2026-10-21 | 2026-10-28 | 6 | 0% |  | F. Okonkwo | D. Chen |  | 60
4.0.2.1.2 | Integration & API design | 4 | Task | 2026-10-29 | 2026-11-05 | 6 | 0% | 4.0.2.1.1 | F. Okonkwo | G. Petrova |  | 96
4.0.2.2 | Data architecture & pipeline design | 3 | Task | 2026-11-06 | 2026-11-19 | 10 | 0% | 4.0.2.1 | R. Bianchi | S. Fitzgerald |  | 160
4.0.2.3 | Model design & approach selection | 3 | Summary | 2026-11-20 | 2026-12-03 | 10 | 0%
4.0.2.3.1 | Model approach evaluation | 4 | Task | 2026-11-20 | 2026-11-26 | 5 | 0% | 4.0.2.2 | K. Okoro2 | L. Whitby2 |  | 80
4.0.2.3.2 | Model design specification | 4 | Task | 2026-11-27 | 2026-12-03 | 5 | 0% | 4.0.2.3.1 | L. Whitby2 | M. Beaumont2 |  | 80
4.0.2.4 | Security threat model & controls design | 3 | Group task | 2026-12-04 | 2026-12-15 | 8 | 0% | 4.0.2.3 | S. Vasquez | T. Delvecchio, U. Kandel, V. Redmond, M. Hassan | Cybersecurity / InfoSec (10) | 250
4.0.2.5 | Privacy-by-design & PHI data-flow review | 3 | Task | 2026-12-16 | 2026-12-23 | 6 | 0% | 4.0.2.4 | Q. Beckham | E. Sato |  | 57
4.0.2.6 | Infrastructure & environment design | 3 | Task | 2026-12-24 | 2027-01-01 | 7 | 0% | 4.0.2.5 | A. Prescott | B. Fairweather |  | 112
4.0.2.7 | Design review & EARB approval | 3 | Task | 2027-01-04 | 2027-01-07 | 4 | 0% | 4.0.2.6 | G. Petrova | H. Delgado |  | 64
4.0.3 | Experience & Interaction Design | 2 | Summary | 2026-11-06 | 2027-02-03 | 64 | 0%
4.0.3.1 | User research & journey mapping | 3 | Group task | 2026-11-06 | 2026-11-19 | 10 | 0% |  | J. Lee | U. Marchetti, V. Okwuosa, W. Pham, X. Delgado | Customer UX / Design (8) | 400
4.0.3.2 | Information architecture & wireframes | 3 | Group task | 2026-11-20 | 2026-12-07 | 12 | 0% | 4.0.3.1 | X. Delgado | Y. Nakashima (UX), J. Lee, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 451
4.0.3.3 | Design system & component library | 3 | Group task | 2026-12-08 | 2026-12-23 | 12 | 0% | 4.0.3.2 | J. Lee | U. Marchetti, V. Okwuosa, W. Pham, X. Delgado | Customer UX / Design (8) | 480
4.0.3.4 | Conversational / interaction design | 3 | Group task | 2026-12-24 | 2027-01-06 | 10 | 0% | 4.0.3.3 | X. Delgado | Y. Nakashima (UX), J. Lee, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 376
4.0.3.5 | Accessibility & WCAG compliance review | 3 | Group task | 2027-01-07 | 2027-01-18 | 8 | 0% | 4.0.3.4 | J. Lee | U. Marchetti, V. Okwuosa, W. Pham, X. Delgado | Customer UX / Design (8) | 320
4.0.3.6 | Usability testing & design iteration | 3 | Summary | 2027-01-19 | 2027-02-03 | 12 | 0%
4.0.3.6.1 | Usability test sessions | 4 | Group task | 2027-01-19 | 2027-01-26 | 6 | 0% | 4.0.3.5 | X. Delgado | Y. Nakashima (UX), J. Lee, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 225
4.0.3.6.2 | Design refinement from findings | 4 | Group task | 2027-01-27 | 2027-02-03 | 6 | 0% | 4.0.3.6.1 | J. Lee | U. Marchetti, V. Okwuosa, W. Pham, X. Delgado | Customer UX / Design (8) | 240
4.0.4 | Clinical / Business Policy Alignment | 2 | Summary | 2026-11-24 | 2027-01-12 | 36 | 0%
4.0.4.1 | Clinical policy & medical necessity criteria review | 3 | Group task | 2026-11-24 | 2026-12-07 | 10 | 0% |  | L. Delacroix | M. Beaumont, Dr. J. Whitby, Dr. I. Alvarado, Dr. N. Patel | Clinical / Medical Policy & Informatics (6) | 260
4.0.4.2 | Decision-logic clinical validation | 3 | Group task | 2026-12-08 | 2026-12-21 | 10 | 0% | 4.0.4.1 | K. Okoro | L. Delacroix, Dr. J. Whitby, M. Beaumont, Dr. N. Patel | Clinical / Medical Policy & Informatics (6) | 300
4.0.4.3 | Provider & utilization-management impact review | 3 | Group task | 2026-12-22 | 2026-12-31 | 8 | 0% | 4.0.4.2 | K. Okoro | L. Delacroix, Dr. J. Whitby, Dr. I. Alvarado, Dr. N. Patel | Clinical / Medical Policy & Informatics (6) | 221
4.0.4.4 | Policy exception & appeals handling design | 3 | Task | 2027-01-01 | 2027-01-12 | 8 | 0% | 4.0.4.3 | Dr. J. Whitby | Dr. I. Alvarado, Dr. N. Patel |  | 99
4.0.5 | Data Engineering & Feature Prep | 2 | Summary | 2026-12-10 | 2027-03-04 | 61 | 0%
4.0.5.1 | Data profiling & quality assessment | 3 | Summary | 2026-12-10 | 2026-12-25 | 12 | 0%
4.0.5.1.1 | Legacy source profiling | 4 | Group task | 2026-12-10 | 2026-12-17 | 6 | 0% |  | S. Fitzgerald | T. Andersen, U. Kowalczyk2, V. Delvecchio2, W. Solberg2 | Data & Cloud AI Platform Foundation (20) | 240
4.0.5.1.2 | Data quality scorecard & remediation plan | 4 | Task | 2026-12-18 | 2026-12-25 | 6 | 0% | 4.0.5.1.1 | W. Solberg2 | X. Nakashima2 |  | 96
4.0.5.2 | Data ingestion & pipeline build | 3 | Summary | 2026-12-28 | 2027-01-15 | 15 | 0%
4.0.5.2.1 | Source connectors & ingestion | 4 | Group task | 2026-12-28 | 2027-01-05 | 7 | 0% | 4.0.5.1 | X. Nakashima2 | Y. Winfield2, Z. Achebe2, A. Larsen2, B. Sorensen2 | Data & Cloud AI Platform Foundation (20) | 268
4.0.5.2.2 | Transformation & cleansing rules | 4 | Task | 2027-01-06 | 2027-01-15 | 8 | 0% | 4.0.5.2.1 | W. Kumar | B. Sorensen2 |  | 122
4.0.5.3 | Data remediation execution | 3 | Group task | 2027-01-18 | 2027-02-02 | 12 | 0% | 4.0.5.2 | W. Kumar | J. Restrepo, K. Vartan, L. Sondheim, M. Marchetti | Data & Cloud AI Platform Foundation (20) | 480
4.0.5.4 | Feature engineering & dataset assembly | 3 | Task | 2027-02-03 | 2027-02-18 | 12 | 0% | 4.0.5.3 | F. Bennett | C. Garcia2, D. Thompson2 |  | 288
4.0.5.5 | Data privacy & PHI controls validation | 3 | Task | 2027-02-19 | 2027-02-26 | 6 | 0% | 4.0.5.4 | N. Achterberg | E. Sato |  | 67
4.0.5.6 | Training / test dataset governance sign-off | 3 | Task | 2027-03-01 | 2027-03-04 | 4 | 0% | 4.0.5.5 | D. Ibrahim | K. Novak |  | 58
4.0.6 | Model Development & Training | 2 | Summary | 2026-12-28 | 2027-03-25 | 64 | 0%
4.0.6.1 | Baseline model build | 3 | Task | 2026-12-28 | 2027-01-15 | 15 | 0% |  | M. Beaumont2 | N. Kowalczyk3, O. Delvecchio3 |  | 360
4.0.6.2 | Model training & iteration cycles | 3 | Summary | 2027-01-18 | 2027-02-16 | 22 | 0%
4.0.6.2.1 | Training run cycle 1 | 4 | Group task | 2027-01-18 | 2027-01-25 | 6 | 0% | 4.0.6.1 | O. Delvecchio3 | P. Solberg3, Q. Nakashima3, R. Winfield3, S. Achebe3 | Claims & Prior Authorization AI (BRD-01) (28) | 240
4.0.6.2.2 | Evaluation & error analysis | 4 | Task | 2027-01-26 | 2027-02-01 | 5 | 0% | 4.0.6.2.1 | S. Achebe3 | T. Larsen3 |  | 80
4.0.6.2.3 | Training run cycle 2 (tuned) | 4 | Group task | 2027-02-02 | 2027-02-09 | 6 | 0% | 4.0.6.2.2 | T. Larsen3 | U. Sorensen3, V. Kessler2, W. Rutherford2, X. Alvarado2 | Claims & Prior Authorization AI (BRD-01) (28) | 240
4.0.6.2.4 | Training run cycle 3 (final) | 4 | Task | 2027-02-10 | 2027-02-16 | 5 | 0% | 4.0.6.2.3 | X. Alvarado2 | Y. Whitby3 |  | 80
4.0.6.3 | Bias & fairness evaluation | 3 | Task | 2027-02-17 | 2027-02-26 | 8 | 0% | 4.0.6.2 | F. Bennett | C. Garcia2 |  | 128
4.0.6.4 | Explainability & guardrail implementation | 3 | Task | 2027-03-01 | 2027-03-10 | 8 | 0% | 4.0.6.3 | Y. Whitby3 | Z. Okoro3 |  | 128
4.0.6.5 | Model documentation & model card | 3 | Task | 2027-03-11 | 2027-03-18 | 6 | 0% | 4.0.6.4 | Z. Okoro3 | A. Delacroix3 |  | 91
4.0.6.6 | Model peer review (first line) | 3 | Task | 2027-03-19 | 2027-03-25 | 5 | 0% | 4.0.6.5 | B. Vartan3 | A. Delacroix3 |  | 76
4.0.7 | Iterative Build (Sprints) | 2 | Summary | 2027-01-13 | 2027-04-22 | 72 | 0%
4.0.7.1 | Sprint 1 — build & integrate | 3 | Summary | 2027-01-13 | 2027-01-25 | 9 | 0%
4.0.7.1.1 | Sprint 1 planning & backlog refinement | 4 | Task | 2027-01-13 | 2027-01-13 | 1 | 0% |  | B. Vartan3 | C. Halvorsen3 |  | 16
4.0.7.1.2 | Sprint 1 feature & model development | 4 | Group task | 2027-01-14 | 2027-01-20 | 5 | 0% | 4.0.7.1.1 | C. Halvorsen3 | F. Bennett, C. Garcia2, D. Thompson2, E. Washington2 | Claims & Prior Authorization AI (BRD-01) (28) | 200
4.0.7.1.3 | Sprint 1 code review & merge | 4 | Task | 2027-01-21 | 2027-01-22 | 2 | 0% | 4.0.7.1.2 | E. Washington2 | F. Ferraro2 |  | 32
4.0.7.1.4 | Sprint 1 demo, review & retrospective | 4 | Task | 2027-01-25 | 2027-01-25 | 1 | 0% | 4.0.7.1.3 | F. Ferraro2 | G. Delacroix2 |  | 16
4.0.7.2 | Sprint 2 — build & integrate | 3 | Summary | 2027-01-26 | 2027-02-05 | 9 | 0%
4.0.7.2.1 | Sprint 2 planning & backlog refinement | 4 | Task | 2027-01-26 | 2027-01-26 | 1 | 0% | 4.0.7.1 | G. Delacroix2 | H. Vartan2 |  | 16
4.0.7.2.2 | Sprint 2 feature & model development | 4 | Group task | 2027-01-27 | 2027-02-02 | 5 | 0% | 4.0.7.2.1 | H. Vartan2 | I. Halvorsen2, J. Nakamura2, K. Okoro2, L. Whitby2 | Claims & Prior Authorization AI (BRD-01) (28) | 200
4.0.7.2.3 | Sprint 2 code review & merge | 4 | Task | 2027-02-03 | 2027-02-04 | 2 | 0% | 4.0.7.2.2 | L. Whitby2 | M. Beaumont2 |  | 32
4.0.7.2.4 | Sprint 2 demo, review & retrospective | 4 | Task | 2027-02-05 | 2027-02-05 | 1 | 0% | 4.0.7.2.3 | M. Beaumont2 | N. Kowalczyk3 |  | 16
4.0.7.3 | Sprint 3 — build & integrate | 3 | Summary | 2027-02-08 | 2027-02-18 | 9 | 0%
4.0.7.3.1 | Sprint 3 planning & backlog refinement | 4 | Task | 2027-02-08 | 2027-02-08 | 1 | 0% | 4.0.7.2 | N. Kowalczyk3 | O. Delvecchio3 |  | 16
4.0.7.3.2 | Sprint 3 feature & model development | 4 | Group task | 2027-02-09 | 2027-02-15 | 5 | 0% | 4.0.7.3.1 | O. Delvecchio3 | P. Solberg3, Q. Nakashima3, R. Winfield3, S. Achebe3 | Claims & Prior Authorization AI (BRD-01) (28) | 200
4.0.7.3.3 | Sprint 3 code review & merge | 4 | Task | 2027-02-16 | 2027-02-17 | 2 | 0% | 4.0.7.3.2 | S. Achebe3 | T. Larsen3 |  | 32
4.0.7.3.4 | Sprint 3 demo, review & retrospective | 4 | Task | 2027-02-18 | 2027-02-18 | 1 | 0% | 4.0.7.3.3 | T. Larsen3 | U. Sorensen3 |  | 16
4.0.7.4 | Sprint 4 — build & integrate | 3 | Summary | 2027-02-19 | 2027-03-03 | 9 | 0%
4.0.7.4.1 | Sprint 4 planning & backlog refinement | 4 | Task | 2027-02-19 | 2027-02-19 | 1 | 0% | 4.0.7.3 | U. Sorensen3 | V. Kessler2 |  | 16
4.0.7.4.2 | Sprint 4 feature & model development | 4 | Group task | 2027-02-22 | 2027-02-26 | 5 | 0% | 4.0.7.4.1 | V. Kessler2 | W. Rutherford2, X. Alvarado2, Y. Whitby3, Z. Okoro3 | Claims & Prior Authorization AI (BRD-01) (28) | 200
4.0.7.4.3 | Sprint 4 code review & merge | 4 | Task | 2027-03-01 | 2027-03-02 | 2 | 0% | 4.0.7.4.2 | Z. Okoro3 | A. Delacroix3 |  | 30
4.0.7.4.4 | Sprint 4 demo, review & retrospective | 4 | Task | 2027-03-03 | 2027-03-03 | 1 | 0% | 4.0.7.4.3 | B. Vartan3 | A. Delacroix3 |  | 15
4.0.7.5 | Sprint 5 — build & integrate | 3 | Summary | 2027-03-04 | 2027-03-16 | 9 | 0%
4.0.7.5.1 | Sprint 5 planning & backlog refinement | 4 | Task | 2027-03-04 | 2027-03-04 | 1 | 0% | 4.0.7.4 | B. Vartan3 | C. Halvorsen3 |  | 16
4.0.7.5.2 | Sprint 5 feature & model development | 4 | Group task | 2027-03-05 | 2027-03-11 | 5 | 0% | 4.0.7.5.1 | C. Halvorsen3 | F. Bennett, C. Garcia2, D. Thompson2, E. Washington2 | Claims & Prior Authorization AI (BRD-01) (28) | 200
4.0.7.5.3 | Sprint 5 code review & merge | 4 | Task | 2027-03-12 | 2027-03-15 | 2 | 0% | 4.0.7.5.2 | E. Washington2 | F. Ferraro2 |  | 32
4.0.7.5.4 | Sprint 5 demo, review & retrospective | 4 | Task | 2027-03-16 | 2027-03-16 | 1 | 0% | 4.0.7.5.3 | F. Ferraro2 | G. Delacroix2 |  | 16
4.0.7.6 | Sprint 6 — build & integrate | 3 | Summary | 2027-03-17 | 2027-03-29 | 9 | 0%
4.0.7.6.1 | Sprint 6 planning & backlog refinement | 4 | Task | 2027-03-17 | 2027-03-17 | 1 | 0% | 4.0.7.5 | G. Delacroix2 | H. Vartan2 |  | 16
4.0.7.6.2 | Sprint 6 feature & model development | 4 | Group task | 2027-03-18 | 2027-03-24 | 5 | 0% | 4.0.7.6.1 | H. Vartan2 | I. Halvorsen2, J. Nakamura2, K. Okoro2, L. Whitby2 | Claims & Prior Authorization AI (BRD-01) (28) | 200
4.0.7.6.3 | Sprint 6 code review & merge | 4 | Task | 2027-03-25 | 2027-03-26 | 2 | 0% | 4.0.7.6.2 | L. Whitby2 | M. Beaumont2 |  | 32
4.0.7.6.4 | Sprint 6 demo, review & retrospective | 4 | Task | 2027-03-29 | 2027-03-29 | 1 | 0% | 4.0.7.6.3 | M. Beaumont2 | N. Kowalczyk3 |  | 16
4.0.7.7 | Sprint 7 — build & integrate | 3 | Summary | 2027-03-30 | 2027-04-09 | 9 | 0%
4.0.7.7.1 | Sprint 7 planning & backlog refinement | 4 | Task | 2027-03-30 | 2027-03-30 | 1 | 0% | 4.0.7.6 | N. Kowalczyk3 | O. Delvecchio3 |  | 16
4.0.7.7.2 | Sprint 7 feature & model development | 4 | Group task | 2027-03-31 | 2027-04-06 | 5 | 0% | 4.0.7.7.1 | O. Delvecchio3 | P. Solberg3, Q. Nakashima3, R. Winfield3, S. Achebe3 | Claims & Prior Authorization AI (BRD-01) (28) | 200
4.0.7.7.3 | Sprint 7 code review & merge | 4 | Task | 2027-04-07 | 2027-04-08 | 2 | 0% | 4.0.7.7.2 | S. Achebe3 | T. Larsen3 |  | 32
4.0.7.7.4 | Sprint 7 demo, review & retrospective | 4 | Task | 2027-04-09 | 2027-04-09 | 1 | 0% | 4.0.7.7.3 | T. Larsen3 | U. Sorensen3 |  | 16
4.0.7.8 | Sprint 8 — build & integrate | 3 | Summary | 2027-04-12 | 2027-04-22 | 9 | 0%
4.0.7.8.1 | Sprint 8 planning & backlog refinement | 4 | Task | 2027-04-12 | 2027-04-12 | 1 | 0% | 4.0.7.7 | U. Sorensen3 | V. Kessler2 |  | 16
4.0.7.8.2 | Sprint 8 feature & model development | 4 | Group task | 2027-04-13 | 2027-04-19 | 5 | 0% | 4.0.7.8.1 | V. Kessler2 | W. Rutherford2, X. Alvarado2, Y. Whitby3, Z. Okoro3 | Claims & Prior Authorization AI (BRD-01) (28) | 200
4.0.7.8.3 | Sprint 8 code review & merge | 4 | Task | 2027-04-20 | 2027-04-21 | 2 | 0% | 4.0.7.8.2 | Z. Okoro3 | A. Delacroix3 |  | 30
4.0.7.8.4 | Sprint 8 demo, review & retrospective | 4 | Task | 2027-04-22 | 2027-04-22 | 1 | 0% | 4.0.7.8.3 | B. Vartan3 | A. Delacroix3 |  | 15
4.0.8 | Integration & Environment Build | 2 | Summary | 2027-01-29 | 2027-03-29 | 42 | 0%
4.0.8.1 | Application & workflow integration | 3 | Summary | 2027-01-29 | 2027-02-25 | 20 | 0%
4.0.8.1.1 | API & service integration | 4 | Group task | 2027-01-29 | 2027-02-09 | 8 | 0% |  | B. Vartan3 | C. Halvorsen3, F. Bennett, C. Garcia2, D. Thompson2 | Claims & Prior Authorization AI (BRD-01) (28) | 320
4.0.8.1.2 | Human-in-the-loop review workflow | 4 | Task | 2027-02-10 | 2027-02-17 | 6 | 0% | 4.0.8.1.1 | D. Thompson2 | E. Washington2 |  | 96
4.0.8.1.3 | Channel / UI integration | 4 | Task | 2027-02-18 | 2027-02-25 | 6 | 0% | 4.0.8.1.2 | E. Washington2 | F. Ferraro2 |  | 96
4.0.8.2 | MLOps deployment pipeline setup | 3 | Task | 2027-02-26 | 2027-03-11 | 10 | 0% | 4.0.8.1 | M. Marchetti | N. Whitcomb |  | 160
4.0.8.3 | Environment build & configuration | 3 | Group task | 2027-03-12 | 2027-03-19 | 6 | 0% | 4.0.8.2 | B. Fairweather | C. Sondheim, D. Marchetti, E. Whitcomb, F. Talbot | IT Operations / Infrastructure (10) | 240
4.0.8.4 | Integration smoke test & stabilization | 3 | Task | 2027-03-22 | 2027-03-29 | 6 | 0% | 4.0.8.3 | F. Ferraro2 | G. Delacroix2 |  | 96
4.0.9 | Testing & QA | 2 | Summary | 2027-02-16 | 2027-06-24 | 93 | 0%
4.0.9.1 | Test strategy & plan | 3 | Task | 2027-02-16 | 2027-02-23 | 6 | 0% |  | V. Müller | J. Bennett |  | 96
4.0.9.2 | Test case authoring & data setup | 3 | Group task | 2027-02-24 | 2027-03-09 | 10 | 0% | 4.0.9.1 | J. Bennett | K. Garcia, L. Thompson, M. Washington (QA), N. Ferraro | QA & Testing (18) | 400
4.0.9.3 | Unit & component testing | 3 | Group task | 2027-03-10 | 2027-03-23 | 10 | 0% | 4.0.9.2 | N. Ferraro | O. Delacroix, P. Vartan, Q. Halvorsen, R. Nakamura | QA & Testing (18) | 400
4.0.9.4 | Integration testing | 3 | Group task | 2027-03-24 | 2027-04-08 | 12 | 0% | 4.0.9.3 | R. Nakamura | S. Okoro, T. Whitby, U. Beaumont, V. Kowalczyk | QA & Testing (18) | 480
4.0.9.5 | System & end-to-end testing | 3 | Summary | 2027-04-09 | 2027-04-26 | 12 | 0%
4.0.9.5.1 | Functional E2E scenarios | 4 | Group task | 2027-04-09 | 2027-04-16 | 6 | 0% | 4.0.9.4 | V. Kowalczyk | W. Delvecchio, X. Solberg, Y. Nakashima (QA), Z. Winfield (QA) | QA & Testing (18) | 235
4.0.9.5.2 | Negative & edge-case testing | 4 | Task | 2027-04-19 | 2027-04-26 | 6 | 0% | 4.0.9.5.1 | V. Müller | Z. Winfield (QA) |  | 91
4.0.9.6 | Model performance & regression testing | 3 | Task | 2027-04-27 | 2027-05-10 | 10 | 0% | 4.0.9.5 | V. Müller | J. Bennett, K. Garcia |  | 240
4.0.9.7 | Security & penetration testing | 3 | Group task | 2027-05-11 | 2027-05-20 | 8 | 0% | 4.0.9.6 | N. Winthrop | O. Castillo, P. Halstead, Q. Beaumont, M. Hassan | Cybersecurity / InfoSec (10) | 269
4.0.9.8 | Performance & load testing | 3 | Task | 2027-05-21 | 2027-06-01 | 8 | 0% | 4.0.9.7 | V. Müller | J. Bennett |  | 128
4.0.9.9 | Defect triage & resolution cycles | 3 | Group task | 2027-06-02 | 2027-06-17 | 12 | 0% | 4.0.9.8 | K. Garcia | L. Thompson, M. Washington (QA), N. Ferraro, O. Delacroix | QA & Testing (18) + Claims & Prior Authorization AI (BRD-01) (28) | 480
4.0.9.10 | Test summary & exit report | 3 | Task | 2027-06-18 | 2027-06-24 | 5 | 0% | 4.0.9.9 | J. Bennett | K. Garcia |  | 80
4.0.10 | Independent Model Validation | 2 | Summary | 2027-03-04 | 2027-04-09 | 27 | 0%
4.0.10.1 | IMV submission & documentation review | 3 | Task | 2027-03-04 | 2027-03-11 | 6 | 0% |  | P. Okafor | W. Achebe |  | 96
4.0.10.2 | Independent performance & fairness validation | 3 | Summary | 2027-03-12 | 2027-03-25 | 10 | 0%
4.0.10.2.1 | Independent replication testing | 4 | Task | 2027-03-12 | 2027-03-18 | 5 | 0% | 4.0.10.1 | W. Achebe | X. Sorensen |  | 80
4.0.10.2.2 | Fairness & bias re-testing | 4 | Task | 2027-03-19 | 2027-03-25 | 5 | 0% | 4.0.10.2.1 | X. Sorensen | Y. Larsen |  | 80
4.0.10.3 | Validation findings & remediation | 3 | Task | 2027-03-26 | 2027-04-06 | 8 | 0% | 4.0.10.2 | P. Okafor | W. Achebe, X. Sorensen |  | 192
4.0.10.4 | IMV sign-off (production gate) | 3 | Task | 2027-04-07 | 2027-04-09 | 3 | 0% | 4.0.10.3 | Y. Larsen | Z. Winfield (IMV) |  | 48
4.0.11 | Compliance, Clinical & Controls Review | 2 | Summary | 2027-03-22 | 2027-05-13 | 39 | 0%
4.0.11.1 | Legal review (liability, disclaimers, contracts) | 3 | Group task | 2027-03-22 | 2027-03-29 | 6 | 0% |  | K. Okonkwo | M. Bernstein, S. Patel, D. Flores, R. Thorne | Legal (6) | 187
4.0.11.2 | Compliance & regulatory review | 3 | Group task | 2027-03-30 | 2027-04-08 | 8 | 0% | 4.0.11.1 | L. Huang | T. Jackson, R. Kimani, B. Cho, C. Morrison | Compliance (7) | 291
4.0.11.3 | Clinical / medical-policy review | 3 | Group task | 2027-04-09 | 2027-04-19 | 7 | 0% | 4.0.11.2 | L. Delacroix | M. Beaumont, Dr. J. Whitby, Dr. I. Alvarado, Dr. N. Patel | Clinical / Medical Policy & Informatics (6) | 182
4.0.11.4 | SOX / financial-controls testing | 3 | Group task | 2027-04-20 | 2027-04-27 | 6 | 0% | 4.0.11.3 | M. Osei | N. Brennan, P. Whitcomb, O. Fairweather, K. Williams | SOX / Financial Controls (6) | 199
4.0.11.5 | Data privacy audit & DPIA | 3 | Task | 2027-04-28 | 2027-05-05 | 6 | 0% | 4.0.11.4 | N. Achterberg | O. Whitlock |  | 96
4.0.11.6 | Cybersecurity controls assurance | 3 | Task | 2027-05-06 | 2027-05-13 | 6 | 0% | 4.0.11.5 | Q. Beaumont | R. Fontaine |  | 96
4.0.12 | User Acceptance Testing | 2 | Summary | 2027-04-07 | 2027-06-14 | 49 | 0%
4.0.12.1 | UAT planning & environment readiness | 3 | Group task | 2027-04-07 | 2027-04-14 | 6 | 0% |  | Y. Sorensen6 | Z. Kessler5, A. Rutherford5, B. Alvarado5, C. Whitby8 | User Acceptance Testing (UAT) (11) | 144
4.0.12.2 | UAT test scenario authoring | 3 | Group task | 2027-04-15 | 2027-04-26 | 8 | 0% | 4.0.12.1 | C. Whitby8 | D. Okoro8, E. Beaumont6, F. Kowalczyk7, G. Delvecchio7 | User Acceptance Testing (UAT) (11) | 160
4.0.12.3 | UAT execution cycles | 3 | Summary | 2027-04-27 | 2027-05-24 | 20 | 0%
4.0.12.3.1 | UAT cycle 1 | 4 | Group task | 2027-04-27 | 2027-05-04 | 6 | 0% | 4.0.12.2 | Y. Sorensen6 | H. Solberg7, I. Nakashima7, G. Delvecchio7, Z. Kessler5 | User Acceptance Testing (UAT) (11) | 168
4.0.12.3.2 | UAT defect fixes & retest | 4 | Group task | 2027-05-05 | 2027-05-11 | 5 | 0% | 4.0.12.3.1 | Z. Kessler5 | A. Rutherford5, B. Alvarado5, C. Whitby8, D. Okoro8 | User Acceptance Testing (UAT) (11) | 100
4.0.12.3.3 | UAT cycle 2 (regression) | 4 | Group task | 2027-05-12 | 2027-05-18 | 5 | 0% | 4.0.12.3.2 | H. Solberg7 | D. Okoro8, E. Beaumont6, F. Kowalczyk7, G. Delvecchio7 | User Acceptance Testing (UAT) (11) | 112
4.0.12.3.4 | Final UAT confirmation | 4 | Group task | 2027-05-19 | 2027-05-24 | 4 | 0% | 4.0.12.3.3 | Y. Sorensen6 | H. Solberg7, I. Nakashima7, Z. Kessler5, A. Rutherford5 | User Acceptance Testing (UAT) (11) | 112
4.0.12.4 | Business process & runbook validation | 3 | Group task | 2027-05-25 | 2027-06-01 | 6 | 0% | 4.0.12.3 | F. Talbot | G. Restrepo, H. Vartan, I. Halvorsen, H. Nakamura | IT Operations / Infrastructure (10) | 196
4.0.12.5 | Operational readiness assessment | 3 | Group task | 2027-06-02 | 2027-06-09 | 6 | 0% | 4.0.12.4 | N. Alvarado4 | O. Whitby7, P. Okoro7, Q. Beaumont5, M. Washington (CustOps) | Customer Service Operations (12) | 202
4.0.12.6 | UAT sign-off | 3 | Task | 2027-06-10 | 2027-06-14 | 3 | 0% | 4.0.12.5 | A. Rutherford5 | B. Alvarado5 |  | 24
4.0.13 | Change Management & Adoption | 2 | Summary | 2027-04-23 | 2027-07-08 | 55 | 0%
4.0.13.1 | Change impact assessment & stakeholder analysis | 3 | Task | 2027-04-23 | 2027-05-03 | 7 | 0% |  | E. Winthrop | F. Achebe |  | 95
4.0.13.2 | Training material development | 3 | Summary | 2027-05-04 | 2027-05-17 | 10 | 0%
4.0.13.2.1 | End-user training curriculum | 4 | Task | 2027-05-04 | 2027-05-10 | 5 | 0% | 4.0.13.1 | F. Achebe | H. Kandel |  | 60
4.0.13.2.2 | Job aids & quick-reference | 4 | Task | 2027-05-11 | 2027-05-17 | 5 | 0% | 4.0.13.2.1 | I. Redmond | H. Kandel |  | 60
4.0.13.3 | Training delivery & enablement | 3 | Group task | 2027-05-18 | 2027-06-02 | 12 | 0% | 4.0.13.2 | G. Okonkwo | B. Prescott, C. Whitfield, D. Solis, I. Redmond | Change Management & Training (8) | 461
4.0.13.4 | Communications campaign | 3 | Group task | 2027-06-03 | 2027-06-14 | 8 | 0% | 4.0.13.3 | R. Castellanos | S. Halloway, T. Ainslie, B. Sullivan | Corporate Communications / PR (4) | 173
4.0.13.5 | Frontline readiness & super-user network | 3 | Group task | 2027-06-15 | 2027-06-24 | 8 | 0% | 4.0.13.4 | Q. Beaumont5 | S. Delvecchio6, T. Solberg6, R. Kowalczyk6, U. Nakashima6 | Customer Service Operations (12) | 301
4.0.13.6 | Adoption tracking & reinforcement | 3 | Task | 2027-06-25 | 2027-07-08 | 10 | 0% | 4.0.13.5 | D. Solis | E. Winthrop |  | 152
4.0.14 | Pilot Deployment | 2 | Summary | 2027-05-11 | 2027-07-05 | 40 | 0%
4.0.14.1 | Pilot readiness review & go/no-go | 3 | Task | 2027-05-11 | 2027-05-14 | 4 | 0% |  | G. Delacroix2 | H. Vartan2 |  | 64
4.0.14.2 | Controlled pilot rollout | 3 | Group task | 2027-05-17 | 2027-06-01 | 12 | 0% | 4.0.14.1 | H. Vartan2 | I. Halvorsen2, J. Nakamura2, K. Okoro2, L. Whitby2 | Claims & Prior Authorization AI (BRD-01) (28) | 480
4.0.14.3 | Pilot monitoring & tuning | 3 | Task | 2027-06-02 | 2027-06-15 | 10 | 0% | 4.0.14.2 | C. Garcia2 | D. Thompson2, E. Washington2 |  | 240
4.0.14.4 | Pilot support & issue resolution | 3 | Group task | 2027-06-16 | 2027-06-29 | 10 | 0% | 4.0.14.3 | X. Larsen6 | U. Nakashima6, V. Winfield6, W. Achebe6, M. Washington (CustOps) | Customer Service Operations (12) | 280
4.0.14.5 | Pilot evaluation & production decision | 3 | Task | 2027-06-30 | 2027-07-05 | 4 | 0% | 4.0.14.4 | L. Whitby2 | M. Beaumont2 |  | 64
4.0.15 | Production Deployment & Hypercare | 2 | Summary | 2027-05-27 | 2027-08-02 | 48 | 0%
4.0.15.1 | Production readiness review (3 boards) | 3 | Task | 2027-05-27 | 2027-06-02 | 5 | 0% |  | M. Beaumont2 | N. Kowalczyk3 |  | 80
4.0.15.2 | Production cutover & go-live | 3 | Group task | 2027-06-03 | 2027-06-10 | 6 | 0% | 4.0.15.1 | F. Bennett | C. Garcia2, D. Thompson2, E. Washington2, F. Ferraro2 | Claims & Prior Authorization AI (BRD-01) (28) + IT Operations / Infrastructure (10) | 240
4.0.15.3 | Hypercare & stabilization | 3 | Summary | 2027-06-11 | 2027-07-01 | 15 | 0%
4.0.15.3.1 | Hypercare monitoring | 4 | Group task | 2027-06-11 | 2027-06-22 | 8 | 0% | 4.0.15.2 | N. Kowalczyk3 | O. Delvecchio3, P. Solberg3, Q. Nakashima3, R. Winfield3 | Claims & Prior Authorization AI (BRD-01) (28) | 320
4.0.15.3.2 | Incident response & fixes | 4 | Group task | 2027-06-23 | 2027-07-01 | 7 | 0% | 4.0.15.3.1 | R. Winfield3 | S. Achebe3, T. Larsen3, U. Sorensen3, V. Kessler2 | Claims & Prior Authorization AI (BRD-01) (28) | 280
4.0.15.4 | Post-go-live service desk support | 3 | Group task | 2027-07-02 | 2027-07-19 | 12 | 0% | 4.0.15.3 | N. Alvarado4 | O. Whitby7, P. Okoro7, Q. Beaumont5, M. Washington (CustOps) | Customer Service Operations (12) | 403
4.0.15.5 | Benefits baseline established | 3 | Task | 2027-07-20 | 2027-07-23 | 4 | 0% | 4.0.15.4 | F. Bennett | C. Garcia2 |  | 64
4.0.15.6 | Transition to steady-state operations | 3 | Task | 2027-07-26 | 2027-08-02 | 6 | 0% | 4.0.15.5 | A. Prescott | H. Nakamura |  | 62
5.0 | BRD-02 · Member & Provider Experience AI | 1 | Summary | 2027-10-01 | 2028-08-17 | 230 | 0%
5.0.1 | Requirements & JAD | 2 | Summary | 2027-10-01 | 2027-12-24 | 61 | 0%
5.0.1.1 | Requirements elicitation workshops (JAD series) | 3 | Summary | 2027-10-01 | 2027-10-25 | 17 | 0%
5.0.1.1.1 | Current-state process mapping | 4 | Task | 2027-10-01 | 2027-10-08 | 6 | 0% |  | X. Garcia | D. Nakamura3 |  | 96
5.0.1.1.2 | Use-case & user-story definition | 4 | Group task | 2027-10-11 | 2027-10-18 | 6 | 0% | 5.0.1.1.1 | D. Nakamura3 | E. Okoro4, F. Whitby4, G. Beaumont3, H. Kowalczyk4 | Member & Provider Experience AI (BRD-02) (22) | 240
5.0.1.1.3 | Non-functional & compliance requirements | 4 | Task | 2027-10-19 | 2027-10-25 | 5 | 0% | 5.0.1.1.2 | X. Garcia | D. Nakamura3 |  | 80
5.0.1.2 | Data & source-system requirements | 3 | Summary | 2027-10-26 | 2027-11-04 | 8 | 0%
5.0.1.2.1 | Source-system inventory | 4 | Task | 2027-10-26 | 2027-10-29 | 4 | 0% | 5.0.1.1 | N. Whitcomb | O. Talbot |  | 64
5.0.1.2.2 | Data availability & quality requirements | 4 | Task | 2027-11-01 | 2027-11-04 | 4 | 0% | 5.0.1.2.1 | O. Talbot | P. Restrepo2 |  | 64
5.0.1.3 | Model & decision-logic requirements | 3 | Task | 2027-11-05 | 2027-11-16 | 8 | 0% | 5.0.1.2 | H. Kowalczyk4 | I. Delvecchio4 |  | 128
5.0.1.4 | Business rules & policy catalogue | 3 | Task | 2027-11-17 | 2027-11-25 | 7 | 0% | 5.0.1.3 | X. Garcia | D. Nakamura3 |  | 112
5.0.1.5 | Clinical / actuarial SME requirements review | 3 | Group task | 2027-11-26 | 2027-12-03 | 6 | 0% | 5.0.1.4 | X. Delgado | Y. Nakashima (UX), J. Lee, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 225
5.0.1.6 | Requirements traceability matrix baseline | 3 | Task | 2027-12-06 | 2027-12-10 | 5 | 0% | 5.0.1.5 | I. Delvecchio4 | J. Solberg4 |  | 80
5.0.1.7 | Requirements review & BRD authoring | 3 | Task | 2027-12-13 | 2027-12-21 | 7 | 0% | 5.0.1.6 | J. Solberg4 | K. Nakashima4 |  | 112
5.0.1.8 | BRD sign-off (JAD close, AI Governance Board) | 3 | Task | 2027-12-22 | 2027-12-24 | 3 | 0% | 5.0.1.7 | K. Nakashima4 | L. Winfield4 |  | 48
5.0.2 | Architecture & Design | 2 | Summary | 2027-10-20 | 2028-01-06 | 57 | 0%
5.0.2.1 | Solution architecture & integration design | 3 | Summary | 2027-10-20 | 2027-11-04 | 12 | 0%
5.0.2.1.1 | Target-state architecture | 4 | Task | 2027-10-20 | 2027-10-27 | 6 | 0% |  | H. Delgado | I. Suzuki |  | 96
5.0.2.1.2 | Integration & API design | 4 | Task | 2027-10-28 | 2027-11-04 | 6 | 0% | 5.0.2.1.1 | I. Suzuki | J. Kowalczyk |  | 96
5.0.2.2 | Data architecture & pipeline design | 3 | Task | 2027-11-05 | 2027-11-18 | 10 | 0% | 5.0.2.1 | P. Restrepo2 | Q. Halvorsen2 |  | 160
5.0.2.3 | Model design & approach selection | 3 | Summary | 2027-11-19 | 2027-12-02 | 10 | 0%
5.0.2.3.1 | Model approach evaluation | 4 | Task | 2027-11-19 | 2027-11-25 | 5 | 0% | 5.0.2.2 | L. Winfield4 | M. Achebe4 |  | 80
5.0.2.3.2 | Model design specification | 4 | Task | 2027-11-26 | 2027-12-02 | 5 | 0% | 5.0.2.3.1 | M. Achebe4 | N. Larsen4 |  | 80
5.0.2.4 | Security threat model & controls design | 3 | Group task | 2027-12-03 | 2027-12-14 | 8 | 0% | 5.0.2.3 | R. Fontaine | S. Vasquez, T. Delvecchio, U. Kandel, V. Redmond | Cybersecurity / InfoSec (10) | 301
5.0.2.5 | Privacy-by-design & PHI data-flow review | 3 | Task | 2027-12-15 | 2027-12-22 | 6 | 0% | 5.0.2.4 | O. Whitlock | P. Sandoval |  | 91
5.0.2.6 | Infrastructure & environment design | 3 | Task | 2027-12-23 | 2027-12-31 | 7 | 0% | 5.0.2.5 | A. Prescott | B. Fairweather |  | 112
5.0.2.7 | Design review & EARB approval | 3 | Task | 2028-01-03 | 2028-01-06 | 4 | 0% | 5.0.2.6 | J. Kowalczyk | K. Andersen |  | 58
5.0.3 | Experience & Interaction Design | 2 | Summary | 2027-11-08 | 2028-02-03 | 64 | 0%
5.0.3.1 | User research & journey mapping | 3 | Group task | 2027-11-08 | 2027-11-19 | 10 | 0% |  | J. Lee | U. Marchetti, V. Okwuosa, W. Pham, X. Delgado | Customer UX / Design (8) | 400
5.0.3.2 | Information architecture & wireframes | 3 | Group task | 2027-11-22 | 2027-12-07 | 12 | 0% | 5.0.3.1 | X. Delgado | Y. Nakashima (UX), J. Lee, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 451
5.0.3.3 | Design system & component library | 3 | Group task | 2027-12-08 | 2027-12-23 | 12 | 0% | 5.0.3.2 | J. Lee | U. Marchetti, V. Okwuosa, W. Pham, X. Delgado | Customer UX / Design (8) | 480
5.0.3.4 | Conversational / interaction design | 3 | Group task | 2027-12-24 | 2028-01-06 | 10 | 0% | 5.0.3.3 | X. Delgado | Y. Nakashima (UX), J. Lee, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 376
5.0.3.5 | Accessibility & WCAG compliance review | 3 | Group task | 2028-01-07 | 2028-01-18 | 8 | 0% | 5.0.3.4 | J. Lee | U. Marchetti, V. Okwuosa, W. Pham, X. Delgado | Customer UX / Design (8) | 320
5.0.3.6 | Usability testing & design iteration | 3 | Summary | 2028-01-19 | 2028-02-03 | 12 | 0%
5.0.3.6.1 | Usability test sessions | 4 | Group task | 2028-01-19 | 2028-01-26 | 6 | 0% | 5.0.3.5 | X. Delgado | Y. Nakashima (UX), J. Lee, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 225
5.0.3.6.2 | Design refinement from findings | 4 | Group task | 2028-01-27 | 2028-02-03 | 6 | 0% | 5.0.3.6.1 | J. Lee | U. Marchetti, V. Okwuosa, W. Pham, X. Delgado | Customer UX / Design (8) | 240
5.0.4 | Clinical / Business Policy Alignment | 2 | Summary | 2027-11-25 | 2028-01-13 | 36 | 0%
5.0.4.1 | Clinical policy & medical necessity criteria review | 3 | Group task | 2027-11-25 | 2027-12-08 | 10 | 0% |  | X. Delgado | Y. Nakashima (UX), J. Lee, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 376
5.0.4.2 | Decision-logic clinical validation | 3 | Group task | 2027-12-09 | 2027-12-22 | 10 | 0% | 5.0.4.1 | J. Lee | U. Marchetti, V. Okwuosa, W. Pham, X. Delgado | Customer UX / Design (8) | 400
5.0.4.3 | Provider & utilization-management impact review | 3 | Group task | 2027-12-23 | 2028-01-03 | 8 | 0% | 5.0.4.2 | X. Delgado | Y. Nakashima (UX), J. Lee, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 301
5.0.4.4 | Policy exception & appeals handling design | 3 | Task | 2028-01-04 | 2028-01-13 | 8 | 0% | 5.0.4.3 | J. Lee | U. Marchetti, V. Okwuosa |  | 192
5.0.5 | Data Engineering & Feature Prep | 2 | Summary | 2027-12-14 | 2028-03-07 | 61 | 0%
5.0.5.1 | Data profiling & quality assessment | 3 | Summary | 2027-12-14 | 2027-12-29 | 12 | 0%
5.0.5.1.1 | Legacy source profiling | 4 | Group task | 2027-12-14 | 2027-12-21 | 6 | 0% |  | Q. Halvorsen2 | R. Bianchi, S. Fitzgerald, T. Andersen, U. Kowalczyk2 | Data & Cloud AI Platform Foundation (20) | 240
5.0.5.1.2 | Data quality scorecard & remediation plan | 4 | Task | 2027-12-22 | 2027-12-29 | 6 | 0% | 5.0.5.1.1 | U. Kowalczyk2 | V. Delvecchio2 |  | 96
5.0.5.2 | Data ingestion & pipeline build | 3 | Summary | 2027-12-30 | 2028-01-19 | 15 | 0%
5.0.5.2.1 | Source connectors & ingestion | 4 | Group task | 2027-12-30 | 2028-01-07 | 7 | 0% | 5.0.5.1 | V. Delvecchio2 | W. Solberg2, X. Nakashima2, Y. Winfield2, Z. Achebe2 | Data & Cloud AI Platform Foundation (20) | 280
5.0.5.2.2 | Transformation & cleansing rules | 4 | Task | 2028-01-10 | 2028-01-19 | 8 | 0% | 5.0.5.2.1 | Z. Achebe2 | A. Larsen2 |  | 122
5.0.5.3 | Data remediation execution | 3 | Group task | 2028-01-20 | 2028-02-04 | 12 | 0% | 5.0.5.2 | W. Kumar | J. Restrepo, K. Vartan, A. Larsen2, B. Sorensen2 | Data & Cloud AI Platform Foundation (20) | 460
5.0.5.4 | Feature engineering & dataset assembly | 3 | Task | 2028-02-07 | 2028-02-22 | 12 | 0% | 5.0.5.3 | X. Garcia | D. Nakamura3, E. Okoro4 |  | 288
5.0.5.5 | Data privacy & PHI controls validation | 3 | Task | 2028-02-23 | 2028-03-01 | 6 | 0% | 5.0.5.4 | P. Sandoval | Q. Beckham |  | 81
5.0.5.6 | Training / test dataset governance sign-off | 3 | Task | 2028-03-02 | 2028-03-07 | 4 | 0% | 5.0.5.5 | D. Ibrahim | S. Khurana |  | 64
5.0.6 | Model Development & Training | 2 | Summary | 2027-12-31 | 2028-03-29 | 64 | 0%
5.0.6.1 | Baseline model build | 3 | Task | 2027-12-31 | 2028-01-20 | 15 | 0% |  | N. Larsen4 | O. Sorensen4, P. Kessler3 |  | 360
5.0.6.2 | Model training & iteration cycles | 3 | Summary | 2028-01-21 | 2028-02-21 | 22 | 0%
5.0.6.2.1 | Training run cycle 1 | 4 | Group task | 2028-01-21 | 2028-01-28 | 6 | 0% | 5.0.6.1 | P. Kessler3 | S. Whitby5, T. Okoro5, Q. Rutherford3, R. Alvarado3 | Member & Provider Experience AI (BRD-02) (22) | 225
5.0.6.2.2 | Evaluation & error analysis | 4 | Task | 2028-01-31 | 2028-02-04 | 5 | 0% | 5.0.6.2.1 | T. Okoro5 | U. Delacroix4 |  | 72
5.0.6.2.3 | Training run cycle 2 (tuned) | 4 | Group task | 2028-02-07 | 2028-02-14 | 6 | 0% | 5.0.6.2.2 | V. Vartan4 | X. Garcia, W. Halvorsen4, U. Delacroix4, Y. Nakamura4 | Member & Provider Experience AI (BRD-02) (22) | 211
5.0.6.2.4 | Training run cycle 3 (final) | 4 | Task | 2028-02-15 | 2028-02-21 | 5 | 0% | 5.0.6.2.3 | X. Garcia | D. Nakamura3 |  | 80
5.0.6.3 | Bias & fairness evaluation | 3 | Task | 2028-02-22 | 2028-03-02 | 8 | 0% | 5.0.6.2 | X. Garcia | D. Nakamura3 |  | 128
5.0.6.4 | Explainability & guardrail implementation | 3 | Task | 2028-03-03 | 2028-03-14 | 8 | 0% | 5.0.6.3 | D. Nakamura3 | E. Okoro4 |  | 128
5.0.6.5 | Model documentation & model card | 3 | Task | 2028-03-15 | 2028-03-22 | 6 | 0% | 5.0.6.4 | E. Okoro4 | F. Whitby4 |  | 96
5.0.6.6 | Model peer review (first line) | 3 | Task | 2028-03-23 | 2028-03-29 | 5 | 0% | 5.0.6.5 | F. Whitby4 | G. Beaumont3 |  | 80
5.0.7 | Iterative Build (Sprints) | 2 | Summary | 2028-01-19 | 2028-04-27 | 72 | 0%
5.0.7.1 | Sprint 1 — build & integrate | 3 | Summary | 2028-01-19 | 2028-01-31 | 9 | 0%
5.0.7.1.1 | Sprint 1 planning & backlog refinement | 4 | Task | 2028-01-19 | 2028-01-19 | 1 | 0% |  | G. Beaumont3 | H. Kowalczyk4 |  | 16
5.0.7.1.2 | Sprint 1 feature & model development | 4 | Group task | 2028-01-20 | 2028-01-26 | 5 | 0% | 5.0.7.1.1 | H. Kowalczyk4 | I. Delvecchio4, J. Solberg4, K. Nakashima4, L. Winfield4 | Member & Provider Experience AI (BRD-02) (22) | 200
5.0.7.1.3 | Sprint 1 code review & merge | 4 | Task | 2028-01-27 | 2028-01-28 | 2 | 0% | 5.0.7.1.2 | L. Winfield4 | M. Achebe4 |  | 32
5.0.7.1.4 | Sprint 1 demo, review & retrospective | 4 | Task | 2028-01-31 | 2028-01-31 | 1 | 0% | 5.0.7.1.3 | M. Achebe4 | N. Larsen4 |  | 16
5.0.7.2 | Sprint 2 — build & integrate | 3 | Summary | 2028-02-01 | 2028-02-11 | 9 | 0%
5.0.7.2.1 | Sprint 2 planning & backlog refinement | 4 | Task | 2028-02-01 | 2028-02-01 | 1 | 0% | 5.0.7.1 | N. Larsen4 | O. Sorensen4 |  | 16
5.0.7.2.2 | Sprint 2 feature & model development | 4 | Group task | 2028-02-02 | 2028-02-08 | 5 | 0% | 5.0.7.2.1 | O. Sorensen4 | P. Kessler3, S. Whitby5, Q. Rutherford3, R. Alvarado3 | Member & Provider Experience AI (BRD-02) (22) | 188
5.0.7.2.3 | Sprint 2 code review & merge | 4 | Task | 2028-02-09 | 2028-02-10 | 2 | 0% | 5.0.7.2.2 | S. Whitby5 | T. Okoro5 |  | 32
5.0.7.2.4 | Sprint 2 demo, review & retrospective | 4 | Task | 2028-02-11 | 2028-02-11 | 1 | 0% | 5.0.7.2.3 | T. Okoro5 | U. Delacroix4 |  | 14
5.0.7.3 | Sprint 3 — build & integrate | 3 | Summary | 2028-02-14 | 2028-02-24 | 9 | 0%
5.0.7.3.1 | Sprint 3 planning & backlog refinement | 4 | Task | 2028-02-14 | 2028-02-14 | 1 | 0% | 5.0.7.2 | V. Vartan4 | U. Delacroix4 |  | 14
5.0.7.3.2 | Sprint 3 feature & model development | 4 | Group task | 2028-02-15 | 2028-02-21 | 5 | 0% | 5.0.7.3.1 | V. Vartan4 | X. Garcia, D. Nakamura3, W. Halvorsen4, Y. Nakamura4 | Member & Provider Experience AI (BRD-02) (22) | 184
5.0.7.3.3 | Sprint 3 code review & merge | 4 | Task | 2028-02-22 | 2028-02-23 | 2 | 0% | 5.0.7.3.2 | D. Nakamura3 | E. Okoro4 |  | 32
5.0.7.3.4 | Sprint 3 demo, review & retrospective | 4 | Task | 2028-02-24 | 2028-02-24 | 1 | 0% | 5.0.7.3.3 | E. Okoro4 | F. Whitby4 |  | 16
5.0.7.4 | Sprint 4 — build & integrate | 3 | Summary | 2028-02-25 | 2028-03-08 | 9 | 0%
5.0.7.4.1 | Sprint 4 planning & backlog refinement | 4 | Task | 2028-02-25 | 2028-02-25 | 1 | 0% | 5.0.7.3 | F. Whitby4 | G. Beaumont3 |  | 16
5.0.7.4.2 | Sprint 4 feature & model development | 4 | Group task | 2028-02-28 | 2028-03-03 | 5 | 0% | 5.0.7.4.1 | G. Beaumont3 | H. Kowalczyk4, I. Delvecchio4, J. Solberg4, K. Nakashima4 | Member & Provider Experience AI (BRD-02) (22) | 200
5.0.7.4.3 | Sprint 4 code review & merge | 4 | Task | 2028-03-06 | 2028-03-07 | 2 | 0% | 5.0.7.4.2 | K. Nakashima4 | L. Winfield4 |  | 32
5.0.7.4.4 | Sprint 4 demo, review & retrospective | 4 | Task | 2028-03-08 | 2028-03-08 | 1 | 0% | 5.0.7.4.3 | L. Winfield4 | M. Achebe4 |  | 16
5.0.7.5 | Sprint 5 — build & integrate | 3 | Summary | 2028-03-09 | 2028-03-21 | 9 | 0%
5.0.7.5.1 | Sprint 5 planning & backlog refinement | 4 | Task | 2028-03-09 | 2028-03-09 | 1 | 0% | 5.0.7.4 | M. Achebe4 | N. Larsen4 |  | 16
5.0.7.5.2 | Sprint 5 feature & model development | 4 | Group task | 2028-03-10 | 2028-03-16 | 5 | 0% | 5.0.7.5.1 | N. Larsen4 | O. Sorensen4, P. Kessler3, Q. Rutherford3, R. Alvarado3 | Member & Provider Experience AI (BRD-02) (22) | 188
5.0.7.5.3 | Sprint 5 code review & merge | 4 | Task | 2028-03-17 | 2028-03-20 | 2 | 0% | 5.0.7.5.2 | S. Whitby5 | R. Alvarado3 |  | 29
5.0.7.5.4 | Sprint 5 demo, review & retrospective | 4 | Task | 2028-03-21 | 2028-03-21 | 1 | 0% | 5.0.7.5.3 | S. Whitby5 | T. Okoro5 |  | 16
5.0.7.6 | Sprint 6 — build & integrate | 3 | Summary | 2028-03-22 | 2028-04-03 | 9 | 0%
5.0.7.6.1 | Sprint 6 planning & backlog refinement | 4 | Task | 2028-03-22 | 2028-03-22 | 1 | 0% | 5.0.7.5 | T. Okoro5 | U. Delacroix4 |  | 14
5.0.7.6.2 | Sprint 6 feature & model development | 4 | Group task | 2028-03-23 | 2028-03-29 | 5 | 0% | 5.0.7.6.1 | V. Vartan4 | X. Garcia, W. Halvorsen4, U. Delacroix4, Y. Nakamura4 | Member & Provider Experience AI (BRD-02) (22) | 176
5.0.7.6.3 | Sprint 6 code review & merge | 4 | Task | 2028-03-30 | 2028-03-31 | 2 | 0% | 5.0.7.6.2 | X. Garcia | D. Nakamura3 |  | 32
5.0.7.6.4 | Sprint 6 demo, review & retrospective | 4 | Task | 2028-04-03 | 2028-04-03 | 1 | 0% | 5.0.7.6.3 | D. Nakamura3 | E. Okoro4 |  | 16
5.0.7.7 | Sprint 7 — build & integrate | 3 | Summary | 2028-04-04 | 2028-04-14 | 9 | 0%
5.0.7.7.1 | Sprint 7 planning & backlog refinement | 4 | Task | 2028-04-04 | 2028-04-04 | 1 | 0% | 5.0.7.6 | E. Okoro4 | F. Whitby4 |  | 16
5.0.7.7.2 | Sprint 7 feature & model development | 4 | Group task | 2028-04-05 | 2028-04-11 | 5 | 0% | 5.0.7.7.1 | F. Whitby4 | G. Beaumont3, H. Kowalczyk4, I. Delvecchio4, J. Solberg4 | Member & Provider Experience AI (BRD-02) (22) | 200
5.0.7.7.3 | Sprint 7 code review & merge | 4 | Task | 2028-04-12 | 2028-04-13 | 2 | 0% | 5.0.7.7.2 | J. Solberg4 | K. Nakashima4 |  | 32
5.0.7.7.4 | Sprint 7 demo, review & retrospective | 4 | Task | 2028-04-14 | 2028-04-14 | 1 | 0% | 5.0.7.7.3 | K. Nakashima4 | L. Winfield4 |  | 16
5.0.7.8 | Sprint 8 — build & integrate | 3 | Summary | 2028-04-17 | 2028-04-27 | 9 | 0%
5.0.7.8.1 | Sprint 8 planning & backlog refinement | 4 | Task | 2028-04-17 | 2028-04-17 | 1 | 0% | 5.0.7.7 | L. Winfield4 | M. Achebe4 |  | 16
5.0.7.8.2 | Sprint 8 feature & model development | 4 | Group task | 2028-04-18 | 2028-04-24 | 5 | 0% | 5.0.7.8.1 | M. Achebe4 | N. Larsen4, O. Sorensen4, P. Kessler3, Q. Rutherford3 | Member & Provider Experience AI (BRD-02) (22) | 196
5.0.7.8.3 | Sprint 8 code review & merge | 4 | Task | 2028-04-25 | 2028-04-26 | 2 | 0% | 5.0.7.8.2 | Q. Rutherford3 | R. Alvarado3 |  | 27
5.0.7.8.4 | Sprint 8 demo, review & retrospective | 4 | Task | 2028-04-27 | 2028-04-27 | 1 | 0% | 5.0.7.8.3 | S. Whitby5 | R. Alvarado3 |  | 14
5.0.8 | Integration & Environment Build | 2 | Summary | 2028-02-07 | 2028-04-04 | 42 | 0%
5.0.8.1 | Application & workflow integration | 3 | Summary | 2028-02-07 | 2028-03-03 | 20 | 0%
5.0.8.1.1 | API & service integration | 4 | Group task | 2028-02-07 | 2028-02-16 | 8 | 0% |  | S. Whitby5 | T. Okoro5, V. Vartan4, W. Halvorsen4, U. Delacroix4 | Member & Provider Experience AI (BRD-02) (22) | 301
5.0.8.1.2 | Human-in-the-loop review workflow | 4 | Task | 2028-02-17 | 2028-02-24 | 6 | 0% | 5.0.8.1.1 | W. Halvorsen4 | Y. Nakamura4 |  | 77
5.0.8.1.3 | Channel / UI integration | 4 | Task | 2028-02-25 | 2028-03-03 | 6 | 0% | 5.0.8.1.2 | J. Lee | U. Marchetti |  | 96
5.0.8.2 | MLOps deployment pipeline setup | 3 | Task | 2028-03-06 | 2028-03-17 | 10 | 0% | 5.0.8.1 | K. Vartan | L. Sondheim |  | 160
5.0.8.3 | Environment build & configuration | 3 | Group task | 2028-03-20 | 2028-03-27 | 6 | 0% | 5.0.8.2 | B. Fairweather | C. Sondheim, D. Marchetti, E. Whitcomb, F. Talbot | IT Operations / Infrastructure (10) | 240
5.0.8.4 | Integration smoke test & stabilization | 3 | Task | 2028-03-28 | 2028-04-04 | 6 | 0% | 5.0.8.3 | X. Garcia | Y. Nakamura4 |  | 82
5.0.9 | Testing & QA | 2 | Summary | 2028-02-24 | 2028-07-03 | 93 | 0%
5.0.9.1 | Test strategy & plan | 3 | Task | 2028-02-24 | 2028-03-02 | 6 | 0% |  | K. Garcia | L. Thompson |  | 96
5.0.9.2 | Test case authoring & data setup | 3 | Group task | 2028-03-03 | 2028-03-16 | 10 | 0% | 5.0.9.1 | L. Thompson | M. Washington (QA), N. Ferraro, O. Delacroix, P. Vartan | QA & Testing (18) | 400
5.0.9.3 | Unit & component testing | 3 | Group task | 2028-03-17 | 2028-03-30 | 10 | 0% | 5.0.9.2 | P. Vartan | Q. Halvorsen, R. Nakamura, S. Okoro, T. Whitby | QA & Testing (18) | 400
5.0.9.4 | Integration testing | 3 | Group task | 2028-03-31 | 2028-04-17 | 12 | 0% | 5.0.9.3 | T. Whitby | U. Beaumont, V. Kowalczyk, W. Delvecchio, X. Solberg | QA & Testing (18) | 480
5.0.9.5 | System & end-to-end testing | 3 | Summary | 2028-04-18 | 2028-05-03 | 12 | 0%
5.0.9.5.1 | Functional E2E scenarios | 4 | Group task | 2028-04-18 | 2028-04-25 | 6 | 0% | 5.0.9.4 | X. Solberg | Y. Nakashima (QA), V. Müller, J. Bennett, Z. Winfield (QA) | QA & Testing (18) | 235
5.0.9.5.2 | Negative & edge-case testing | 4 | Task | 2028-04-26 | 2028-05-03 | 6 | 0% | 5.0.9.5.1 | J. Bennett | K. Garcia |  | 96
5.0.9.6 | Model performance & regression testing | 3 | Task | 2028-05-04 | 2028-05-17 | 10 | 0% | 5.0.9.5 | V. Müller | J. Bennett, K. Garcia |  | 240
5.0.9.7 | Security & penetration testing | 3 | Group task | 2028-05-18 | 2028-05-29 | 8 | 0% | 5.0.9.6 | N. Winthrop | O. Castillo, P. Halstead, V. Redmond, M. Hassan | Cybersecurity / InfoSec (10) | 256
5.0.9.8 | Performance & load testing | 3 | Task | 2028-05-30 | 2028-06-08 | 8 | 0% | 5.0.9.7 | K. Garcia | L. Thompson |  | 128
5.0.9.9 | Defect triage & resolution cycles | 3 | Group task | 2028-06-09 | 2028-06-26 | 12 | 0% | 5.0.9.8 | K. Garcia | L. Thompson, M. Washington (QA), N. Ferraro, O. Delacroix | QA & Testing (18) + Member & Provider Experience AI (BRD-02) (22) | 480
5.0.9.10 | Test summary & exit report | 3 | Task | 2028-06-27 | 2028-07-03 | 5 | 0% | 5.0.9.9 | L. Thompson | M. Washington (QA) |  | 80
5.0.10 | Independent Model Validation | 2 | Summary | 2028-03-14 | 2028-04-19 | 27 | 0%
5.0.10.1 | IMV submission & documentation review | 3 | Task | 2028-03-14 | 2028-03-21 | 6 | 0% |  | Z. Winfield (IMV) | A. Kessler |  | 91
5.0.10.2 | Independent performance & fairness validation | 3 | Summary | 2028-03-22 | 2028-04-04 | 10 | 0%
5.0.10.2.1 | Independent replication testing | 4 | Task | 2028-03-22 | 2028-03-28 | 5 | 0% | 5.0.10.1 | P. Okafor | A. Kessler |  | 76
5.0.10.2.2 | Fairness & bias re-testing | 4 | Task | 2028-03-29 | 2028-04-04 | 5 | 0% | 5.0.10.2.1 | P. Okafor | W. Achebe |  | 80
5.0.10.3 | Validation findings & remediation | 3 | Task | 2028-04-05 | 2028-04-14 | 8 | 0% | 5.0.10.2 | P. Okafor | W. Achebe, X. Sorensen |  | 192
5.0.10.4 | IMV sign-off (production gate) | 3 | Task | 2028-04-17 | 2028-04-19 | 3 | 0% | 5.0.10.3 | W. Achebe | X. Sorensen |  | 48
5.0.11 | Compliance, Clinical & Controls Review | 2 | Summary | 2028-03-31 | 2028-05-24 | 39 | 0%
5.0.11.1 | Legal review (liability, disclaimers, contracts) | 3 | Group task | 2028-03-31 | 2028-04-07 | 6 | 0% |  | N. Harris | K. Okonkwo, M. Bernstein, S. Patel, R. Thorne | Legal (6) | 197
5.0.11.2 | Compliance & regulatory review | 3 | Group task | 2028-04-10 | 2028-04-19 | 8 | 0% | 5.0.11.1 | T. Jackson | L. Huang, R. Kimani, U. Kowalski, J. Martinez | Compliance (7) | 256
5.0.11.3 | Clinical / medical-policy review | 3 | Group task | 2028-04-20 | 2028-04-28 | 7 | 0% | 5.0.11.2 | U. Marchetti | V. Okwuosa, W. Pham, X. Delgado, Y. Nakashima (UX) | Customer UX / Design (8) | 280
5.0.11.4 | SOX / financial-controls testing | 3 | Group task | 2028-05-01 | 2028-05-08 | 6 | 0% | 5.0.11.3 | P. Whitcomb | M. Osei, N. Brennan, Q. Marchetti, K. Williams | SOX / Financial Controls (6) | 194
5.0.11.5 | Data privacy audit & DPIA | 3 | Task | 2028-05-09 | 2028-05-16 | 6 | 0% | 5.0.11.4 | Q. Beckham | E. Sato |  | 57
5.0.11.6 | Cybersecurity controls assurance | 3 | Task | 2028-05-17 | 2028-05-24 | 6 | 0% | 5.0.11.5 | P. Halstead | Q. Beaumont |  | 96
5.0.12 | User Acceptance Testing | 2 | Summary | 2028-04-19 | 2028-06-26 | 49 | 0%
5.0.12.1 | UAT planning & environment readiness | 3 | Group task | 2028-04-19 | 2028-04-26 | 6 | 0% |  | B. Alvarado5 | C. Whitby8, D. Okoro8, E. Beaumont6, F. Kowalczyk7 | User Acceptance Testing (UAT) (11) | 120
5.0.12.2 | UAT test scenario authoring | 3 | Group task | 2028-04-27 | 2028-05-08 | 8 | 0% | 5.0.12.1 | Y. Sorensen6 | H. Solberg7, I. Nakashima7, F. Kowalczyk7, G. Delvecchio7 | User Acceptance Testing (UAT) (11) | 224
5.0.12.3 | UAT execution cycles | 3 | Summary | 2028-05-09 | 2028-06-05 | 20 | 0%
5.0.12.3.1 | UAT cycle 1 | 4 | Group task | 2028-05-09 | 2028-05-16 | 6 | 0% | 5.0.12.2 | Y. Sorensen6 | Z. Kessler5, A. Rutherford5, B. Alvarado5, C. Whitby8 | User Acceptance Testing (UAT) (11) | 144
5.0.12.3.2 | UAT defect fixes & retest | 4 | Group task | 2028-05-17 | 2028-05-23 | 5 | 0% | 5.0.12.3.1 | C. Whitby8 | D. Okoro8, E. Beaumont6, F. Kowalczyk7, G. Delvecchio7 | User Acceptance Testing (UAT) (11) | 100
5.0.12.3.3 | UAT cycle 2 (regression) | 4 | Group task | 2028-05-24 | 2028-05-30 | 5 | 0% | 5.0.12.3.2 | Y. Sorensen6 | H. Solberg7, I. Nakashima7, G. Delvecchio7, Z. Kessler5 | User Acceptance Testing (UAT) (11) | 140
5.0.12.3.4 | Final UAT confirmation | 4 | Group task | 2028-05-31 | 2028-06-05 | 4 | 0% | 5.0.12.3.3 | Z. Kessler5 | A. Rutherford5, B. Alvarado5, C. Whitby8, D. Okoro8 | User Acceptance Testing (UAT) (11) | 80
5.0.12.4 | Business process & runbook validation | 3 | Group task | 2028-06-06 | 2028-06-13 | 6 | 0% | 5.0.12.3 | F. Talbot | G. Restrepo, H. Vartan, I. Halvorsen, H. Nakamura | IT Operations / Infrastructure (10) | 196
5.0.12.5 | Operational readiness assessment | 3 | Group task | 2028-06-14 | 2028-06-21 | 6 | 0% | 5.0.12.4 | Q. Beaumont5 | S. Delvecchio6, T. Solberg6, R. Kowalczyk6, U. Nakashima6 | Customer Service Operations (12) | 225
5.0.12.6 | UAT sign-off | 3 | Task | 2028-06-22 | 2028-06-26 | 3 | 0% | 5.0.12.5 | D. Okoro8 | E. Beaumont6 |  | 24
5.0.13 | Change Management & Adoption | 2 | Summary | 2028-05-08 | 2028-07-21 | 55 | 0%
5.0.13.1 | Change impact assessment & stakeholder analysis | 3 | Task | 2028-05-08 | 2028-05-16 | 7 | 0% |  | E. Winthrop | F. Achebe |  | 95
5.0.13.2 | Training material development | 3 | Summary | 2028-05-17 | 2028-05-30 | 10 | 0%
5.0.13.2.1 | End-user training curriculum | 4 | Task | 2028-05-17 | 2028-05-23 | 5 | 0% | 5.0.13.1 | F. Achebe | H. Kandel |  | 60
5.0.13.2.2 | Job aids & quick-reference | 4 | Task | 2028-05-24 | 2028-05-30 | 5 | 0% | 5.0.13.2.1 | I. Redmond | H. Kandel |  | 60
5.0.13.3 | Training delivery & enablement | 3 | Group task | 2028-05-31 | 2028-06-15 | 12 | 0% | 5.0.13.2 | G. Okonkwo | B. Prescott, C. Whitfield, D. Solis, I. Redmond | Change Management & Training (8) | 461
5.0.13.4 | Communications campaign | 3 | Group task | 2028-06-16 | 2028-06-27 | 8 | 0% | 5.0.13.3 | R. Castellanos | S. Halloway, T. Ainslie, B. Sullivan | Corporate Communications / PR (4) | 173
5.0.13.5 | Frontline readiness & super-user network | 3 | Group task | 2028-06-28 | 2028-07-07 | 8 | 0% | 5.0.13.4 | X. Larsen6 | U. Nakashima6, V. Winfield6, W. Achebe6, M. Washington (CustOps) | Customer Service Operations (12) | 224
5.0.13.6 | Adoption tracking & reinforcement | 3 | Task | 2028-07-10 | 2028-07-21 | 10 | 0% | 5.0.13.5 | D. Solis | E. Winthrop |  | 152
5.0.14 | Pilot Deployment | 2 | Summary | 2028-05-25 | 2028-07-19 | 40 | 0%
5.0.14.1 | Pilot readiness review & go/no-go | 3 | Task | 2028-05-25 | 2028-05-30 | 4 | 0% |  | X. Garcia | D. Nakamura3 |  | 64
5.0.14.2 | Controlled pilot rollout | 3 | Group task | 2028-05-31 | 2028-06-15 | 12 | 0% | 5.0.14.1 | D. Nakamura3 | E. Okoro4, F. Whitby4, G. Beaumont3, H. Kowalczyk4 | Member & Provider Experience AI (BRD-02) (22) | 480
5.0.14.3 | Pilot monitoring & tuning | 3 | Task | 2028-06-16 | 2028-06-29 | 10 | 0% | 5.0.14.2 | D. Nakamura3 | E. Okoro4, F. Whitby4 |  | 240
5.0.14.4 | Pilot support & issue resolution | 3 | Group task | 2028-06-30 | 2028-07-13 | 10 | 0% | 5.0.14.3 | N. Alvarado4 | O. Whitby7, P. Okoro7, Q. Beaumont5, M. Washington (CustOps) | Customer Service Operations (12) | 336
5.0.14.5 | Pilot evaluation & production decision | 3 | Task | 2028-07-14 | 2028-07-19 | 4 | 0% | 5.0.14.4 | H. Kowalczyk4 | I. Delvecchio4 |  | 64
5.0.15 | Production Deployment & Hypercare | 2 | Summary | 2028-06-13 | 2028-08-17 | 48 | 0%
5.0.15.1 | Production readiness review (3 boards) | 3 | Task | 2028-06-13 | 2028-06-19 | 5 | 0% |  | I. Delvecchio4 | J. Solberg4 |  | 80
5.0.15.2 | Production cutover & go-live | 3 | Group task | 2028-06-20 | 2028-06-27 | 6 | 0% | 5.0.15.1 | X. Garcia | D. Nakamura3, E. Okoro4, F. Whitby4, G. Beaumont3 | Member & Provider Experience AI (BRD-02) (22) + IT Operations / Infrastructure (10) | 240
5.0.15.3 | Hypercare & stabilization | 3 | Summary | 2028-06-28 | 2028-07-18 | 15 | 0%
5.0.15.3.1 | Hypercare monitoring | 4 | Group task | 2028-06-28 | 2028-07-07 | 8 | 0% | 5.0.15.2 | J. Solberg4 | K. Nakashima4, L. Winfield4, M. Achebe4, N. Larsen4 | Member & Provider Experience AI (BRD-02) (22) | 320
5.0.15.3.2 | Incident response & fixes | 4 | Group task | 2028-07-10 | 2028-07-18 | 7 | 0% | 5.0.15.3.1 | N. Larsen4 | O. Sorensen4, P. Kessler3, Q. Rutherford3, R. Alvarado3 | Member & Provider Experience AI (BRD-02) (22) | 263
5.0.15.4 | Post-go-live service desk support | 3 | Group task | 2028-07-19 | 2028-08-03 | 12 | 0% | 5.0.15.3 | Q. Beaumont5 | S. Delvecchio6, T. Solberg6, R. Kowalczyk6, U. Nakashima6 | Customer Service Operations (12) | 451
5.0.15.5 | Benefits baseline established | 3 | Task | 2028-08-04 | 2028-08-09 | 4 | 0% | 5.0.15.4 | X. Garcia | D. Nakamura3 |  | 64
5.0.15.6 | Transition to steady-state operations | 3 | Task | 2028-08-10 | 2028-08-17 | 6 | 0% | 5.0.15.5 | U. Nakashima6 | V. Winfield6 |  | 76
6.0 | BRD-03 · Underwriting & Risk AI | 1 | Summary | 2027-11-01 | 2028-10-25 | 258 | 0%
6.0.1 | Requirements & JAD | 2 | Summary | 2027-11-01 | 2028-01-24 | 61 | 0%
6.0.1.1 | Requirements elicitation workshops (JAD series) | 3 | Summary | 2027-11-01 | 2027-11-23 | 17 | 0%
6.0.1.1.1 | Current-state process mapping | 4 | Task | 2027-11-01 | 2027-11-08 | 6 | 0% |  | Z. Thompson | A. Okoro6 |  | 96
6.0.1.1.2 | Use-case & user-story definition | 4 | Group task | 2027-11-09 | 2027-11-16 | 6 | 0% | 6.0.1.1.1 | A. Okoro6 | B. Whitby6, C. Beaumont4, D. Kowalczyk5, E. Delvecchio5 | Underwriting & Risk AI (BRD-03) (14) | 240
6.0.1.1.3 | Non-functional & compliance requirements | 4 | Task | 2027-11-17 | 2027-11-23 | 5 | 0% | 6.0.1.1.2 | Z. Thompson | A. Okoro6 |  | 80
6.0.1.2 | Data & source-system requirements | 3 | Summary | 2027-11-24 | 2027-12-03 | 8 | 0%
6.0.1.2.1 | Source-system inventory | 4 | Task | 2027-11-24 | 2027-11-29 | 4 | 0% | 6.0.1.1 | L. Sondheim | M. Marchetti |  | 64
6.0.1.2.2 | Data availability & quality requirements | 4 | Task | 2027-11-30 | 2027-12-03 | 4 | 0% | 6.0.1.2.1 | M. Marchetti | N. Whitcomb |  | 64
6.0.1.3 | Model & decision-logic requirements | 3 | Task | 2027-12-06 | 2027-12-15 | 8 | 0% | 6.0.1.2 | E. Delvecchio5 | F. Solberg5 |  | 128
6.0.1.4 | Business rules & policy catalogue | 3 | Task | 2027-12-16 | 2027-12-24 | 7 | 0% | 6.0.1.3 | Z. Thompson | A. Okoro6 |  | 112
6.0.1.5 | Clinical / actuarial SME requirements review | 3 | Group task | 2027-12-27 | 2028-01-03 | 6 | 0% | 6.0.1.4 | K. Okoro | L. Delacroix, Dr. J. Whitby, M. Beaumont, Dr. N. Patel | Clinical / Medical Policy & Informatics (6) | 179
6.0.1.6 | Requirements traceability matrix baseline | 3 | Task | 2028-01-04 | 2028-01-10 | 5 | 0% | 6.0.1.5 | F. Solberg5 | G. Nakashima5 |  | 80
6.0.1.7 | Requirements review & BRD authoring | 3 | Task | 2028-01-11 | 2028-01-19 | 7 | 0% | 6.0.1.6 | G. Nakashima5 | H. Winfield5 |  | 112
6.0.1.8 | BRD sign-off (JAD close, AI Governance Board) | 3 | Task | 2028-01-20 | 2028-01-24 | 3 | 0% | 6.0.1.7 | H. Winfield5 | I. Achebe5 |  | 48
6.0.2 | Architecture & Design | 2 | Summary | 2027-11-22 | 2028-02-08 | 57 | 0%
6.0.2.1 | Solution architecture & integration design | 3 | Summary | 2027-11-22 | 2027-12-07 | 12 | 0%
6.0.2.1.1 | Target-state architecture | 4 | Task | 2027-11-22 | 2027-11-29 | 6 | 0% |  | L. Fitzgerald | K. Andersen |  | 86
6.0.2.1.2 | Integration & API design | 4 | Task | 2027-11-30 | 2027-12-07 | 6 | 0% | 6.0.2.1.1 | L. Fitzgerald | D. Chen |  | 60
6.0.2.2 | Data architecture & pipeline design | 3 | Task | 2027-12-08 | 2027-12-21 | 10 | 0% | 6.0.2.1 | N. Whitcomb | O. Talbot |  | 160
6.0.2.3 | Model design & approach selection | 3 | Summary | 2027-12-22 | 2028-01-04 | 10 | 0%
6.0.2.3.1 | Model approach evaluation | 4 | Task | 2027-12-22 | 2027-12-28 | 5 | 0% | 6.0.2.2 | I. Achebe5 | J. Larsen5 |  | 80
6.0.2.3.2 | Model design specification | 4 | Task | 2027-12-29 | 2028-01-04 | 5 | 0% | 6.0.2.3.1 | J. Larsen5 | K. Sorensen5 |  | 80
6.0.2.4 | Security threat model & controls design | 3 | Group task | 2028-01-05 | 2028-01-14 | 8 | 0% | 6.0.2.3 | Q. Beaumont | R. Fontaine, S. Vasquez, T. Delvecchio, U. Kandel | Cybersecurity / InfoSec (10) | 314
6.0.2.5 | Privacy-by-design & PHI data-flow review | 3 | Task | 2028-01-17 | 2028-01-24 | 6 | 0% | 6.0.2.4 | N. Achterberg | E. Sato |  | 67
6.0.2.6 | Infrastructure & environment design | 3 | Task | 2028-01-25 | 2028-02-02 | 7 | 0% | 6.0.2.5 | A. Prescott | H. Nakamura |  | 73
6.0.2.7 | Design review & EARB approval | 3 | Task | 2028-02-03 | 2028-02-08 | 4 | 0% | 6.0.2.6 | F. Okonkwo | D. Chen |  | 40
6.0.3 | Experience & Interaction Design | 2 | Summary | 2027-12-13 | 2028-03-09 | 64 | 0%
6.0.3.1 | User research & journey mapping | 3 | Group task | 2027-12-13 | 2027-12-24 | 10 | 0% |  | Y. Nakashima (UX) | J. Lee, U. Marchetti, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 376
6.0.3.2 | Information architecture & wireframes | 3 | Group task | 2027-12-27 | 2028-01-11 | 12 | 0% | 6.0.3.1 | U. Marchetti | V. Okwuosa, W. Pham, X. Delgado, Y. Nakashima (UX) | Customer UX / Design (8) | 480
6.0.3.3 | Design system & component library | 3 | Group task | 2028-01-12 | 2028-01-27 | 12 | 0% | 6.0.3.2 | Y. Nakashima (UX) | J. Lee, U. Marchetti, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 451
6.0.3.4 | Conversational / interaction design | 3 | Group task | 2028-01-28 | 2028-02-10 | 10 | 0% | 6.0.3.3 | U. Marchetti | V. Okwuosa, W. Pham, X. Delgado, Y. Nakashima (UX) | Customer UX / Design (8) | 400
6.0.3.5 | Accessibility & WCAG compliance review | 3 | Group task | 2028-02-11 | 2028-02-22 | 8 | 0% | 6.0.3.4 | Y. Nakashima (UX) | J. Lee, U. Marchetti, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 301
6.0.3.6 | Usability testing & design iteration | 3 | Summary | 2028-02-23 | 2028-03-09 | 12 | 0%
6.0.3.6.1 | Usability test sessions | 4 | Group task | 2028-02-23 | 2028-03-01 | 6 | 0% | 6.0.3.5 | U. Marchetti | V. Okwuosa, W. Pham, X. Delgado, Y. Nakashima (UX) | Customer UX / Design (8) | 240
6.0.3.6.2 | Design refinement from findings | 4 | Group task | 2028-03-02 | 2028-03-09 | 6 | 0% | 6.0.3.6.1 | Y. Nakashima (UX) | J. Lee, U. Marchetti, Z. Fairbanks, A. Castillo | Customer UX / Design (8) | 225
6.0.4 | Clinical / Business Policy Alignment | 2 | Summary | 2028-01-03 | 2028-02-21 | 36 | 0%
6.0.4.1 | Clinical policy & medical necessity criteria review | 3 | Group task | 2028-01-03 | 2028-01-14 | 10 | 0% |  | K. Okoro | L. Delacroix, Dr. J. Whitby, Dr. I. Alvarado, Dr. N. Patel | Clinical / Medical Policy & Informatics (6) | 276
6.0.4.2 | Decision-logic clinical validation | 3 | Group task | 2028-01-17 | 2028-01-28 | 10 | 0% | 6.0.4.1 | L. Delacroix | M. Beaumont, Dr. J. Whitby, Dr. I. Alvarado, Dr. N. Patel | Clinical / Medical Policy & Informatics (6) | 260
6.0.4.3 | Provider & utilization-management impact review | 3 | Group task | 2028-01-31 | 2028-02-09 | 8 | 0% | 6.0.4.2 | K. Okoro | L. Delacroix, Dr. J. Whitby, M. Beaumont, Dr. N. Patel | Clinical / Medical Policy & Informatics (6) | 240
6.0.4.4 | Policy exception & appeals handling design | 3 | Task | 2028-02-10 | 2028-02-21 | 8 | 0% | 6.0.4.3 | K. Okoro | L. Delacroix, Dr. J. Whitby |  | 173
6.0.5 | Data Engineering & Feature Prep | 2 | Summary | 2028-01-24 | 2028-04-17 | 61 | 0%
6.0.5.1 | Data profiling & quality assessment | 3 | Summary | 2028-01-24 | 2028-02-08 | 12 | 0%
6.0.5.1.1 | Legacy source profiling | 4 | Group task | 2028-01-24 | 2028-01-31 | 6 | 0% |  | O. Talbot | P. Restrepo2, Q. Halvorsen2, R. Bianchi, S. Fitzgerald | Data & Cloud AI Platform Foundation (20) | 240
6.0.5.1.2 | Data quality scorecard & remediation plan | 4 | Task | 2028-02-01 | 2028-02-08 | 6 | 0% | 6.0.5.1.1 | S. Fitzgerald | T. Andersen |  | 96
6.0.5.2 | Data ingestion & pipeline build | 3 | Summary | 2028-02-09 | 2028-02-29 | 15 | 0%
6.0.5.2.1 | Source connectors & ingestion | 4 | Group task | 2028-02-09 | 2028-02-17 | 7 | 0% | 6.0.5.1 | T. Andersen | U. Kowalczyk2, V. Delvecchio2, W. Solberg2, X. Nakashima2 | Data & Cloud AI Platform Foundation (20) | 280
6.0.5.2.2 | Transformation & cleansing rules | 4 | Task | 2028-02-18 | 2028-02-29 | 8 | 0% | 6.0.5.2.1 | X. Nakashima2 | Y. Winfield2 |  | 128
6.0.5.3 | Data remediation execution | 3 | Group task | 2028-03-01 | 2028-03-16 | 12 | 0% | 6.0.5.2 | Y. Winfield2 | Z. Achebe2, W. Kumar, A. Larsen2, B. Sorensen2 | Data & Cloud AI Platform Foundation (20) | 460
6.0.5.4 | Feature engineering & dataset assembly | 3 | Task | 2028-03-17 | 2028-04-03 | 12 | 0% | 6.0.5.3 | Z. Thompson | A. Okoro6, B. Whitby6 |  | 288
6.0.5.5 | Data privacy & PHI controls validation | 3 | Task | 2028-04-04 | 2028-04-11 | 6 | 0% | 6.0.5.4 | N. Achterberg | O. Whitlock |  | 96
6.0.5.6 | Training / test dataset governance sign-off | 3 | Task | 2028-04-12 | 2028-04-17 | 4 | 0% | 6.0.5.5 | S. Khurana | A. Reyes |  | 64
6.0.6 | Model Development & Training | 2 | Summary | 2028-02-14 | 2028-05-11 | 64 | 0%
6.0.6.1 | Baseline model build | 3 | Task | 2028-02-14 | 2028-03-03 | 15 | 0% |  | K. Sorensen5 | L. Kessler4, M. Rutherford4 |  | 360
6.0.6.2 | Model training & iteration cycles | 3 | Summary | 2028-03-06 | 2028-04-04 | 22 | 0%
6.0.6.2.1 | Training run cycle 1 | 4 | Group task | 2028-03-06 | 2028-03-13 | 6 | 0% | 6.0.6.1 | M. Rutherford4 | Z. Thompson, A. Okoro6, B. Whitby6, C. Beaumont4 | Underwriting & Risk AI (BRD-03) (14) | 240
6.0.6.2.2 | Evaluation & error analysis | 4 | Task | 2028-03-14 | 2028-03-20 | 5 | 0% | 6.0.6.2.1 | C. Beaumont4 | D. Kowalczyk5 |  | 80
6.0.6.2.3 | Training run cycle 2 (tuned) | 4 | Group task | 2028-03-21 | 2028-03-28 | 6 | 0% | 6.0.6.2.2 | D. Kowalczyk5 | E. Delvecchio5, F. Solberg5, G. Nakashima5, H. Winfield5 | Underwriting & Risk AI (BRD-03) (14) | 240
6.0.6.2.4 | Training run cycle 3 (final) | 4 | Task | 2028-03-29 | 2028-04-04 | 5 | 0% | 6.0.6.2.3 | H. Winfield5 | I. Achebe5 |  | 80
6.0.6.3 | Bias & fairness evaluation | 3 | Task | 2028-04-05 | 2028-04-14 | 8 | 0% | 6.0.6.2 | Z. Thompson | A. Okoro6 |  | 128
6.0.6.4 | Explainability & guardrail implementation | 3 | Task | 2028-04-17 | 2028-04-26 | 8 | 0% | 6.0.6.3 | I. Achebe5 | J. Larsen5 |  | 128
6.0.6.5 | Model documentation & model card | 3 | Task | 2028-04-27 | 2028-05-04 | 6 | 0% | 6.0.6.4 | J. Larsen5 | K. Sorensen5 |  | 96
6.0.6.6 | Model peer review (first line) | 3 | Task | 2028-05-05 | 2028-05-11 | 5 | 0% | 6.0.6.5 | K. Sorensen5 | L. Kessler4 |  | 80
6.0.7 | Iterative Build (Sprints) | 2 | Summary | 2028-03-06 | 2028-06-13 | 72 | 0%
6.0.7.1 | Sprint 1 — build & integrate | 3 | Summary | 2028-03-06 | 2028-03-16 | 9 | 0%
6.0.7.1.1 | Sprint 1 planning & backlog refinement | 4 | Task | 2028-03-06 | 2028-03-06 | 1 | 0% |  | L. Kessler4 | M. Rutherford4 |  | 16
6.0.7.1.2 | Sprint 1 feature & model development | 4 | Group task | 2028-03-07 | 2028-03-13 | 5 | 0% | 6.0.7.1.1 | M. Rutherford4 | Z. Thompson, A. Okoro6, B. Whitby6, C. Beaumont4 | Underwriting & Risk AI (BRD-03) (14) | 200
6.0.7.1.3 | Sprint 1 code review & merge | 4 | Task | 2028-03-14 | 2028-03-15 | 2 | 0% | 6.0.7.1.2 | C. Beaumont4 | D. Kowalczyk5 |  | 32
6.0.7.1.4 | Sprint 1 demo, review & retrospective | 4 | Task | 2028-03-16 | 2028-03-16 | 1 | 0% | 6.0.7.1.3 | D. Kowalczyk5 | E. Delvecchio5 |  | 16
6.0.7.2 | Sprint 2 — build & integrate | 3 | Summary | 2028-03-17 | 2028-03-29 | 9 | 0%
6.0.7.2.1 | Sprint 2 planning & backlog refinement | 4 | Task | 2028-03-17 | 2028-03-17 | 1 | 0% | 6.0.7.1 | E. Delvecchio5 | F. Solberg5 |  | 16
6.0.7.2.2 | Sprint 2 feature & model development | 4 | Group task | 2028-03-20 | 2028-03-24 | 5 | 0% | 6.0.7.2.1 | F. Solberg5 | G. Nakashima5, H. Winfield5, I. Achebe5, J. Larsen5 | Underwriting & Risk AI (BRD-03) (14) | 200
6.0.7.2.3 | Sprint 2 code review & merge | 4 | Task | 2028-03-27 | 2028-03-28 | 2 | 0% | 6.0.7.2.2 | J. Larsen5 | K. Sorensen5 |  | 32
6.0.7.2.4 | Sprint 2 demo, review & retrospective | 4 | Task | 2028-03-29 | 2028-03-29 | 1 | 0% | 6.0.7.2.3 | K. Sorensen5 | L. Kessler4 |  | 16
6.0.7.3 | Sprint 3 — build & integrate | 3 | Summary | 2028-03-30 | 2028-04-11 | 9 | 0%
6.0.7.3.1 | Sprint 3 planning & backlog refinement | 4 | Task | 2028-03-30 | 2028-03-30 | 1 | 0% | 6.0.7.2 | L. Kessler4 | M. Rutherford4 |  | 16
6.0.7.3.2 | Sprint 3 feature & model development | 4 | Group task | 2028-03-31 | 2028-04-06 | 5 | 0% | 6.0.7.3.1 | M. Rutherford4 | Z. Thompson, A. Okoro6, B. Whitby6, C. Beaumont4 | Underwriting & Risk AI (BRD-03) (14) | 200
6.0.7.3.3 | Sprint 3 code review & merge | 4 | Task | 2028-04-07 | 2028-04-10 | 2 | 0% | 6.0.7.3.2 | C. Beaumont4 | D. Kowalczyk5 |  | 32
6.0.7.3.4 | Sprint 3 demo, review & retrospective | 4 | Task | 2028-04-11 | 2028-04-11 | 1 | 0% | 6.0.7.3.3 | D. Kowalczyk5 | E. Delvecchio5 |  | 16
6.0.7.4 | Sprint 4 — build & integrate | 3 | Summary | 2028-04-12 | 2028-04-24 | 9 | 0%
6.0.7.4.1 | Sprint 4 planning & backlog refinement | 4 | Task | 2028-04-12 | 2028-04-12 | 1 | 0% | 6.0.7.3 | E. Delvecchio5 | F. Solberg5 |  | 16
6.0.7.4.2 | Sprint 4 feature & model development | 4 | Group task | 2028-04-13 | 2028-04-19 | 5 | 0% | 6.0.7.4.1 | F. Solberg5 | G. Nakashima5, H. Winfield5, I. Achebe5, J. Larsen5 | Underwriting & Risk AI (BRD-03) (14) | 200
6.0.7.4.3 | Sprint 4 code review & merge | 4 | Task | 2028-04-20 | 2028-04-21 | 2 | 0% | 6.0.7.4.2 | J. Larsen5 | K. Sorensen5 |  | 32
6.0.7.4.4 | Sprint 4 demo, review & retrospective | 4 | Task | 2028-04-24 | 2028-04-24 | 1 | 0% | 6.0.7.4.3 | K. Sorensen5 | L. Kessler4 |  | 16
6.0.7.5 | Sprint 5 — build & integrate | 3 | Summary | 2028-04-25 | 2028-05-05 | 9 | 0%
6.0.7.5.1 | Sprint 5 planning & backlog refinement | 4 | Task | 2028-04-25 | 2028-04-25 | 1 | 0% | 6.0.7.4 | L. Kessler4 | M. Rutherford4 |  | 16
6.0.7.5.2 | Sprint 5 feature & model development | 4 | Group task | 2028-04-26 | 2028-05-02 | 5 | 0% | 6.0.7.5.1 | M. Rutherford4 | Z. Thompson, A. Okoro6, B. Whitby6, C. Beaumont4 | Underwriting & Risk AI (BRD-03) (14) | 200
6.0.7.5.3 | Sprint 5 code review & merge | 4 | Task | 2028-05-03 | 2028-05-04 | 2 | 0% | 6.0.7.5.2 | C. Beaumont4 | D. Kowalczyk5 |  | 32
6.0.7.5.4 | Sprint 5 demo, review & retrospective | 4 | Task | 2028-05-05 | 2028-05-05 | 1 | 0% | 6.0.7.5.3 | D. Kowalczyk5 | E. Delvecchio5 |  | 16
6.0.7.6 | Sprint 6 — build & integrate | 3 | Summary | 2028-05-08 | 2028-05-18 | 9 | 0%
6.0.7.6.1 | Sprint 6 planning & backlog refinement | 4 | Task | 2028-05-08 | 2028-05-08 | 1 | 0% | 6.0.7.5 | E. Delvecchio5 | F. Solberg5 |  | 16
6.0.7.6.2 | Sprint 6 feature & model development | 4 | Group task | 2028-05-09 | 2028-05-15 | 5 | 0% | 6.0.7.6.1 | F. Solberg5 | G. Nakashima5, H. Winfield5, I. Achebe5, J. Larsen5 | Underwriting & Risk AI (BRD-03) (14) | 200
6.0.7.6.3 | Sprint 6 code review & merge | 4 | Task | 2028-05-16 | 2028-05-17 | 2 | 0% | 6.0.7.6.2 | J. Larsen5 | K. Sorensen5 |  | 32
6.0.7.6.4 | Sprint 6 demo, review & retrospective | 4 | Task | 2028-05-18 | 2028-05-18 | 1 | 0% | 6.0.7.6.3 | K. Sorensen5 | L. Kessler4 |  | 16
6.0.7.7 | Sprint 7 — build & integrate | 3 | Summary | 2028-05-19 | 2028-05-31 | 9 | 0%
6.0.7.7.1 | Sprint 7 planning & backlog refinement | 4 | Task | 2028-05-19 | 2028-05-19 | 1 | 0% | 6.0.7.6 | L. Kessler4 | M. Rutherford4 |  | 16
6.0.7.7.2 | Sprint 7 feature & model development | 4 | Group task | 2028-05-22 | 2028-05-26 | 5 | 0% | 6.0.7.7.1 | M. Rutherford4 | Z. Thompson, A. Okoro6, B. Whitby6, C. Beaumont4 | Underwriting & Risk AI (BRD-03) (14) | 200
6.0.7.7.3 | Sprint 7 code review & merge | 4 | Task | 2028-05-29 | 2028-05-30 | 2 | 0% | 6.0.7.7.2 | C. Beaumont4 | D. Kowalczyk5 |  | 32
6.0.7.7.4 | Sprint 7 demo, review & retrospective | 4 | Task | 2028-05-31 | 2028-05-31 | 1 | 0% | 6.0.7.7.3 | D. Kowalczyk5 | E. Delvecchio5 |  | 16
6.0.7.8 | Sprint 8 — build & integrate | 3 | Summary | 2028-06-01 | 2028-06-13 | 9 | 0%
6.0.7.8.1 | Sprint 8 planning & backlog refinement | 4 | Task | 2028-06-01 | 2028-06-01 | 1 | 0% | 6.0.7.7 | E. Delvecchio5 | F. Solberg5 |  | 16
6.0.7.8.2 | Sprint 8 feature & model development | 4 | Group task | 2028-06-02 | 2028-06-08 | 5 | 0% | 6.0.7.8.1 | F. Solberg5 | G. Nakashima5, H. Winfield5, I. Achebe5, J. Larsen5 | Underwriting & Risk AI (BRD-03) (14) | 200
6.0.7.8.3 | Sprint 8 code review & merge | 4 | Task | 2028-06-09 | 2028-06-12 | 2 | 0% | 6.0.7.8.2 | J. Larsen5 | K. Sorensen5 |  | 32
6.0.7.8.4 | Sprint 8 demo, review & retrospective | 4 | Task | 2028-06-13 | 2028-06-13 | 1 | 0% | 6.0.7.8.3 | K. Sorensen5 | L. Kessler4 |  | 16
6.0.8 | Integration & Environment Build | 2 | Summary | 2028-03-27 | 2028-05-23 | 42 | 0%
6.0.8.1 | Application & workflow integration | 3 | Summary | 2028-03-27 | 2028-04-21 | 20 | 0%
6.0.8.1.1 | API & service integration | 4 | Group task | 2028-03-27 | 2028-04-05 | 8 | 0% |  | L. Kessler4 | M. Rutherford4, Z. Thompson, A. Okoro6, B. Whitby6 | Underwriting & Risk AI (BRD-03) (14) | 320
6.0.8.1.2 | Human-in-the-loop review workflow | 4 | Task | 2028-04-06 | 2028-04-13 | 6 | 0% | 6.0.8.1.1 | B. Whitby6 | C. Beaumont4 |  | 96
6.0.8.1.3 | Channel / UI integration | 4 | Task | 2028-04-14 | 2028-04-21 | 6 | 0% | 6.0.8.1.2 | C. Beaumont4 | D. Kowalczyk5 |  | 96
6.0.8.2 | MLOps deployment pipeline setup | 3 | Task | 2028-04-24 | 2028-05-05 | 10 | 0% | 6.0.8.1 | W. Kumar | J. Restrepo |  | 160
6.0.8.3 | Environment build & configuration | 3 | Group task | 2028-05-08 | 2028-05-15 | 6 | 0% | 6.0.8.2 | A. Prescott | B. Fairweather, C. Sondheim, D. Marchetti, E. Whitcomb | IT Operations / Infrastructure (10) | 240
6.0.8.4 | Integration smoke test & stabilization | 3 | Task | 2028-05-16 | 2028-05-23 | 6 | 0% | 6.0.8.3 | D. Kowalczyk5 | E. Delvecchio5 |  | 96
6.0.9 | Testing & QA | 2 | Summary | 2028-04-17 | 2028-08-23 | 93 | 0%
6.0.9.1 | Test strategy & plan | 3 | Task | 2028-04-17 | 2028-04-24 | 6 | 0% |  | M. Washington (QA) | N. Ferraro |  | 96
6.0.9.2 | Test case authoring & data setup | 3 | Group task | 2028-04-25 | 2028-05-08 | 10 | 0% | 6.0.9.1 | N. Ferraro | O. Delacroix, P. Vartan, Q. Halvorsen, R. Nakamura | QA & Testing (18) | 400
6.0.9.3 | Unit & component testing | 3 | Group task | 2028-05-09 | 2028-05-22 | 10 | 0% | 6.0.9.2 | R. Nakamura | S. Okoro, T. Whitby, U. Beaumont, V. Kowalczyk | QA & Testing (18) | 400
6.0.9.4 | Integration testing | 3 | Group task | 2028-05-23 | 2028-06-07 | 12 | 0% | 6.0.9.3 | V. Kowalczyk | W. Delvecchio, X. Solberg, Y. Nakashima (QA), Z. Winfield (QA) | QA & Testing (18) | 470
6.0.9.5 | System & end-to-end testing | 3 | Summary | 2028-06-08 | 2028-06-23 | 12 | 0%
6.0.9.5.1 | Functional E2E scenarios | 4 | Group task | 2028-06-08 | 2028-06-15 | 6 | 0% | 6.0.9.4 | V. Müller | J. Bennett, K. Garcia, L. Thompson, Z. Winfield (QA) | QA & Testing (18) | 235
6.0.9.5.2 | Negative & edge-case testing | 4 | Task | 2028-06-16 | 2028-06-23 | 6 | 0% | 6.0.9.5.1 | L. Thompson | M. Washington (QA) |  | 96
6.0.9.6 | Model performance & regression testing | 3 | Task | 2028-06-26 | 2028-07-07 | 10 | 0% | 6.0.9.5 | V. Müller | J. Bennett, K. Garcia |  | 240
6.0.9.7 | Security & penetration testing | 3 | Group task | 2028-07-10 | 2028-07-19 | 8 | 0% | 6.0.9.6 | N. Winthrop | O. Castillo, U. Kandel, V. Redmond, M. Hassan | Cybersecurity / InfoSec (10) | 250
6.0.9.8 | Performance & load testing | 3 | Task | 2028-07-20 | 2028-07-31 | 8 | 0% | 6.0.9.7 | M. Washington (QA) | N. Ferraro |  | 128
6.0.9.9 | Defect triage & resolution cycles | 3 | Group task | 2028-08-01 | 2028-08-16 | 12 | 0% | 6.0.9.8 | K. Garcia | L. Thompson, M. Washington (QA), N. Ferraro, O. Delacroix | QA & Testing (18) + Underwriting & Risk AI (BRD-03) (14) | 480
6.0.9.10 | Test summary & exit report | 3 | Task | 2028-08-17 | 2028-08-23 | 5 | 0% | 6.0.9.9 | N. Ferraro | O. Delacroix |  | 80
6.0.10 | Independent Model Validation | 2 | Summary | 2028-05-08 | 2028-06-13 | 27 | 0%
6.0.10.1 | IMV submission & documentation review | 3 | Task | 2028-05-08 | 2028-05-15 | 6 | 0% |  | X. Sorensen | Y. Larsen |  | 96
6.0.10.2 | Independent performance & fairness validation | 3 | Summary | 2028-05-16 | 2028-05-29 | 10 | 0%
6.0.10.2.1 | Independent replication testing | 4 | Task | 2028-05-16 | 2028-05-22 | 5 | 0% | 6.0.10.1 | Y. Larsen | Z. Winfield (IMV) |  | 80
6.0.10.2.2 | Fairness & bias re-testing | 4 | Task | 2028-05-23 | 2028-05-29 | 5 | 0% | 6.0.10.2.1 | Z. Winfield (IMV) | A. Kessler |  | 76
6.0.10.3 | Validation findings & remediation | 3 | Task | 2028-05-30 | 2028-06-08 | 8 | 0% | 6.0.10.2 | P. Okafor | W. Achebe, X. Sorensen |  | 192
6.0.10.4 | IMV sign-off (production gate) | 3 | Task | 2028-06-09 | 2028-06-13 | 3 | 0% | 6.0.10.3 | P. Okafor | A. Kessler |  | 46
6.0.11 | Compliance, Clinical & Controls Review | 2 | Summary | 2028-05-29 | 2028-07-20 | 39 | 0%
6.0.11.1 | Legal review (liability, disclaimers, contracts) | 3 | Group task | 2028-05-29 | 2028-06-05 | 6 | 0% |  | M. Bernstein | N. Harris, S. Patel, D. Flores, R. Thorne | Legal (6) | 187
6.0.11.2 | Compliance & regulatory review | 3 | Group task | 2028-06-06 | 2028-06-15 | 8 | 0% | 6.0.11.1 | T. Jackson | R. Kimani, B. Cho, C. Morrison, U. Kowalski | Compliance (7) | 278
6.0.11.3 | Clinical / medical-policy review | 3 | Group task | 2028-06-16 | 2028-06-26 | 7 | 0% | 6.0.11.2 | K. Okoro | L. Delacroix, Dr. J. Whitby, Dr. I. Alvarado, Dr. N. Patel | Clinical / Medical Policy & Informatics (6) | 193
6.0.11.4 | SOX / financial-controls testing | 3 | Group task | 2028-06-27 | 2028-07-04 | 6 | 0% | 6.0.11.3 | N. Brennan | P. Whitcomb, O. Fairweather, Q. Marchetti, K. Williams | SOX / Financial Controls (6) | 189
6.0.11.5 | Data privacy audit & DPIA | 3 | Task | 2028-07-05 | 2028-07-12 | 6 | 0% | 6.0.11.4 | O. Whitlock | P. Sandoval |  | 91
6.0.11.6 | Cybersecurity controls assurance | 3 | Task | 2028-07-13 | 2028-07-20 | 6 | 0% | 6.0.11.5 | O. Castillo | P. Halstead |  | 96
6.0.12 | User Acceptance Testing | 2 | Summary | 2028-06-19 | 2028-08-24 | 49 | 0%
6.0.12.1 | UAT planning & environment readiness | 3 | Group task | 2028-06-19 | 2028-06-26 | 6 | 0% |  | H. Solberg7 | I. Nakashima7, E. Beaumont6, F. Kowalczyk7, G. Delvecchio7 | User Acceptance Testing (UAT) (11) | 144
6.0.12.2 | UAT test scenario authoring | 3 | Group task | 2028-06-27 | 2028-07-06 | 8 | 0% | 6.0.12.1 | Y. Sorensen6 | I. Nakashima7, Z. Kessler5, A. Rutherford5, B. Alvarado5 | User Acceptance Testing (UAT) (11) | 205
6.0.12.3 | UAT execution cycles | 3 | Summary | 2028-07-07 | 2028-08-03 | 20 | 0%
6.0.12.3.1 | UAT cycle 1 | 4 | Group task | 2028-07-07 | 2028-07-14 | 6 | 0% | 6.0.12.2 | B. Alvarado5 | C. Whitby8, D. Okoro8, E. Beaumont6, F. Kowalczyk7 | User Acceptance Testing (UAT) (11) | 120
6.0.12.3.2 | UAT defect fixes & retest | 4 | Group task | 2028-07-17 | 2028-07-21 | 5 | 0% | 6.0.12.3.1 | Y. Sorensen6 | H. Solberg7, I. Nakashima7, F. Kowalczyk7, G. Delvecchio7 | User Acceptance Testing (UAT) (11) | 140
6.0.12.3.3 | UAT cycle 2 (regression) | 4 | Group task | 2028-07-24 | 2028-07-28 | 5 | 0% | 6.0.12.3.2 | Y. Sorensen6 | Z. Kessler5, A. Rutherford5, B. Alvarado5, C. Whitby8 | User Acceptance Testing (UAT) (11) | 120
6.0.12.3.4 | Final UAT confirmation | 4 | Group task | 2028-07-31 | 2028-08-03 | 4 | 0% | 6.0.12.3.3 | C. Whitby8 | D. Okoro8, E. Beaumont6, F. Kowalczyk7, G. Delvecchio7 | User Acceptance Testing (UAT) (11) | 80
6.0.12.4 | Business process & runbook validation | 3 | Group task | 2028-08-04 | 2028-08-11 | 6 | 0% | 6.0.12.3 | E. Whitcomb | F. Talbot, G. Restrepo, H. Vartan, I. Halvorsen | IT Operations / Infrastructure (10) | 230
6.0.12.5 | Operational readiness assessment | 3 | Group task | 2028-08-14 | 2028-08-21 | 6 | 0% | 6.0.12.4 | X. Larsen6 | N. Alvarado4, V. Winfield6, W. Achebe6, M. Washington (CustOps) | Customer Service Operations (12) | 178
6.0.12.6 | UAT sign-off | 3 | Task | 2028-08-22 | 2028-08-24 | 3 | 0% | 6.0.12.5 | H. Solberg7 | G. Delvecchio7 |  | 31
6.0.13 | Change Management & Adoption | 2 | Summary | 2028-07-10 | 2028-09-22 | 55 | 0%
6.0.13.1 | Change impact assessment & stakeholder analysis | 3 | Task | 2028-07-10 | 2028-07-18 | 7 | 0% |  | E. Winthrop | F. Achebe |  | 95
6.0.13.2 | Training material development | 3 | Summary | 2028-07-19 | 2028-08-01 | 10 | 0%
6.0.13.2.1 | End-user training curriculum | 4 | Task | 2028-07-19 | 2028-07-25 | 5 | 0% | 6.0.13.1 | F. Achebe | H. Kandel |  | 60
6.0.13.2.2 | Job aids & quick-reference | 4 | Task | 2028-07-26 | 2028-08-01 | 5 | 0% | 6.0.13.2.1 | I. Redmond | H. Kandel |  | 60
6.0.13.3 | Training delivery & enablement | 3 | Group task | 2028-08-02 | 2028-08-17 | 12 | 0% | 6.0.13.2 | G. Okonkwo | B. Prescott, C. Whitfield, D. Solis, I. Redmond | Change Management & Training (8) | 461
6.0.13.4 | Communications campaign | 3 | Group task | 2028-08-18 | 2028-08-29 | 8 | 0% | 6.0.13.3 | R. Castellanos | S. Halloway, T. Ainslie, B. Sullivan | Corporate Communications / PR (4) | 173
6.0.13.5 | Frontline readiness & super-user network | 3 | Group task | 2028-08-30 | 2028-09-08 | 8 | 0% | 6.0.13.4 | N. Alvarado4 | O. Whitby7, P. Okoro7, Q. Beaumont5, R. Kowalczyk6 | Customer Service Operations (12) | 314
6.0.13.6 | Adoption tracking & reinforcement | 3 | Task | 2028-09-11 | 2028-09-22 | 10 | 0% | 6.0.13.5 | D. Solis | E. Winthrop |  | 152
6.0.14 | Pilot Deployment | 2 | Summary | 2028-07-31 | 2028-09-22 | 40 | 0%
6.0.14.1 | Pilot readiness review & go/no-go | 3 | Task | 2028-07-31 | 2028-08-03 | 4 | 0% |  | E. Delvecchio5 | F. Solberg5 |  | 64
6.0.14.2 | Controlled pilot rollout | 3 | Group task | 2028-08-04 | 2028-08-21 | 12 | 0% | 6.0.14.1 | F. Solberg5 | G. Nakashima5, H. Winfield5, I. Achebe5, J. Larsen5 | Underwriting & Risk AI (BRD-03) (14) | 480
6.0.14.3 | Pilot monitoring & tuning | 3 | Task | 2028-08-22 | 2028-09-04 | 10 | 0% | 6.0.14.2 | A. Okoro6 | B. Whitby6, C. Beaumont4 |  | 240
6.0.14.4 | Pilot support & issue resolution | 3 | Group task | 2028-09-05 | 2028-09-18 | 10 | 0% | 6.0.14.3 | S. Delvecchio6 | T. Solberg6, R. Kowalczyk6, U. Nakashima6, V. Winfield6 | Customer Service Operations (12) | 360
6.0.14.5 | Pilot evaluation & production decision | 3 | Task | 2028-09-19 | 2028-09-22 | 4 | 0% | 6.0.14.4 | J. Larsen5 | K. Sorensen5 |  | 64
6.0.15 | Production Deployment & Hypercare | 2 | Summary | 2028-08-21 | 2028-10-25 | 48 | 0%
6.0.15.1 | Production readiness review (3 boards) | 3 | Task | 2028-08-21 | 2028-08-25 | 5 | 0% |  | K. Sorensen5 | L. Kessler4 |  | 80
6.0.15.2 | Production cutover & go-live | 3 | Group task | 2028-08-28 | 2028-09-04 | 6 | 0% | 6.0.15.1 | Z. Thompson | A. Okoro6, B. Whitby6, C. Beaumont4, D. Kowalczyk5 | Underwriting & Risk AI (BRD-03) (14) + IT Operations / Infrastructure (10) | 240
6.0.15.3 | Hypercare & stabilization | 3 | Summary | 2028-09-05 | 2028-09-25 | 15 | 0%
6.0.15.3.1 | Hypercare monitoring | 4 | Group task | 2028-09-05 | 2028-09-14 | 8 | 0% | 6.0.15.2 | L. Kessler4 | M. Rutherford4, Z. Thompson, A. Okoro6, B. Whitby6 | Underwriting & Risk AI (BRD-03) (14) | 320
6.0.15.3.2 | Incident response & fixes | 4 | Group task | 2028-09-15 | 2028-09-25 | 7 | 0% | 6.0.15.3.1 | B. Whitby6 | C. Beaumont4, D. Kowalczyk5, E. Delvecchio5, F. Solberg5 | Underwriting & Risk AI (BRD-03) (14) | 280
6.0.15.4 | Post-go-live service desk support | 3 | Group task | 2028-09-26 | 2028-10-11 | 12 | 0% | 6.0.15.3 | X. Larsen6 | N. Alvarado4, V. Winfield6, W. Achebe6, M. Washington (CustOps) | Customer Service Operations (12) | 355
6.0.15.5 | Benefits baseline established | 3 | Task | 2028-10-12 | 2028-10-17 | 4 | 0% | 6.0.15.4 | Z. Thompson | A. Okoro6 |  | 64
6.0.15.6 | Transition to steady-state operations | 3 | Task | 2028-10-18 | 2028-10-25 | 6 | 0% | 6.0.15.5 | I. Halvorsen | H. Nakamura |  | 52
7.0 | Optimization, Benefits & Closeout | 1 | Summary | 2029-01-05 | 2029-08-29 | 169 | 0%
7.0.1 | Model Optimization & Retraining | 2 | Summary | 2029-01-05 | 2029-04-17 | 73 | 0%
7.0.1.1 | Cross-BRD model performance review | 3 | Task | 2029-01-05 | 2029-01-22 | 12 | 0% |  | A. Reyes | J. Ferraro, M. Delacroix |  | 288
7.0.1.2 | Retraining & optimization cycles | 3 | Summary | 2029-01-23 | 2029-02-21 | 22 | 0%
7.0.1.2.1 | BRD-01 model retraining | 4 | Group task | 2029-01-23 | 2029-01-31 | 7 | 0% | 7.0.1.1 | V. Kessler2 | W. Rutherford2, X. Alvarado2, Y. Whitby3, Z. Okoro3 | Claims & Prior Authorization AI (BRD-01) (28) | 280
7.0.1.2.2 | BRD-02 model retraining | 4 | Group task | 2029-02-01 | 2029-02-09 | 7 | 0% | 7.0.1.2.1 | S. Whitby5 | T. Okoro5, V. Vartan4, R. Alvarado3, U. Delacroix4 | Member & Provider Experience AI (BRD-02) (22) | 258
7.0.1.2.3 | BRD-03 model retraining | 4 | Group task | 2029-02-12 | 2029-02-21 | 8 | 0% | 7.0.1.2.2 | F. Solberg5 | G. Nakashima5, H. Winfield5, I. Achebe5, J. Larsen5 | Underwriting & Risk AI (BRD-03) (14) | 320
7.0.1.3 | Drift remediation & tuning | 3 | Group task | 2029-02-22 | 2029-03-14 | 15 | 0% | 7.0.1.2 | J. Restrepo | K. Vartan, L. Sondheim, M. Marchetti, N. Whitcomb | Data & Cloud AI Platform Foundation (20) | 600
7.0.1.4 | Model governance re-validation (IMV) | 3 | Task | 2029-03-15 | 2029-03-30 | 12 | 0% | 7.0.1.3 | P. Okafor | W. Achebe, X. Sorensen |  | 288
7.0.1.5 | Prompt / rules optimization & A-B testing | 3 | Task | 2029-04-02 | 2029-04-17 | 12 | 0% | 7.0.1.4 | F. Bennett | C. Garcia2, D. Thompson2 |  | 288
7.0.2 | Platform & Cost Optimization | 2 | Summary | 2029-01-30 | 2029-03-26 | 40 | 0%
7.0.2.1 | Compute & token cost optimization | 3 | Task | 2029-01-30 | 2029-02-19 | 15 | 0% |  | N. Whitcomb | O. Talbot, P. Restrepo2 |  | 360
7.0.2.2 | Architecture simplification & tech-debt reduction | 3 | Group task | 2029-02-20 | 2029-03-12 | 15 | 0% | 7.0.2.1 | F. Okonkwo | G. Petrova, H. Delgado, I. Suzuki, J. Kowalczyk | Enterprise Architecture (8) | 600
7.0.2.3 | License & vendor rationalization | 3 | Task | 2029-03-13 | 2029-03-26 | 10 | 0% | 7.0.2.2 | I. Merchant | L. Park |  | 128
7.0.3 | Benefits Realization & Audit | 2 | Summary | 2029-02-22 | 2029-04-25 | 45 | 0%
7.0.3.1 | Benefits tracking & measurement framework | 3 | Task | 2029-02-22 | 2029-03-09 | 12 | 0% |  | A. Rodriguez | B. Halvorsen |  | 192
7.0.3.2 | Benefits data collection & validation | 3 | Group task | 2029-03-12 | 2029-03-30 | 15 | 0% | 7.0.3.1 | B. Halvorsen | C. Restrepo, D. Vartan, E. Talbot, F. Sondheim | Program Finance (6) | 564
7.0.3.3 | Benefits realization audit | 3 | Task | 2029-04-02 | 2029-04-13 | 10 | 0% | 7.0.3.2 | A. Rodriguez | F. Sondheim |  | 144
7.0.3.4 | Financial reconciliation & reporting | 3 | Group task | 2029-04-16 | 2029-04-25 | 8 | 0% | 7.0.3.3 | M. Osei | N. Brennan, P. Whitcomb, O. Fairweather, K. Williams | SOX / Financial Controls (6) | 266
7.0.4 | Knowledge Transfer & Transition | 2 | Summary | 2029-03-19 | 2029-07-10 | 82 | 0%
7.0.4.1 | Knowledge transfer to ACME teams | 3 | Summary | 2029-03-19 | 2029-04-13 | 20 | 0%
7.0.4.1.1 | Platform & MLOps knowledge transfer | 4 | Group task | 2029-03-19 | 2029-03-30 | 10 | 0% |  | N. Whitcomb | O. Talbot, P. Restrepo2, Q. Halvorsen2, R. Bianchi | Data & Cloud AI Platform Foundation (20) | 400
7.0.4.1.2 | Governance & model knowledge transfer | 4 | Group task | 2029-04-02 | 2029-04-13 | 10 | 0% | 7.0.4.1.1 | M. Delacroix | C. Alvarez, T. Nakamura, R. Osei, P. Singh | AI Governance & CoE (12) | 392
7.0.4.2 | Customer Service Operations enablement | 3 | Group task | 2029-04-16 | 2029-05-04 | 15 | 0% | 7.0.4.1 | N. Alvarado4 | O. Whitby7, P. Okoro7, Q. Beaumont5, R. Kowalczyk6 | Customer Service Operations (12) | 588
7.0.4.3 | Documentation & runbook finalization | 3 | Group task | 2029-05-07 | 2029-05-22 | 12 | 0% | 7.0.4.2 | A. Prescott | B. Fairweather, C. Sondheim, D. Marchetti, H. Nakamura | IT Operations / Infrastructure (10) | 413
7.0.4.4 | Steady-state operations transition | 3 | Task | 2029-05-23 | 2029-06-12 | 15 | 0% | 7.0.4.3 | R. Bianchi | S. Fitzgerald, T. Andersen |  | 360
7.0.4.5 | Independent ACME operation period (≥ 4 weeks) | 3 | Group task | 2029-06-13 | 2029-07-10 | 20 | 0% | 7.0.4.4 | S. Delvecchio6 | T. Solberg6, R. Kowalczyk6, U. Nakashima6, V. Winfield6 | Customer Service Operations (12) | 720
7.0.5 | Organizational Transition | 2 | Summary | 2029-04-11 | 2029-05-31 | 37 | 0%
7.0.5.1 | Role transition & workforce redeployment | 3 | Group task | 2029-04-11 | 2029-05-01 | 15 | 0% |  | F. Bianchi | E. Marsh, G. Solberg, H. Rutherford, C. Johnson | HR / Workforce Planning & Org Design (6) | 432
7.0.5.2 | Consultant roll-off & access decommissioning | 3 | Task | 2029-05-02 | 2029-05-15 | 10 | 0% | 7.0.5.1 | D. Ferraro | C. Johnson |  | 96
7.0.5.3 | Final change & adoption reinforcement | 3 | Group task | 2029-05-16 | 2029-05-31 | 12 | 0% | 7.0.5.2 | G. Okonkwo | E. Winthrop, F. Achebe, I. Redmond, H. Kandel | Change Management & Training (8) | 403
7.0.6 | Continuous Improvement & Innovation | 2 | Summary | 2029-05-04 | 2029-07-06 | 46 | 0%
7.0.6.1 | Use-case backlog review & prioritization | 3 | Group task | 2029-05-04 | 2029-05-21 | 12 | 0% |  | R. Osei | V. Castellano, L. Whitfield, D. Ibrahim, K. Novak | AI Governance & CoE (12) | 461
7.0.6.2 | Emerging AI capability evaluation | 3 | Task | 2029-05-22 | 2029-06-06 | 12 | 0% | 7.0.6.1 | S. Khurana | A. Reyes, J. Ferraro |  | 288
7.0.6.3 | Process improvement from operational feedback | 3 | Group task | 2029-06-07 | 2029-06-22 | 12 | 0% | 7.0.6.2 | X. Larsen6 | N. Alvarado4, V. Winfield6, W. Achebe6, M. Washington (CustOps) | Customer Service Operations (12) | 355
7.0.6.4 | Customer experience measurement & NPS analysis | 3 | Task | 2029-06-25 | 2029-07-06 | 10 | 0% | 7.0.6.3 | J. Lee | U. Marchetti, V. Okwuosa |  | 240
7.0.7 | Program Closeout | 2 | Summary | 2029-05-29 | 2029-08-29 | 67 | 0%
7.0.7.1 | Closeout report & performance summary | 3 | Task | 2029-05-29 | 2029-06-07 | 8 | 0% |  | H. Kim | V. Patel, G. Brown |  | 153
7.0.7.2 | Financial close & contingency return | 3 | Task | 2029-06-08 | 2029-06-19 | 8 | 0% | 7.0.7.1 | A. Rodriguez | B. Halvorsen, C. Restrepo |  | 192
7.0.7.3 | Lessons learned consolidation | 3 | Task | 2029-06-20 | 2029-06-27 | 6 | 0% | 7.0.7.2 | C. Tyrrell | Q. Wilson, G. Brown |  | 115
7.0.7.4 | Contract & vendor closeout | 3 | Task | 2029-06-28 | 2029-07-05 | 6 | 0% | 7.0.7.3 | G. Ainsley | L. Park |  | 86
7.0.7.5 | Records archival & audit pack | 3 | Task | 2029-08-06 | 2029-08-13 | 6 | 0% |  | C. Tyrrell | M. Kavanagh |  | 55
7.0.7.6 | Final communications & recognition | 3 | Task | 2029-08-17 | 2029-08-22 | 4 | 0% |  | S. Halloway | T. Ainslie |  | 48
7.0.7.7 | Program closeout approval (ESB) | 3 | Task | 2029-08-27 | 2029-08-29 | 3 | 0% |  | C. Tyrrell | M. Kavanagh |  | 28