CHANGE REQUEST CR-003

Change Control Detail — Project Catalyst, AI Transformation Program

ACME Highland Health  |  Pulaski Advisory Group  |  $99M · 262 people · 36.5 months

A worked example of the program's change-control process at full depth. The Change Control Log is the register of all changes; this is the underlying document for a single request — the artifact that a Tier 2 change actually requires before any board will consider it. CR-003 was raised in Week 4 of Phase 0, when legacy claims data profiling surfaced fragmentation materially worse than the estimate the BRD-01 schedule was built on.

## 1 · Request Header

| Change Request ID | CR-003 |
| --- | --- |
| Title | Legacy claims data remediation — additional scope and effort to support BRD-01 model training |
| Change type | Scope addition with cost and schedule impact |
| Tier | Tier 2 — exceeds Program Director standing authority (scope change of any size; budget > $500K) |
| Status | Under review |
| Date raised | 10 September 2026 (Week 4, Phase 0) |
| Requested by | Data & Cloud AI Platform Lead |
| Change owner | C. Tyrrell, Program Director |
| Approval authority | Executive Steering Board (cost/schedule) with AI Governance Board endorsement (model data quality) |
| Target decision date | 25 September 2026, alongside the AI Readiness Assessment Report |
| Linked risk | RSK-01 — Legacy claims data fragmentation (inherent rating: Likely × High) |

## 2 · Background & Description of Change

The Phase 0 AI Readiness Assessment includes a data-quality profiling exercise across the claims and prior-authorization source systems that will feed BRD-01. Profiling is substantially complete and has established that source data is materially more fragmented than the planning assumption used to build the BRD-01 schedule.

Specifically, profiling has found: inconsistent provider identifiers across three claims platforms arising from historical acquisitions; incomplete diagnosis and procedure coding on a significant proportion of older records; no reliable linkage key between prior-authorization requests and their resulting claims; and inconsistent handling of adjustment and reversal records. Individually each is manageable. Together, they mean that the training dataset assembled from these sources would not be fit to train a prior-authorization decisioning model to the standard the program's Master Test & QA Strategy requires — specifically dimensions 1 (data quality and representativeness) and 5 (fairness), since coding gaps are not evenly distributed across the member population.

This request seeks approval for a dedicated data remediation workstream — additional engineering effort, tooling, and elapsed time — to establish a governed, linked, quality-assured claims dataset before BRD-01 model development begins, rather than discovering the problem during model training.

## 3 · Reason for Change & Consequence of Not Acting

The program's planning assumption was that source claims data would require standard cleansing within the effort already provided in WBS element 2.0. Profiling has disproved that assumption. This is not a scope preference; it is a correction to a factual estimate, surfaced by the Phase-0 activity designed to surface exactly this class of problem.

If the change is not approved: BRD-01 model development would proceed on a dataset known to be unfit. The most likely outcome is that the model fails independent validation on data quality or fairness grounds, forcing rework at a far later and more expensive point — after model development, integration, and testing effort has already been spent. Secondary consequences include a materially higher risk of a fairness finding on a member-facing prior-authorization decision, which carries regulatory exposure under the same scrutiny anticipated in RSK-04.

## 4 · Options Analysis

| Option | Description | Cost | Schedule Impact | Residual Risk |
| --- | --- | --- | --- | --- |
| Option ADo nothing | Proceed on existing data with in-flight cleansing during model development | $0 | None initially; high probability of 3–5 month rework later | Unacceptable — near-certain IMV failure on data quality and fairness |
| Option BPartial remediation | Remediate identifier linkage only; accept coding gaps and handle statistically during modelling | $740,000 | 3 weeks to BRD-01 requirements sign-off | Moderate — linkage resolved, but coding gaps still create sub-population bias exposure |
| Option CFull remediation Recommended | Dedicated remediation workstream: identifier resolution, coding completion where recoverable, PA-to-claim linkage, adjustment/reversal normalization, plus a permanent data-quality rules engine | $1,240,000 | 6 weeks to BRD-01 requirements sign-off; no impact to the 30 Sep 2027 production milestone (absorbed within BRD-01 float) | Low — dataset fit for training and for fairness assessment |
| Option DDefer BRD-01 | Re-sequence so BRD-02 leads and BRD-01 follows after remediation | $2,100,000 | Re-baselines the entire program; BRD-01 production slips ~9 months | Rejected — sacrifices the flagship, disrupts CMS-0057-F coordination, poor value |

## 5 · Impact Assessment

Assessment below is for the recommended Option C.

| Dimension | Impact | Detail |
| --- | --- | --- |
| Scope | Addition | New deliverable "Legacy claims data remediation" added under WBS 2.0 Data & Cloud AI Platform. No existing scope removed. |
| Cost | +$1,240,000 | Funded from contingency reserve, not from a budget increase. Reserve reduces $9.0M → $7.76M (7.8% of authorized baseline, remaining within acceptable range for the risk profile). |
| Schedule | 6 weeks | BRD-01 requirements sign-off moves 18 Dec 2026 → 29 Jan 2027. Platform Foundation (12 Mar 2027) and BRD-01 Production (30 Sep 2027) milestones are unchanged — the six weeks are absorbed within existing float on the BRD-01 path. |
| Resources | +6 FTE, 14 weeks | 4 data engineers (offshore, synthetic/de-identified work), 2 onshore data analysts for PHI-bearing linkage work. Sourced through existing Pulaski SOW-01 capacity; no new vendor. |
| Quality | Positive | Directly improves the evidence base for test dimensions 1 and 5. Reduces probability of an IMV failure at the BRD-01 production gate. |
| Risk | Reduces RSK-01 | Moves RSK-01 from Likely × High toward Possible × Moderate once remediation completes. Introduces minor new delivery risk around remediation duration, tracked as a sub-risk. |
| Benefits | Neutral to positive | No change to the $27.2M steady-state benefit case. Protects the largest benefit stream (PA automation, $12.8M/yr) from a delayed or degraded launch. |
| Compliance | Positive | A governed, lineage-traceable dataset strengthens the program's position under NAIC and state AI-in-insurance scrutiny. |
| Contractual | None | Within SOW-01 scope and envelope; no amendment required. Milestone payment schedule unchanged. |

## 6 · Recommendation

Recommend approval of Option C — full remediation, $1,240,000 drawn from contingency reserve. It is the only option that produces a dataset fit for both model training and defensible fairness assessment, and it does so without moving the program's external commitments: BRD-01 still reaches production on 30 September 2027. Option A defers a known problem into a more expensive phase; Option B leaves the fairness exposure — the one risk the program is least able to absorb — substantially open; Option D destroys the Year 1 value case for a problem that has a $1.24M solution. The contingency reserve was sized at 9.1% precisely because RSK-01 was identified as a leading exposure at authorization; this is the reserve performing its intended function.

## 7 · Implementation Plan (if approved)

| Step | Activity | Owner | Duration | Completion |
| --- | --- | --- | --- | --- |
| 1 | Mobilize remediation team; confirm onshore/offshore data-access boundaries with Data Privacy Office | Platform Lead / HR | 1 week | 2 Oct 2026 |
| 2 | Provider identifier resolution across the three claims platforms | Data engineering | 4 weeks | 30 Oct 2026 |
| 3 | Prior-auth to claim linkage key construction and validation | Data engineering | 3 weeks | 20 Nov 2026 |
| 4 | Diagnosis/procedure coding completion where recoverable; gap documentation where not | Data analysts + Clinical | 4 weeks | 18 Dec 2026 |
| 5 | Adjustment and reversal normalization | Data engineering | 2 weeks | 8 Jan 2027 |
| 6 | Data-quality rules engine deployed; sub-population coverage verified for fairness testing | Platform + IMV | 2 weeks | 22 Jan 2027 |
| 7 | Dataset governance sign-off; BRD-01 requirements sign-off | AI Governance Board | 1 week | 29 Jan 2027 |

## 8 · Affected Baselines & Artifacts

If approved, the following are updated under configuration control within five business days of the decision:

| Artifact | Change required |
| --- | --- |
| Program Budget | Contingency ledger entry: $1.24M drawn, reserve balance $7.76M. Category and workstream views updated; total authorized baseline unchanged at $99.0M. |
| WBS Budget Rollup & Resource-Loaded WBS | New deliverable and seven work packages under element 2.0; resource assignments and dates added. |
| Program Management Plan | Milestone table: BRD-01 requirements sign-off 18 Dec 2026 → 29 Jan 2027. |
| RAIDD Log | RSK-01 updated to "mitigation in execution" with revised residual rating; new sub-risk for remediation duration. |
| BRD-01 | Data requirements section updated to reference the remediated dataset and its governance sign-off. |
| Change Control Log | CR-003 status moved to Approved with decision date and approver record. |
| Program Dashboard | Contingency drawdown reflected; RSK-01 heat-map position updated at next reporting cycle. |

## 9 · Approval Routing & Decision Record

Tier 2 changes require the relevant board's approval. Because this request affects both the cost baseline and model data quality, it is routed to both the Executive Steering Board and the AI Governance Board, with Program Finance and SOX review preceding the decision.

| Reviewer / Approver | Role in decision | Status | Date |
| --- | --- | --- | --- |
| Program Finance (A. Rodriguez) | Cost validation and contingency impact | Reviewed — supports | 12 Sep 2026 |
| SOX / Financial Controls | Controls review (contingency drawdown) | Reviewed — no objection | 15 Sep 2026 |
| Data Privacy Office (E. Sato) | PHI access boundaries for remediation work | Reviewed — conditions noted | 16 Sep 2026 |
| Chief Enterprise Architect (D. Chen) | Architecture impact — data-quality rules engine | Reviewed — supports | 17 Sep 2026 |
| AI Governance Board (S. Khurana) | Endorsement — model data quality and fairness basis | Scheduled | 25 Sep 2026 |
| Executive Steering Board (Chair: M. Kavanagh) | Approval authority — cost and schedule baseline | Scheduled | 25 Sep 2026 |

### Decision block

| Decision | ☐ Approved ☐ Approved with conditions ☐ Rejected ☐ Deferred |
| --- | --- |
| Conditions (if any) |  |
| Executive Sponsor signature |  |
| Date |  |

## 10 · Audit Trail

| Date | Event | Actor |
| --- | --- | --- |
| 08 Sep 2026 | Profiling findings escalated from the AI Readiness Assessment workstream | Data & Cloud AI Platform Lead |
| 10 Sep 2026 | CR-003 raised and logged; tier assessed as Tier 2 | PMO (T. Valdez) |
| 11 Sep 2026 | Options analysis and impact assessment drafted | Program Director + Platform Lead |
| 12–17 Sep 2026 | Functional reviews completed (Finance, SOX, Privacy, Architecture) | Respective functions |
| 25 Sep 2026 | Scheduled for joint ESB / AIGB decision | PMO |

How this fits the process. Tier 1 changes are decided by the Program Director within standing authority and recorded on the log without a document at this depth. Tier 2 — this request — requires the full analysis above and a board decision. Tier 3 (contingency draws above $1M in aggregate, program viability, or Charter re-baseline) escalates to the Executive Sponsor and CFO. The tier definitions and turnaround targets are set out in the Change Control Log.

Illustrative program data for a fictional engagement (ACME Highland Health / Pulaski Advisory Group), created to demonstrate program-management practice. CR-003 is a modeled change request consistent with the program's Week-4 / Phase-0 position at 11 September 2026; it is shown under review, and no program baseline has been altered. Figures reconcile to the $99.0M authorized budget and the $9.0M contingency reserve. Cross-references: Change Control Log · RAIDD Log · Program Budget · Master Test & QA Strategy.