COST-BENEFIT ANALYSIS

Business Case — Project Catalyst, AI Transformation Program

ACME Highland Health  |  Pulaski Advisory Group  |  $99M · 262 people · 36.5 months

## Executive Summary

Project Catalyst is a $99.0M, 36.5-month investment to build enterprise AI capability at ACME Highland Health across claims & prior authorization, member & provider experience, and underwriting & risk. This analysis models the program over a 10-year horizon at an 8% discount rate. The business case is positive but disciplined: it clears the 8% hurdle with a modest margin, and its return depends on delivering the benefit ramp on schedule. It is presented on conservative assumptions rather than optimistic ones — the intent is a case that holds up under scrutiny, not one that flatters the program.

Recommendation: Proceed. The program returns a positive NPV of +$2,968,904 and an IRR of 8.94%, clearing the 8% cost of capital. Simple payback is ~7.6 years from program start (~9.6 years on a discounted basis, within the 10-year window); measured from the start of steady-state operations — once the 3-year build is complete — operational payback is ~4.6 years. Because the margin over the hurdle is modest, approval should be paired with disciplined benefit-realization tracking and the FinOps controls described below.

## 1 · Approach & Methodology

The analysis compares the fully-loaded program investment against quantified, risk-adjusted operational benefits over a 10-year horizon (Years 1–3 build; Years 4–10 steady-state operation). Key modeling conventions:

Discount rate 8% — ACME's weighted cost of capital; all cash flows discounted to present value at end-of-year timing.

Conservative benefit recognition — no benefit during the build beyond partial ramp as capabilities go live; full run-rate not assumed until Year 5.

Run-state cost included — ongoing cloud/compute, model monitoring and retraining, and CoE operations of $9.5M/year netted against gross benefit from Year 4 onward.

Benefits are operational, not headcount-elimination — modeled as productivity, deflection, automation, and loss-avoidance, consistent with the program's human-in-the-loop governance posture.

Excludes the separate CMS-0057-F baseline compliance project (out of scope) and any speculative revenue upside.

## 2 · Investment (Cost) Model

The $99.0M program investment is drawn against three annual SOW envelopes. Steady-state run cost of $9.5M/year begins once capabilities are in production (Year 4+).

| Program Year | Scope | Build Investment | Run-State Cost |
| --- | --- | --- | --- |
| Year 1 | Foundation, CoE, Platform, BRD-01 | $27,720,000 | $0 |
| Year 2 | BRD-02, BRD-03 (peak delivery) | $41,580,000 | $0 |
| Year 3 | Optimization & sustain, closeout | $29,700,000 | $0 |
| Years 4–10 | Steady-state operation (per year) | $0 | $9,500,000 |
| Build total |  | $99,000,000 | $9.5M/yr |

Build investment reconciles to the Program Budget and Charter §13.1. Run-state cost reconciles to the ongoing-operations line in the TCO model.

## 3 · Benefit Model — Full Run-Rate (Year 5+)

Four quantified benefit streams total $27.2M annually at full run-rate, each modeled conservatively from ACME's operating baselines.

| Benefit Stream | Basis of Estimate | Annual Value |
| --- | --- | --- |
| Claims & PA Automation & Labor | ~800k annual prior-auth requests; AI auto-adjudication of routine cases under clinical oversight reduces manual review labor and cycle time against a ~$30/request baseline cost. | $12,800,000 |
| PA & Claims Fraud / Waste Detection | Improved detection of inappropriate or anomalous prior-auth and claims patterns via model scoring. | $2,400,000 |
| Member & Provider Experience & Deflection | Virtual-assistant contact deflection plus agent-assist productivity across member and provider service channels. | $8,800,000 |
| Underwriting Risk & Productivity | Improved risk selection and underwriter throughput from decision-support scoring (post independent validation). | $3,200,000 |
| Total Full Run-Rate Annual Benefit |  | $27,200,000 |

### Benefit Realization Ramp (Years 1–5)

Benefits ramp as capabilities reach production and adoption matures — a deliberately conservative curve given the phased BRD go-lives.

| Year | Phase | Realization | Gross Benefit | Drivers |
| --- | --- | --- | --- | --- |
| Year 1 | Build & Pilot | 0% | $0 | BRD-01 pilot only; no production volume |
| Year 2 | BRD-01 ramp + BRD-02/03 pilot | 25% | $6,800,000 | BRD-01 in production (PA automation ramping); BRD-02/03 in pilot |
| Year 3 | Expansion & optimization | 55% | $14,960,000 | BRD-02 to production; BRD-03 ramping; PA approaching steady-state |
| Year 4 | Sustained operations | 85% | $23,120,000 | All BRDs in steady-state on trailing edge of ramp |
| Year 5+ | Full run-rate | 100% | $27,200,000 | All systems optimized; full benefit capture |

## 4 · 10-Year Cash Flow, NPV, IRR & Payback

Net cash flow combines build investment (Years 1–3), realized gross benefit, and run-state cost (Years 4+), discounted at 8%.

| Yr | Investment | Gross Benefit | Run Cost | Net Cash Flow | Cumulative | PV @ 8% | Cum. PV |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Y1 | $27.72M | $0 | $0 | -$27,720,000 | -$27.72M | -$25,666,667 | -$25.67M |
| Y2 | $41.58M | $6.80M | $0 | -$34,780,000 | -$62.50M | -$29,818,244 | -$55.48M |
| Y3 | $29.70M | $14.96M | $0 | -$14,740,000 | -$77.24M | -$11,701,087 | -$67.19M |
| Y4 | $0 | $23.12M | $9.50M | +$13,620,000 | -$63.62M | +$10,011,107 | -$57.17M |
| Y5 | $0 | $27.20M | $9.50M | +$17,700,000 | -$45.92M | +$12,046,323 | -$45.13M |
| Y6 | $0 | $27.20M | $9.50M | +$17,700,000 | -$28.22M | +$11,154,002 | -$33.97M |
| Y7 | $0 | $27.20M | $9.50M | +$17,700,000 | -$10.52M | +$10,327,780 | -$23.65M |
| Y8 | $0 | $27.20M | $9.50M | +$17,700,000 | +$7.18M | +$9,562,759 | -$14.08M |
| Y9 | $0 | $27.20M | $9.50M | +$17,700,000 | +$24.88M | +$8,854,407 | -$5.23M |
| Y10 | $0 | $27.20M | $9.50M | +$17,700,000 | +$42.58M | +$8,198,525 | +$2.97M |
| NPV |  |  |  |  |  |  | +$2,968,904 |

Reading the payback three ways. Because most of the cost is front-loaded and benefits ramp, payback depends on the reference point: Simple payback (from program start): ~7.6 years — cumulative undiscounted cash flow turns positive during Year 8. Discounted payback (from program start): ~9.6 years — cumulative present value turns positive in Year 10, within the evaluation window. Operational payback (from steady-state operations, after the 3-year build): ~4.6 years — run-state net cash flow recovers the accumulated build outlay within roughly four-and-a-half years of go-live.

## 5 · Sensitivity Analysis

NPV sensitivity to a ±20% swing in each key assumption, holding others at base case. Prior-auth volume and baseline cost are the dominant value drivers; delivery-schedule and incident risks are downside-only.

| Assumption | Base Case | Downside | Base NPV | Upside |
| --- | --- | --- | --- | --- |
| PA automation volume (annual requests) | 800,000 | -$8.4M | +$2.97M | +$8.4M |
| Baseline PA processing cost | $30/req | -$6.2M | +$2.97M | +$6.2M |
| Cloud/compute cost escalation | 0.8%/yr | -$1.8M | +$2.97M | — |
| Benefit-ramp delay (6 months per BRD) | On time | -$5.1M | +$2.97M | — |
| Model incident (pause PA 3 months, Yr 2) | No incident | -$2.3M | +$2.97M | — |

Implication. The case is most exposed to prior-auth volume/cost assumptions and to schedule slippage. A single 6-month ramp delay per BRD (-$5.1M) is enough to push NPV negative — which is why benefit-realization tracking and the FinOps compute controls are treated as conditions of approval, not optional.

## 6 · Scenario Analysis

| Scenario | Assumptions | 10-Yr NPV | Payback (simple) |
| --- | --- | --- | --- |
| Conservative | Benefits -20%, one 6-month ramp delay | ~-$6M | > 10 years (Year 11) |
| Base | Modeled assumptions as above | +$2.97M | ~7.6 years |
| Optimistic | Benefits +20%, on-time ramp, lower compute escalation | ~+$12M | ~6 years |

The spread is deliberately wide: this is a program whose return is earned through execution discipline. The base case is defensible; the conservative case is a genuine downside that governance is designed to prevent.

## 7 · Indirect & Qualitative Benefits

Not monetized in the model above, but material to the decision:

Regulatory posture — a governed AI capability positions ACME ahead of tightening AI-in-insurance oversight (NAIC, state laws) and supports the separate CMS-0057-F compliance effort.

Reusable platform & CoE — the Data & Cloud AI Platform and Center of Excellence lower the cost of every future AI use case beyond the three in scope.

Member & provider experience — faster prior-auth decisions and better self-service improve satisfaction and retention, with second-order revenue effects excluded from the model.

Talent & capability — the program builds durable in-house AI/MLOps capability that outlasts the engagement.

## 8 · Risks to Benefit Realization

The benefit case is directly exposed to the program's anticipated risks — each has a mitigation owner on the RAIDD Log:

Data quality (RSK-01) — poor legacy claims data delays PA automation, the largest benefit stream.

Compute cost (RSK-02) — unmanaged GenAI spend erodes net benefit; FinOps guardrails protect the run-state cost line.

Adoption (RSK-07) — deflection and productivity benefits depend on frontline adoption; phased rollout protects them.

Model incident (RSK-03) — a member-facing incident forcing a pause directly reduces realized benefit (see sensitivity).

Bottom line. On conservative assumptions Project Catalyst clears its cost of capital with a positive NPV and an 8.94% IRR, and builds a reusable AI platform, governance capability, and regulatory posture that the numbers above do not fully capture. The recommendation is to proceed, conditioned on disciplined benefit tracking and the compute-cost and adoption controls that the sensitivity analysis shows the case depends on.

## Read Alongside

This analysis pairs with the Total Cost of Ownership (10-year run-and-maintain view), the Program Budget (baseline detail), and the Program Charter §2.3 financial summary.

Illustrative program data for a fictional engagement (ACME Highland Health / Pulaski Advisory Group), created to demonstrate program-management practice. Financial figures are modeled and reconcile to the $99.0M program investment, the three annual SOW envelopes, and the TCO model; NPV (+$2,968,904), IRR (8.94%), and payback are computed from the cash-flow model shown. Not actual financial records. Cross-references: Total Cost of Ownership · Program Budget · Program Charter.