PROGRAM DASHBOARD

Program Controls · Executive Dashboard — Project Catalyst, AI Transformation Program

ACME Highland Health  |  Pulaski Advisory Group  |  $99M · 262 people · 36.5 months

Status as of Friday, 11 September 2026 — Week 4, Phase 0 (Foundation)

1 · Program Health at a Glance

Project Catalyst is in Week 4 of Phase 0 (Foundation) — the 12-week mobilization leg of a 36.5-month, $99.0M program running 17 Aug 2026 through 29 Aug 2029. Overall status is GREEN: the program is tracking to its approved schedule and cost baselines with no variances to report, which is expected this early in delivery. Foundation work is advancing on four parallel fronts — the AI Readiness Assessment, the AI Center-of-Excellence charter & governance framework, platform/cloud vendor selection, and early BRD-01 (Claims & Prior Authorization AI) requirements preparation ahead of the December design sign-off. The program's ten anticipated risks are logged on the RAIDD register as forward-looking items; none has yet materialized. Near-term focus: deliver the AI Readiness Assessment Report (25 Sep) and stand up the AI Governance Board and Enterprise Architecture Review Board so phase-gate governance is fully operational before Phase 1 design begins.

| Indicator | Value | Detail | Signal |
| --- | --- | --- | --- |
| Overall Status | Green | On baseline · no variance to report | On track |
| Schedule (SPI) | 1.00 | 2.3% of 1,108-day schedule elapsed | On baseline |
| Cost (CPI) | 1.00 | ~$2.0M of $99.0M drawn to date | On baseline |
| Open Risks | 0 / 10 | 0 realized · 10 anticipated on register | Monitoring |
| Next Milestone | AI Readiness Report | Targeted 25 Sep 2026 | On plan |

Budget & Earned Value

| Measure | Spent / Baseline | % Drawn |
| --- | --- | --- |
| Year 1 SOW envelope | $2.0M / $27.72M | 7% |
| Program budget (life-of-program) | $2.0M / $99.0M | 2% |
| Phase 0 Foundation allocation | $2.0M / $4.9M | 41% |

EVM: PV $2.0M · EV $2.0M · AC $2.0M · CPI 1.00 · SPI 1.00.  Envelopes reconcile to the CBA, TCO, and the three annual SOWs.

Milestone Rail — First-Year Key Milestones

| Date | Milestone | Status |
| --- | --- | --- |
| 17 Aug 2026 | Program kickoff | Complete |
| 25 Sep 2026 | AI Readiness Assessment Report | Next / in progress |
| 06 Nov 2026 | CoE Charter · Governance Framework · Platform Vendor | Upcoming |
| 18 Dec 2026 | BRD-01 Requirements Sign-off | Upcoming |
| 12 Mar 2027 | Platform Foundation Go-Live | Upcoming |
| 30 Sep 2027 | BRD-01 Production Deployment | Upcoming |

2 · Drill-Down: Scope, Risk & Quality

WBS Workstream Progress — 7 elements · 64 work packages

| WBS Element | Budget | % Complete | Status |
| --- | --- | --- | --- |
| 1.0 Program Management & PMO | $12.6M | 8% | In progress |
| 2.0 Data & Cloud AI Platform | $20.7M | 6% | In progress |
| 3.0 AI Governance & Center of Excellence | $13.2M | 7% | In progress |
| 4.0 BRD-01 · Claims & Prior Authorization AI | $11.02M | 3% | Requirements prep |
| 5.0 BRD-02 · Member & Provider Experience AI | $13.2M | 0% | Not started |
| 6.0 BRD-03 · Underwriting & Risk AI | $12.48M | 0% | Not started |
| 7.0 Optimization, Benefits & Closeout | $15.8M | 0% | Not started |

Budget-weighted completion 2.0%. Cross-cutting workstreams (PMO, Data & Cloud, AI Governance) run in parallel from Day 1; BRD delivery legs ramp by phase.

Top Program Risks — anticipated, monitored

| ID | Risk | Inherent | Mitigation posture |
| --- | --- | --- | --- |
| RSK-01 | Legacy claims data fragmentation | High | Data profiling underway in Phase 0; remediation rules scoped before Build. |
| RSK-02 | GenAI compute / token cost overrun | Med-High | FinOps guardrails & budget alerting in platform build (Year 2 watch). |
| RSK-03 | Member chatbot hallucination / liability | High | Human-in-the-loop, disclaimers, confidence thresholds designed into BRD-02 (Air Canada precedent). |
| RSK-06 | Independent validation flags model bias | Medium | Second-line IMV gate before any BRD-03 production use; retraining budgeted. |

RAIDD Summary — register at Week 4

| Category | Count | Note |
| --- | --- | --- |
| Risks | 10 | All anticipated · 0 realized |
| Assumptions | 6 | Baseline planning set |
| Issues | 0 | None open |
| Dependencies | 4 | 1 external (CMS-0057-F compliance project) |
| Decisions | 3 | Logged in Phase 0 |

Phase-Gate Readiness

| Gate | Target | Status |
| --- | --- | --- |
| G0 · Foundation | Nov 2026 | Prep |
| G1 · Requirements & Design | Feb 2027 | Not started |
| G2 · Build & Test | Jun 2027 | Not started |
| G3 · Pilot & Pre-Prod | Aug 2027 | Not started |
| G4 · Production Scale | Sep 2027 | Not started |

Program Risk Heat Map — inherent rating (anticipated register)

| Likelihood ↓ / Impact → | Very Low | Low | Moderate | High | Very High |
| --- | --- | --- | --- | --- | --- |
| Almost certain | — | — | RSK-10 | — | — |
| Likely | — | — | RSK-02, RSK-07 | RSK-01 | — |
| Possible | — | — | RSK-05, RSK-06 | RSK-03, RSK-04 | — |
| Unlikely | — | — | RSK-09 | RSK-08 | — |
| Rare | — | — | — | — | — |

All ten anticipated risks are plotted by inherent rating — likelihood (rows) against impact (columns), before mitigation. Cell colour marks the severity zone; the risk IDs show which risks sit where. The cluster sits in the Moderate–High band — legacy data quality (RSK-01), chatbot liability (RSK-03), and prior-auth regulatory scrutiny (RSK-04) are highest-rated. None has yet been realized as an issue.

3 · Resource Utilization — Phase 0 Loading

| Role | Focus | Utilization |
| --- | --- | --- |
| C. Tyrrell — Program Director | Program leadership | 100% |
| T. Valdez — PMO Lead | PMO stand-up | 85% |
| M. Torres — Senior Scheduler / EVM | Schedule & cost baseline | 90% |
| D. Chen — Chief Enterprise Architect | Architecture & vendor eval | 75% |
| S. Khurana — AI Governance Director | Governance framework | 65% |
| Vendor / Procurement Lead | Platform selection (active Ph0) | 70% |
| Data & Cloud Platform Lead | Architecture & vendor eval | 70% |
| AI CoE Lead | Charter & operating model | 60% |
| BRD-01 Delivery Lead | Requirements preparation | 55% |
| A. Rodriguez — Program Finance | Cost control & EVM | 45% |
| Data Privacy Officer | PHI/PII framework setup | 40% |
| Cybersecurity Lead | Security architecture inputs | 35% |
| Legal / Compliance | Regulatory framing | 30% |
| Change Mgmt / OCM Lead | Stakeholder & comms setup | 25% |
| QA / Test Lead | Ramps in Phase 2 (Build & Test) | 20% |
| P. Okafor — Independent Model Validation | Ramps in Phase 2 | 15% |

Utilization reflects a Phase-0 profile: foundation, governance, and vendor-selection roles are heavily loaded while BRD build teams, QA, and second-line validation ramp on in later phases. Full staffing model in the Resource Plan and Org Chart.

Illustrative program data for a fictional engagement (ACME Highland Health / Pulaski Advisory Group), created to demonstrate program-management practice. Status metrics reflect a modeled Week-4 / Phase-0 position as of 11 September 2026 and reconcile to the $99.0M program value and the three annual SOW envelopes.