## Slide 1
PROGRAM KICKOFF · PHASE 0 · DAY 1
Project
Catalyst
Governed, production AI at scale — proving speed and governance aren't in tension. Three years, three BRDs, one defensible platform.
August 17, 2026
Kickoff Date
C. Tyrrell
Program Director
262
People · 25 Teams
$99M
Authorized Investment

## Slide 2
AGENDA
What We'll Cover Today
1
Welcome & Program Context
2
Why Now — Regulatory & Competitive
3
Success — How We Define It
4
Scope — Workstreams & BRDs
5
Teams & Delivery Model
6
Governance — Three Boards, One Framework
7
Timeline & Phase Gates
8
Budget Overview
9
Forecast & Earned Value
10
How We'll Work Together
11
Risks We're Watching
12
Decisions Ratified
13
Next Steps & Q&A
2

## Slide 3
WELCOME
Glad You're Here
262 people across 25 teams start a 36.5-month program today — and everything begins with governance, not code.
Project Catalyst stands up governed, production AI across claims, prior authorization, member experience, and underwriting for ACME Highland Health. Over three years and three BRDs, we prove that speed and governance aren't in tension — the AI Center of Excellence and Independent Model Validation come first, before any model reaches production. Today is Day 1 of Phase 0: readiness assessment, the governance charter, and platform selection.
262
People across 25 teams
$99M
Authorized investment
36.5 mo
Aug 2026 – Aug 2029
3

## Slide 4
THE BUSINESS CASE
Why We're Doing This
Two pressures, one solution: a regulatory mandate with a hard date, and competitors already in production.
CMS-0057-F's prior-authorization mandate takes effect January 2027 — this program authorizes production AI at scale, governed and defensible, beyond the separate baseline-compliance project. Meanwhile UnitedHealth, Humana, and Oscar Health already run production AI across claims, PA, and member engagement. Moving slowly while they deploy is unviable; moving fast without governance is a liability. Catalyst proves the two aren't in tension when governance is built in from Day 1.
KEY FACTS
Regulatory
CMS-0057-F — effective Jan 2027
Competitive
UHG, Humana, Oscar in production
Approach
Governance-first, not retrofit
Payoff
Defensible AI at scale
4

## Slide 5
SUCCESS METRICS
What Success Looks Like
1
Zero Critical/High security findings from the first production release onward
2
Independent Model Validation sign-off on accuracy, fairness & explainability before every production release
3
All three BRDs delivered on time by August 2029, within the $99M authorized baseline — contingency only via change control
4
Measurable operational gains — PA cycle time, call-center handle time, underwriting consistency — benchmarked and tracked
5
AI CoE and governance transitioned to permanent ACME operations at closeout
5

## Slide 6
SCOPE
Where the Lines Are
IN SCOPE
✓
BRD-01 — Claims & Prior-Auth AI
The flagship; Year 1 through to production
✓
BRD-02 & BRD-03 — Experience & Underwriting AI
Member/provider experience + underwriting, Year 2
✓
AI Governance & Center of Excellence
Stood up before any model reaches production
✓
Data & Cloud AI Platform Foundation
The production AI platform all BRDs build on
OUT OF SCOPE (CANDIDATE BACKLOG)
✕
Baseline CMS-0057-F compliance
A separate, smaller project — not this program
✕
Shadow / ad-hoc AI
Any AI outside the governance framework
✕
Use cases beyond the three BRDs
Future portfolio, not authorized here
✕
Autonomous member-facing decisions
Human override required at launch
6

## Slide 7
TEAMS
Everyone Who's Building This
262 people across 25 functional teams — the six delivery workstreams below carry the program; Executive Steering & Governance (9), Program Finance, and the remaining specialist teams complete the org. Full named roster in the Resource Plan.
16
Program Leadership & PMO
Lead: C. Tyrrell, Program Director
12
AI Governance & CoE
Lead: S. Khurana, AI Governance Director
20
Data & Cloud AI Platform
Lead: W. Kumar, Platform Lead
28
Claims & Prior-Auth AI · BRD-01
Flagship — Year 1 to production
22
Member & Provider Experience · BRD-02
Year 2 — parallel delivery
14
Underwriting & Risk AI · BRD-03
Year 2 — parallel delivery
7

## Slide 8
GOVERNANCE
Who Decides What
Three boards, one decision-making framework. Authority is distributed by decision type — business, model risk, and architecture — and no BRD passes a phase gate without sign-off from all three. Governance is stood up before any model reaches production, not retrofitted after.
Exec Steering
Business case, budget, program risk, phase-gate readiness, benefits
Chair: M. Kavanagh — ACME COO / Sponsor
AI Governance
Model risk, responsible AI, validation & fairness testing
Independent Model Validation authority
EA Board
Technical architecture, security, integration, data residency
Enterprise Architecture leadership
Phase Gates
No BRD proceeds without all three boards; no model ships without IMV
All three boards, jointly
8

## Slide 9
TIMELINE
Three Years, Phase-Gated to Production
Sequenced across three years — governance and the platform stand up first, then each BRD is gated to production.
Phase 0 · Foundation
Readiness & governance · Aug–Nov '26
Year 1 · Flagship
BRD-01 to production · to Sep '27
Year 2 · Expansion
BRD-02 + BRD-03 · to Aug '28
Year 3 · Optimize
Benefits & sustain · to Aug '29
Transition & Close
CoE to ACME ops · Aug '29
KEY MILESTONES
Nov 6 '26
Phase 0 gate — readiness & governance v1
Dec '26
BRD-01 requirements locked
Mar '27
Data & cloud platform live
Jun '27
BRD-01 pilot go-live
Sep '27
BRD-01 full production
Aug '29
Program closeout & transition
9

## Slide 10
TIMELINE · DETAIL
Project Phases — Detailed View
The program as a work view — bars show when each workstream runs and where they overlap.
2026
2027 H1
2027 H2
2028
2029
FY
Foundation & Governance
AI Governance & CoE standup
Data & Cloud platform build
BRD-01 JAD & requirements
Year 1 — BRD-01 Flagship
BRD-01 build → pilot
BRD-01 full production
Year 2 — Expansion
BRD-02 Experience AI
BRD-03 Underwriting AI
Year 3 — Optimize & Sustain
Benefits realization
Transition to ACME ops
10

## Slide 11
BUDGET
Where the Money Goes
TOTAL PROGRAM BUDGET $99.0M
Internal FTE Labor (ACME)
$19.6M
Loaded cost of ACME staff assigned to the program
Onshore Consultant Labor (Pulaski)
$27.4M
Billable onshore consulting at contracted rates
Offshore Consultant Labor (Pulaski)
$14.2M
Billable offshore engineering and QA capacity
Cloud & AI Platform Infrastructure
$26.9M
Hyperscaler compute/storage, GenAI inference, MLOps
Tooling & Licenses
$1.9M
Delivery tooling, QA/test automation, observability
Contingency Reserve (ESB-controlled)
$9.0M
Released only against realized risk via change control
Labor is 61.8% of the baseline. By contract year: Y1 $27.72M · Y2 $41.58M (peak) · Y3 $29.70M. Full rate card and quarterly spend plan in the Program Budget.
11

## Slide 12
FORECAST & VARIANCE
How We Forecast — Earned Value, Not Burn-Down
This is a governed, gated program — we manage to an earned-value baseline, not a burn-down.
The $99.0M authorized baseline is the single financial control point. Cost and schedule performance are measured against it at every phase gate, and the $9.0M contingency is ESB-controlled — released only against realized risk through formal change control. At the Week-4 Phase 0 status date, the baseline is unchanged and both performance indices sit at 1.00.
$99.0M
Authorized baseline (BAC) — unchanged
CPI 1.00
On budget · $0 variance at Week 4
$9.0M
Contingency — undrawn, ESB-controlled
12

## Slide 13
WORKING TOGETHER
How We'll Stay in Sync
CADENCE
FORUM
PURPOSE
Weekly
25 Team-Lead Status Sync
Phase-gate readiness, cross-team dependencies, RAIDD-log updates
Monthly
Executive Steering Board
Program health (RAG), budget vs. forecast, risk escalations, benefits
Per gate
Three-Board Gate Review
Exec Steering + AI Governance + EA sign-off — no gate passes without all three
As needed
AI Governance Board
Model validation, fairness, responsible-AI & regulatory escalations
13

## Slide 14
RISKS
Risks and Mitigation
The full register at a glance — each risk with its mitigation, likelihood, and impact; detailed cards follow.
IDENTIFIED RISKS
MITIGATION STRATEGY
LIKELIHOOD
IMPACT
01
Legacy claims data fragmentation
✓
$1.2M remediation contingency pre-approved (D-01)
High
High
02
GenAI compute & token cost overrun
✓
Multi-cloud placement; inference-efficient models
High
High
03
Member chatbot hallucination / liability
✓
RAG — retrieval-constrained generation only
Medium
High
04
PA AI regulatory scrutiny — override rate
✓
Human override + IMV + documented audit trail
Medium
High
14

## Slide 15
RISKS WE'RE WATCHING
Risks We're Watching (1 of 2)
R-01
Legacy claims data fragmentation
LIKELIHOOD HIGH
IMPACT HIGH
ACME's claims data spans four legacy systems with differing formats and identifiers; Phase 0 profiling may show integrating and cleansing it for BRD-01 needs far more effort than estimated.
OWNER T. Valdez / PMO
STATUS Open — highest-attention (Phase 0)
Mitigation: $1.2M data-remediation contingency pre-approved (D-01/CN-001); if exceeded, escalate to ESB with phased-delivery or reduced-dataset options.
R-02
GenAI compute & token cost overrun
LIKELIHOOD HIGH
IMPACT HIGH
Production GenAI inference and LLM token consumption could run materially over the platform budget as usage scales across the BRDs.
OWNER W. Kumar / Platform Lead
STATUS Open — monitored on the platform
Mitigation: Multi-cloud workload placement (D-03/CN-003) — train on cheapest GPU, infer on lowest-cost endpoint meeting latency; inference-efficient model choices per BRD.
15

## Slide 16
RISKS WE'RE WATCHING
Risks We're Watching (2 of 2)
R-03
Member chatbot hallucination / liability
LIKELIHOOD MEDIUM
IMPACT HIGH
BRD-02's member-facing assistant could state incorrect coverage or benefits; precedent (Moffatt v. Air Canada, 2024) holds the org liable for its chatbot's statements.
OWNER S. Khurana / AI Governance
STATUS Open — mitigation designed in
Mitigation: RAG architecture: generation constrained to retrieved, verified source passages only (BRD-02 FR-02.005–008); validated before release.
R-04
PA AI regulatory scrutiny — override rate
LIKELIHOOD MEDIUM
IMPACT HIGH
Regulators may scrutinize prior-auth AI override/denial rates; an unexplained pattern could trigger inquiry or enforcement action.
OWNER Dr. N. Patel / CMO
STATUS Open — governed by design
Mitigation: Human-in-the-loop override protocols, Independent Model Validation, and a documented audit trail evidencing the two-line-of-defense model.
16

## Slide 17
DECISIONS RATIFIED
Decisions We're Starting With
Three decisions are already ratified at program authorization — captured here so no one has to reconstruct them later.
D-01
Up to $1.2M contingency pre-approved (CN-001) for extended Phase 0 data remediation if profiling identifies scope beyond estimate
Executive Steering Board At Charter authorization
D-03
Multi-cloud platform architecture (CN-003) adopted for workload-placement cost and latency optimization
Enterprise Architecture Board At Charter authorization
Charter
Governance-first sequencing ratified — AI CoE + Independent Model Validation stand up before any model reaches production
Exec Steering + AI Governance Boards Charter §, at authorization
17

## Slide 18
NEXT STEPS
What Happens Next
1
Aug 21–22
Mandatory compliance & data-handling briefing for all teams; offshore access controls established by Aug 26
2
Aug 28
BRD-01 JAD series opens — scope, regulatory anchors, data mapping (Legal, Compliance, EA, Cyber, clinical SMEs seated)
3
Aug 31
Executive Steering Board reviews Charter + RAIDD; Phase 0 gate readiness tracked toward Nov 6
18

## Slide 19
QUESTIONS?
Let's build something that sets the gold standard.
C. Tyrrell · Program Director
Project Catalyst
All program artifacts available at ct-pm.pages.dev/ai-transformation/