Program Management Plan (PMP) — Version 1.0

Master Planning Document

Project Catalyst— $99,000,000 AI Transformation Program, ACME Highland Health. This Program Management Plan is the master operational document governing how the program will be executed, monitored, controlled, and closed across 36.5 months (Aug 2026–Aug 2029). It integrates all PMBOK subsidiary management plans plus AI-specific governance, model risk, data privacy, and regulatory compliance plans unique to enterprise AI deployment in regulated healthcare. Approved by Executive Steering Board; updates require formal change control.

Part I — Program Integration & Management Approach

## 1. Introduction & Document Purpose

This Program Management Plan (PMP) is the single authoritative document governing how Project Catalyst will be planned, executed, monitored, controlled, and closed. It integrates all subsidiary management plans — scope, schedule, cost, quality, resource, communications, risk, procurement, and stakeholder — plus three plans unique to enterprise AI deployment in regulated healthcare: AI Governance & Model Risk, Data Governance & Privacy, and Regulatory Compliance. Together, these plans constitute the operational blueprint for a 262-person, $99 million, 36.5-month program.

This PMP operates under the authority of theProgram Charter(approved August 3, 2026) and theProgram Governance Model. It is reviewed at every phase gate and updated through the formal change control process defined in Section 21. No section of this plan may be modified without Executive Steering Board approval and a corresponding entry in theChange Control Log.

### 1.1 Intended Audience

Program Director (C. Tyrrell)— primary owner; executes and enforces all procedures in this plan

PMO Lead (T. Valdez)— day-to-day coordinator; maintains all tracking artifacts referenced here

25 Team Leads— responsible for compliance with the section(s) applicable to their team's work

Executive Steering Board— approves this plan and its updates; reviews status against it at phase gates

AI Governance Board & Enterprise Architecture Board— enforce AI-specific and technical sections

Program Finance (A. Rodriguez)— enforces cost management procedures in Section 8

### 1.2 Related Documents

| Document | Relationship to This PMP |
| --- | --- |
| Program Charter | Authorizing document; defines scope, budget, and executive authority. This PMP operationalizes the Charter. |
| Program Governance Model | Defines decision rights, board composition, and phase-gate sign-off process. Referenced throughout this PMP. |
| RAIDD Log | System of record for risks, assumptions, issues, dependencies, and decisions. This PMP defines how each category is managed. |
| Resource Plan | Complete 262-person named roster. This PMP Section 10 defines staffing management procedures. |
| Organization Chart | Complete reporting structure. This PMP Section 10 defines reporting and matrix coordination procedures. |
| RACI Matrix | Responsibility assignments for 14 key activities. This PMP defines the process behind each RACI entry. |
| Change Control Log | Records all formal changes to baselines. This PMP Section 21 defines the change control process. |
| Communications Plan | Detailed communication matrix. This PMP Section 11 summarizes; full detail in the standalone artifact. |
| AI Governance & JAD Charter | Defines JAD session structure and AI CoE mandate. Referenced in Sections 6, 15, and 17. |
| SOW-01, SOW-02, SOW-03 | Contractual scope and fee schedules for Years 1, 2, 3 respectively. Referenced in Section 8. |

## 2. Program Overview & Strategic Context

Project Catalyst is a three-year enterprise AI transformation program for ACME Highland Health, a national health insurer with approximately 4 million members. The program delivers production AI capabilities across three business requirement documents (BRDs), supported by two cross-cutting workstreams, under a governance-first strategy that embeds responsible AI practices from Day 1 rather than retrofitting compliance post-deployment.

### 2.1 Strategic Drivers

Two converging forces make this program necessary and time-bound:

Regulatory mandate (CMS-0057-F):The CMS prior-authorization interoperability mandate takes effect January 2027. ACME's baseline compliance project (separate from this program) handles minimum regulatory requirements. Project Catalyst authorizes the larger, durable capability: production AI at scale, governed against NIST AI RMF and ISO/IEC 42001, with defensible risk controls that survive regulatory scrutiny.

Competitive pressure:UnitedHealth, Humana, and Oscar Health are already running production AI across claims, prior authorization, and member engagement. ACME's competitive position erodes with every quarter of delayed AI deployment. Moving fast without governance is risky; moving slowly while competitors deploy is unviable. This program proves the two are not in tension when governance is built in from the start.

### 2.2 Program Scope Summary

| Workstream | Type | Scope | Timeline |
| --- | --- | --- | --- |
| BRD-01: Claims & Prior Auth AI | Delivery | Agentic prior-auth automation with mandatory human review of adverse determinations | Year 1 (Aug 2026–Sep 2027) |
| BRD-02: Member & Provider UX AI | Delivery | Conversational AI for member self-service and call-center support with escalation-to-human protocols | Year 2 (Oct 2027–Dec 2028) |
| BRD-03: Underwriting & Risk AI | Delivery | Predictive risk-scoring with mandatory fairness/disparate-impact testing before any model influences pricing | Year 2 (Oct 2027–Dec 2028) |
| AI Governance & CoE | Cross-cutting | Hub-and-spoke governance, NIST AI RMF + ISO/IEC 42001 alignment, enterprise AI standards, shadow-AI prevention | Years 1–3 |
| Data & Cloud AI Platform | Cross-cutting | Shared hyperscaler cloud platform, MLOps pipelines, data governance, FinOps controls | Years 1–3 |

### 2.3 Objectives & Success Criteria

Governance:Zero Critical or High security findings from first production release onward. No model reaches production without clean Independent Model Validation sign-off.

Model Quality:Every production model passes accuracy, fairness, explainability, and security validation. Override/escalation protocols documented and tested for every model type.

Schedule:All three BRDs delivered to production by August 2029 within the phase-gate structure. Schedule changes formalized through change control; no unauthorized acceleration or compression of validation gates.

Budget:Deliver within the $99M authorization. Contingency reserve ($9.0M) used only through formal Executive Steering Board approval with documented root cause.

Benefits Realization:Measurable operational outcomes (PA cycle time reduction, call-center handle-time reduction, underwriting consistency improvement) benchmarked at Phase 0 and tracked against actuals through Year 3 closeout.

Sustainability:AI Governance & CoE, Independent Model Validation, and data privacy functions transitioned to permanent ACME operations at program closeout — governance does not end when consulting ends.

### 2.4 Key Milestones

| Milestone | Target Date | Gate Owner |
| --- | --- | --- |
| Program Kickoff | 17 Aug 2026 | Program Director |
| Phase 0 Gate: Foundation & Readiness | 06 Nov 2026 | Executive Steering Board |
| BRD-01 Requirements Sign-off (JAD Complete) | 18 Dec 2026 | AI Governance Board |
| Phase 1 Gate: Design Approved | 28 Feb 2027 | All 3 Boards |
| Data & Cloud Platform Foundation Go-Live | 31 Mar 2027 | EARB |
| Phase 2 Gate: Build & Testing | 30 Jun 2027 | All 3 Boards |
| BRD-01 Pilot Go-Live | 15 Jul 2027 | AI Governance Board |
| Phase 3 Gate: Production Readiness | 31 Aug 2027 | All 3 Boards |
| BRD-01 Full Production Scale | 30 Sep 2027 | Executive Steering Board |
| Year 2 Kickoff (BRD-02/03) | 01 Oct 2027 | Program Director |
| BRD-02 Production Go-Live | 30 Sep 2028 | All 3 Boards |
| BRD-03 Production Go-Live | 31 Dec 2028 | All 3 Boards |
| Year 3: Optimization & Sustain | Jan–Aug 2029 | Program Director |
| Program Closeout & Transition Complete | 29 Aug 2029 | Executive Steering Board |

## 3. Management Approach & Delivery Methodology

Project Catalyst uses ahybrid delivery methodologythat combines phase-gated governance (waterfall structure for program-level oversight, phase gates, and regulatory sign-offs) with agile execution within each BRD delivery workstream (sprint-based development, continuous integration, iterative model training). This is not a concession; it is deliberate: regulated healthcare AI requires documented phase gates for audit and compliance, while the AI/ML development work itself requires the iterative feedback loops that only agile execution provides.

### 3.1 Program-Level Governance (Phase-Gated)

Five formal phase gates per BRD cycle (Phase 0 through Phase 4), each requiring concurrent sign-off from all three governance boards

Phase-gate packages prepared by Program Director, tabled 7 business days before gate date

No phase advancement without documented sign-off; gate rejection requires remediation plan with re-gate date

Charter, RAIDD Log, and Change Control Log updated at every gate

### 3.2 BRD-Level Execution (Agile/Sprint-Based)

Each BRD delivery team operates in 2-week sprints with its own Scrum Master, Product Manager, and backlog

Sprint ceremonies: Daily standup (15 min), Sprint Planning (Day 1, 90 min), Backlog Refinement (mid-sprint, 60 min), Sprint Review/Demo (last day, 45 min), Sprint Retrospective (last day, 45 min)

Cross-BRD coordination via Scrum-of-Scrums (2×/week, 15 min: Program Director + Scrum Masters + Platform Lead)

Sprint velocity tracked per team; burndown charts maintained and reported in monthly status reports

Definition of Ready and Definition of Done established per BRD at Phase 1 and maintained through program lifecycle

### 3.3 Integration Points Between Governance and Agile

The hybrid model's critical integration points are where sprint-level work must pause for governance review:

Model Validation Gate:No trained model advances from sprint-level development to production without independent validation. The sprint team delivers a model to the validation queue; the validation team (P. Okafor) operates on its own cadence (typically 5–10 business days per model review). Sprint planning accounts for this handoff.

Phase-Gate Freeze:During the 7 business days before a phase gate, no new sprint work is started that would change the gate package. Teams use this period for documentation, test completion, and defect remediation.

JAD-to-Sprint Handoff:Requirements locked at JAD sign-off become the Product Backlog seed. The Product Manager decomposes JAD requirements into Epics and Features; team decomposes Features into Stories during Sprint 0.

## 4. Phase Structure & Gate Process

### 4.1 Phase Definitions

| Phase | Duration | Purpose | Key Deliverables | Gate Criteria |
| --- | --- | --- | --- | --- |
| Phase 0Foundation | 12 weeks(Aug–Nov 2026) | Assess readiness, stand up governance, select vendors, mobilize team | AI Readiness Assessment, CoE Charter, Governance Framework v1, Platform vendor BAA, Team onboarding | All readiness criteria met; governance framework approved; platform vendor signed; Phase 1 resource plan confirmed |
| Phase 1Requirements & Design | 12 weeks(Nov 2026–Feb 2027) | Complete JAD series, lock requirements, approve architecture | BRD requirements document (signed), Target architecture, Model validation criteria, Security threat model | Requirements signed by all JAD attendees; architecture approved by EARB; model validation protocol set |
| Phase 2Build & Test | 16 weeks(Feb–Jun 2027) | Build platform, develop models, execute testing | Platform Foundation live, BRD-01 model development complete, UAT environment ready, Sprint velocity stabilized | Platform operational; model build >80% complete; UAT environment provisioned; quality metrics on track |
| Phase 3Pilot & Pre-Production | 8 weeks(Jun–Aug 2027) | Controlled pilot, model validation, production readiness | Pilot Go-Live with controlled user group, Pilot UAT (>95% pass rate), Model Validation Report (clean), Production readiness assessment | Pilot UAT passed; model validation clean (zero Critical, zero uncorrected High); production readiness approved |
| Phase 4Production Scale | 4 weeks(Sep 2027) | Full-scale production deployment, benefits tracking setup | BRD-01 full production live, Benefits tracking baseline, Year 2 scope approved, Hypercare plan activated | Production stable for 2+ weeks; benefits baseline established; Year 2 BRD-02/03 scope approved |

### 4.2 Phase-Gate Sign-Off Procedure

This procedure is mandatory and invariant across all phase gates:

T minus 7 business days — Package Submission:Program Director submits the phase-gate package to all three board chairs. Package contents: executive summary (2 pages), deliverable completion matrix (with evidence), risk assessment update (RAIDD Log delta since last gate), resource plan for next phase, budget forecast vs. actual, quality metrics summary. Package is uploaded to the project portal and notification sent to all board members.

T minus 5 to T minus 1 — Board Review:Each board reviews the package independently. Board chairs submit written questions or concerns to Program Director no later than T minus 2. Program Director responds in writing before the gate meeting; responses are appended to the gate package for the record.

Gate Day — Gate Meeting:2-hour meeting with all three boards present (minimum quorum: chair + 1 additional member from each board). Program Director presents the package (30 min), followed by Q&A (45 min), followed by board deliberation (30 min). Each board votes independently: Approve, Approve with Conditions, or Reject.

T plus 1 — Sign-Off Record:PMO Lead documents the gate decision in the Phase-Gate Record: deliverables accepted (enumerated list), risks re-assessed (updated RAIDD Log entries), next-phase budget approved (amount), next-phase team leads confirmed (names). Record is archived in the project portal as an immutable document. Distribution to all 25 team leads within 24 hours.

Gate Rejection Protocol:If any board votes Reject, the phase gate is not passed. Program Director has 5 business days to produce a remediation plan addressing the board's specific objections. Remediation plan is reviewed at a reconvened gate meeting (1 hour). If the rejection is sustained, escalation to Executive Sponsor. In the program's history, no gate rejection has occurred, but the protocol exists because governance without enforcement is theater.

Part II — Subsidiary Management Plans (PMBOK Knowledge Areas)

## 5. Scope Management Plan

Scope is defined through the five-workstream structure in Section 2.2 and controlled through the WBS (to be published in the Multi-Year WBS Console). The scope baseline is the set of deliverables committed at Charter sign-off, refined through JAD sessions (Phase 0/1), and locked at the Phase 1 gate for each BRD.

### 5.1 Scope Definition

Program-level scope is defined in theProgram CharterSections 4–6 (vision, objectives, five workstreams).

BRD-level scope is developed through JAD sessions (seeAI Governance & JAD Charter) and locked at requirements sign-off.

Each BRD requirements document is decomposed into a WBS by the BRD Lead and Product Manager during Sprint 0.

### 5.2 Scope Validation

Each phase gate requires formal business and technical sign-off on deliverables completed in that phase.

Deliverable acceptance criteria are defined in the phase-gate package (Section 4.2) and verified against the requirements traceability matrix before gate submission.

UAT sign-off is the final scope validation step before production release — it confirms that what was built matches what was specified.

### 5.3 Scope Control

Scope changes are logged as change requests and processed through the change control process (Section 21).

Any request that adds, removes, or materially alters a deliverable defined in a signed BRD requirements document is classified as a scope change, regardless of estimated effort or cost.

Scope changes >5% of BRD value-at-risk require Executive Steering Board approval. Scope changes affecting model governance or validation criteria require AI Governance Board approval.

Shadow AI prevention (RAIDD R-10): Any AI initiative identified outside the program's governance perimeter is evaluated by the AI CoE within 10 business days; disposition is fold-in, defer, or reject (see Section 15.4).

## 6. Requirements Management Plan

Requirements are distinct from scope: scope defines what the program delivers; requirements define the specific functional, non-functional, and regulatory conditions those deliverables must satisfy.

### 6.1 Requirements Gathering

Requirements are gathered through structured JAD sessions with 8 mandatory attendees (seeJAD CharterSection 02). Each session is 2–3 hours, facilitated by the Program Director.

Requirements are captured in the BRD requirements document using a standard template: requirement ID, description, business justification, priority (MoSCoW: Must/Should/Could/Won't this phase), acceptance criteria, regulatory traceability (if applicable).

For AI model requirements specifically, each requirement must include: model type (classification/regression/generative), expected input/output, performance threshold (accuracy, latency), fairness criteria, human-override protocol, and explainability standard.

### 6.2 Requirements Prioritization

MoSCoW prioritization is applied during JAD consolidation workshops. "Must have" requirements are non-negotiable for the current phase; "Should have" are expected but can be deferred with documented justification; "Could have" are included if capacity allows; "Won't have this phase" are explicitly deferred.

Regulatory requirements (CMS-0057-F compliance, NIST AI RMF alignment, state AI-in-insurance mandates) are always classified as "Must have" regardless of effort estimate.

### 6.3 Requirements Traceability

A Requirements Traceability Matrix (RTM) links each requirement to: its JAD session origin, its WBS element(s), its design artifact, its test case(s), and its UAT scenario. The RTM is maintained by the BRD Lead and reviewed at each phase gate.

No requirement may be marked "complete" without at least one linked test case that has passed. This is verified automatically through the testing tool integration; manual overrides require QA Lead approval with documented justification.

### 6.4 Requirements Change After Baseline

Requirements are baselined at JAD sign-off (Phase 1 gate). Changes after baseline are treated as scope changes and processed through formal change control (Section 21).

Emergency requirements changes (e.g., regulatory mandate shift, critical defect requiring re-specification) follow an expedited 48-hour review by the relevant board, with retrospective documentation in the Change Control Log.

## 7. Schedule Management Plan

The schedule baseline spans 36.5 months from Kickoff (17 Aug 2026) to Closeout (29 Aug 2029), organized into the five-phase structure defined in Section 4.1, with Year 2 and Year 3 phases following the same gate rhythm.

### 7.1 Schedule Development

Program-level schedule is maintained in the Program Plan Console (to be published as the Multi-Year WBS Console) by the Senior Scheduler (M. Torres).

Phase-gated milestones use finish-to-start dependencies: Phase 1 cannot begin until Phase 0 gate is passed; Platform Foundation must be live before BRD-01 model build accelerates (dependency DEP-03 in RAIDD Log).

BRD-level schedule is maintained in 2-week sprint increments by each BRD's Scrum Master, with sprint velocity tracked and reported.

### 7.2 Schedule Contingency

A schedule contingency buffer of 5% is held at the program level — approximately 9 weeks across the 36.5-month program, allocated to absorb minor slippage without requiring Executive Steering Board escalation.

If cumulative schedule slippage exceeds 2 weeks on any single BRD, Program Director escalates to the relevant board with a recovery plan within 5 business days.

Critical path activities are identified and monitored weekly. Any critical-path activity that falls behind plan by >3 business days triggers an immediate working-group session (Program Director + affected BRD Lead + PMO Lead).

### 7.3 Schedule Performance Monitoring

Schedule variance (SV) and Schedule Performance Index (SPI) are calculated monthly against the schedule baseline.

SPI threshold: Green (SPI ≥ 0.95), Yellow (SPI 0.85–0.94), Red (SPI < 0.85).

Yellow status triggers a recovery plan from the BRD Lead within 5 business days. Red status triggers Executive Steering Board escalation with options analysis (compress, descope, extend, add resources).

Sprint velocity is tracked per BRD team and reported in monthly status reports. Velocity trend is used to forecast completion dates; if forecast completion date exceeds the phase-gate target by >2 weeks, the BRD Lead must submit a schedule change request.

## 8. Cost Management Plan

### 8.1 Budget Baseline

| Cost Category | Amount | % of Total |
| --- | --- | --- |
| Internal FTE Labor | $19,600,000 | 19.8% |
| Onshore Consultant Labor | $27,400,000 | 27.7% |
| Offshore Consultant Labor | $14,200,000 | 14.3% |
| Cloud & AI Platform Infrastructure | $26,900,000 | 27.2% |
| Tooling (Governance, Compliance, Testing) | $1,900,000 | 1.9% |
| Contingency Reserve | $9,000,000 | 9.1% |
| TOTAL | $99,000,000 | 100% |

### 8.2 SOW Fee Schedule

| SOW | Period | Total Fee | % of Total |
| --- | --- | --- | --- |
| SOW-01 (Year 1: Foundation & Flagship) | Aug 2026 – Sep 2027 | $27,720,000 | 28% |
| SOW-02 (Year 2: Expansion) | Oct 2027 – Dec 2028 | $41,580,000 | 42% |
| SOW-03 (Year 3: Optimization & Sustain) | Jan 2029 – Aug 2029 | $29,700,000 | 30% |
| TOTAL |  | $99,000,000 | 100% |

### 8.3 Cost Tracking & Variance Management

Monthly tracking:Program Finance (A. Rodriguez) tracks actual spend against budget by cost category on a monthly basis. Variance report delivered to Program Director by the 10th business day of each month.

Variance thresholds:Cumulative variance >5% in any cost category triggers an investigation report from Program Finance. Monthly variance >10% in any category triggers Executive Steering Board escalation with root-cause analysis and corrective action plan.

Earned Value:Cost Performance Index (CPI) and Cost Variance (CV) calculated monthly (see Section 22). CPI threshold: Green (CPI ≥ 0.95), Yellow (CPI 0.85–0.94), Red (CPI < 0.85).

Forecast accuracy:Estimate at Completion (EAC) recalculated quarterly using the formula EAC = BAC / CPI. If EAC exceeds the $99M authorization by >$1M, the Program Director prepares an options analysis for the Executive Steering Board: descope, extend timeline, draw contingency, or request additional funding.

### 8.4 Contingency Reserve Management

The $9.0M contingency reserve (approximately 10% of total budget) is governed by the following rules:

Contingency is not discretionary overhead. It exists to absorb identified risks that materialize — not to fund scope growth, nice-to-haves, or unplanned initiatives.

Any drawdownup to $500Krequires Program Director + CFO joint approval, documented in the Change Control Log.

Any drawdown$500K–$1Mrequires Executive Steering Board approval.

Any drawdown>$1Mrequires Executive Sponsor direct approval with formal presentation of root cause, alternatives considered, and payback timeline.

If the contingency reserve drops below $2.0M remaining, the Program Director issues a formal risk escalation to the CFO and Executive Sponsor, regardless of whether the drawdowns were individually approved.

Anticipated contingency uses (from RAIDD Log): data remediation (R-01, up to $1.2M pre-approved via CN-001), compute cost overrun (R-02, FinOps controls in place), and staffing increases for adoption resistance (R-07).

## 9. Quality Management Plan

### 9.1 Quality Philosophy

Quality on this program has two distinct dimensions:software quality(does the system work as designed?) andmodel quality(does the AI model produce accurate, fair, explainable, and safe outputs?). Both dimensions require different testing approaches, different competencies, and different sign-off authorities. This plan addresses both.

### 9.2 Software Quality Standards

Unit Testing:Minimum 80% code coverage for all production code. Automated, run on every commit via CI/CD pipeline.

Integration Testing:End-to-end testing across system boundaries (claims system ↔ AI model ↔ notification engine). Automated where feasible; manual for complex multi-system flows.

Performance Testing:Load and stress testing against production-equivalent volumes. Latency threshold: P95 response time ≤ 2 seconds for synchronous API calls; ≤ 30 seconds for batch PA decisions.

Security Testing:OWASP Top 10 scan, penetration testing, and adversarial-input testing (specific to AI models). Conducted by Cybersecurity team (M. Hassan) independently of delivery teams.

DR/BCP Testing:Disaster recovery test executed once per phase (minimum), with documented recovery time against RTO/RPO targets.

### 9.3 AI Model Quality Standards

Blocking Gate:No AI model advances to production without passing all five model validation criteria below. This is not advisory — Independent Model Validation (P. Okafor) has formal blocking authority. See Section 15 for the full AI Governance & Model Risk Management Plan.

Accuracy Testing:Model performance evaluated against a ground-truth benchmark dataset. Accuracy threshold set per model type during Phase 1 (e.g., PA decision accuracy ≥ 92% on benchmark; member chatbot factual accuracy ≥ 97% on policy questions).

Fairness / Disparate-Impact Testing:Model outputs tested for disparate impact across demographic groups (age, gender, geography, plan type). Threshold: no demographic group's approval/denial rate deviates >5% from the population mean without documented clinical justification.

Explainability Review:Model outputs must be interpretable — for every PA decision, the system must produce a human-readable explanation of the factors that drove the decision. Black-box models without explainability are rejected.

Security Testing (Model-Specific):Adversarial input testing (prompt injection, data poisoning, model inversion), data exfiltration resistance, and output sanitization. Conducted by Cybersecurity team in coordination with Model Validation.

Regulatory Compliance Check:Override/escalation protocols verified (mandatory human review for adverse PA determinations), audit logging confirmed (every model decision traceable), and regulatory anchors validated (CMS-0057-F alignment for BRD-01, NAIC model bulletin alignment for BRD-03).

### 9.4 Quality Metrics & KPIs

| Metric | Target | Measurement Frequency | Owner |
| --- | --- | --- | --- |
| Code Coverage | ≥ 80% | Per commit (automated) | BRD Lead |
| Sprint Defect Escape Rate | < 5% of stories | Per sprint | QA Lead (V. Müller) |
| UAT Test Case Pass Rate | ≥ 95% before production | Per UAT cycle | Operational Testing Manager |
| Model Validation Defect Count | Zero Critical, Zero uncorrected High | Per model validation cycle | P. Okafor |
| P95 API Latency | ≤ 2 seconds | Continuous (monitoring) | Platform Lead (W. Kumar) |
| Security Scan Findings | Zero Critical, Zero High at release | Per release candidate | CISO (M. Hassan) |
| Fairness Deviation | ≤ 5% from population mean | Per model validation cycle | P. Okafor |

### 9.5 User Acceptance Testing (UAT)

UAT is owned by a dedicated Operational Testing Manager (Y. Sorensen6), who reports independently — not through the delivery team chain. This independence prevents delivery pressure from compressing UAT timelines or lowering acceptance thresholds.

UAT participants (11 people) are loaned from operational business units: Claims, Customer Service, Underwriting, and Provider Relations. They test the system as end users, not as QA engineers.

UAT criteria are defined by business SMEs during Phase 1 and validated against the requirements traceability matrix. UAT sign-off is required before production rollout — this is a blocking gate.

UAT cycle is 4–6 weeks per BRD. Defects found during UAT are classified by severity (Critical/High/Medium/Low). UAT sign-off requires zero open Critical or High defects.

## 10. Resource Management Plan

### 10.1 Staffing Summary

Total program roster:262 people across 25 functional teams. Not concurrent headcount; staffing ramps by phase. Peak Year 1: approximately 120 active. Complete named roster with role, location, allocation, rate, and cost inResource PlanandOrganization Chart.

| Category | Count | Annual Labor Cost |
| --- | --- | --- |
| ACME FTE (non-billable to Pulaski SOW) | ~140 people | $19,600,000 |
| Pulaski Onshore Consultant | ~75 people | $27,400,000 |
| Pulaski Offshore Consultant | ~47 people | $14,200,000 |
| Total | 262 | $61,200,000 |

### 10.2 Staffing Ramp & Phase Allocation

Phase 0 (Months 1–3):~80 people active — PMO, governance teams, platform leads, JAD participants. Delivery teams not yet fully mobilized.

Phase 1–2 (Months 4–10):~120 people active — full BRD-01 delivery team, platform team, QA ramp-up. Offshore ramp begins.

Phase 3–4 (Months 11–14):~120 people — peak delivery. UAT team activated. Post-production, BRD-01 delivery team begins transition to sustain mode.

Year 2 (Months 15–29):~180 people at peak — BRD-02 and BRD-03 teams fully mobilized while BRD-01 sustain team continues. Largest concurrent headcount.

Year 3 (Months 30–37):~100 people — optimization, sustain, knowledge transfer, closeout. Pulaski consultants begin roll-off. ACME FTEs transition to permanent operations.

### 10.3 Team Lead Assignments & Reporting

All 25 team leads are named in theResource Planwith their organizational affiliation (ACME FTE or Pulaski consultant). Reporting structure:

Solid-line authority:Executive Board → Program Director (C. Tyrrell). This is the real contractual authority chain.

Dotted-line coordination:Program Director → all 25 team leads. Christian coordinates; he does not directly manage. Each team lead has a solid-line boss in their home organization (ACME department head or Pulaski engagement manager).

ACME FTE non-billable leads (14):Their time is "borrowed" from their home departments. Their allocation percentages (typically 15%–40% for executives, 80%–100% for dedicated staff) reflect the realistic share of their time committed to this program.

Pulaski consultant leads (11):Fully billable to the SOW. Roll off at program closeout or when their deliverable is complete.

### 10.4 Onboarding & Offboarding

Onboarding:All team members complete mandatory compliance & data-handling briefing before accessing program systems. Offshore personnel complete additional data-residency briefing. Onboarding packets issued by PMO; completion tracked.

Offboarding:Knowledge transfer checklist required for any team lead departure. Successor identified and briefed before departure. Access revoked within 24 hours of last day. If a team lead departs mid-phase, a replacement must be named within 10 business days — this is a resource change requiring formal notification to the relevant board.

Resource change thresholds:Changes >5 FTEs or >2 team lead replacements require formal change control (Section 21).

## 11. Communications Management Plan

Full communications matrix is maintained in theCommunications Plan. This section summarizes the management approach.

### 11.1 Communication Cadence

| Communication | Frequency | Owner | Audience | Format |
| --- | --- | --- | --- | --- |
| Program Status Sync | Weekly | C. Tyrrell | PMO Lead + 25 team leads | Meeting (1 hr) + written summary |
| Executive Steering Board | Bi-weekly + phase gates | M. Kavanagh | Board members | Meeting (1.5 hrs) + scorecard |
| AI Governance Board | Bi-weekly + model reviews | S. Khurana | Board members | Meeting (1 hr) + model review packet |
| Enterprise Architecture Review | Weekly (build phases) | D. Chen | EARB + BRD leads | Meeting (1 hr) |
| Monthly Program Status Report | Monthly | C. Tyrrell | Executive Steering Board | Written report (10 pages) + dashboard |
| Program Newsletter | Monthly | B. Sullivan | All ACME staff impacted | Email newsletter |
| Quarterly Risk Review | Quarterly | All 3 boards | RAIDD stakeholders | Working session (2 hrs) |
| Board-Level Update | Quarterly | M. Kavanagh | ACME Board of Directors | Executive briefing (30 min) |

### 11.2 Escalation Communications (Mandatory, Time-Bound)

| Trigger | Notification Window | Owner | Notified Parties |
| --- | --- | --- | --- |
| Model Validation Critical/High finding | Within 24 hours of finding | P. Okafor | AI Governance Board, BRD Lead, Program Director |
| Hallucination or bias incident in production | Within 24 hours of detection | S. Khurana | AI Governance Board, Executive Sponsor, General Counsel |
| Regulatory inquiry or scrutiny | Immediately upon receipt | R. Thorne | Executive Steering Board, AI Governance Board |
| Security breach or data exposure | Within 4 hours of detection | M. Hassan | Executive Sponsor, General Counsel, Chief Privacy Officer |
| Budget variance >10% in any category | Within 48 hours of identification | A. Rodriguez | Program Director, CFO, Executive Steering Board |
| Schedule slippage >2 weeks on critical path | Within 48 hours of identification | M. Torres | Program Director, affected Board |

### 11.3 Stakeholder Information Needs

Executive Sponsors:Need program health at a glance (dashboard), budget status, risk escalations, and board-level talking points. Do not need sprint-level detail.

Team Leads:Need phase-gate readiness, cross-team dependency status, resource changes, and RAIDD Log updates. Need sprint-level detail for their own team.

External Regulators (when briefed):Need governance framework summary, model validation methodology, audit trail demonstrations, and compliance posture. Do not receive budget, staffing, or vendor details.

ACME Board of Directors:Need strategic progress summary, risk exposure, competitive positioning impact, and financial status. Briefed through Audit Committee liaison (A. Thompson).

## 12. Risk Management Plan

TheRAIDD Logis the system of record for all risks, assumptions, issues, dependencies, and decisions. This section defines the management process.

### 12.1 Risk Identification

Initial risk identification occurs at Phase 0 (pre-program kickoff). The program starts with 10 identified risks (R-01 through R-10), each with named owner, probability/impact score, and mitigation strategy.

New risks may be identified at any time by any team member. The risk is submitted to the Risk & Issues Coordinator (V. Patel), who logs it in the RAIDD Log within 24 hours and assigns a preliminary score and owner.

Quarterly Risk & Assumption Review (all 3 boards) is the formal mechanism for comprehensive risk re-assessment — but risks that emerge between quarterly reviews are logged immediately, not held.

### 12.2 Risk Assessment

Risks are assessed on a 1–9 scale (Probability × Impact), each dimension rated Low (1), Medium (2), or High (3):

|  | Impact: Low (1) | Impact: Medium (2) | Impact: High (3) |
| --- | --- | --- | --- |
| Prob: High (3) | 3 | 6 | 9 |
| Prob: Medium (2) | 2 | 4 | 6 |
| Prob: Low (1) | 1 | 2 | 3 |

Score interpretation:1–3 Low(monitor) ·4–6 Medium(active mitigation) ·7–9 High(escalate to board within 48 hours).

### 12.3 Risk Response Strategies

Avoid:Eliminate the risk by changing the plan (e.g., switch vendor, adjust scope). Requires change control.

Mitigate:Reduce probability or impact (e.g., dual-source qualification for R-01, FinOps guardrails for R-02). Most common response on this program.

Transfer:Shift impact to a third party (e.g., vendor contractual liability clauses for R-05). Requires Legal review.

Accept:Acknowledge and monitor. Used for low-score risks or risks where mitigation cost exceeds impact. Requires documented justification.

### 12.4 Risk Monitoring & Escalation

Risk owners update their assigned risks weekly in the RAIDD Log. Stale entries (>2 weeks without update) are flagged by the PMO and escalated to Program Director.

If a risk's probability or impact changes materially (moves to a different quadrant in the assessment matrix), the owner notifies the Program Director and the relevant board within 48 hours.

A risk that materializes becomes an Issue (logged in the RAIDD Issue section with owner, target resolution date, and status).

### 12.5 AI-Specific Risk Categories

Beyond standard program risks, this program carries risk categories unique to enterprise AI deployment:

Model accuracy degradation:Production model performance drifts over time as data distribution shifts. Monitored via automated model-performance dashboards; retraining trigger thresholds defined per model during Phase 1.

Hallucination/factual error:Generative AI models produce incorrect or harmful outputs. Precedent:Moffatt v. Air Canada. Mitigated by mandatory human-in-the-loop for adverse determinations and real-time output monitoring.

Bias/fairness violation:Model outputs exhibit disparate impact across protected classes. Mitigated by mandatory pre-production fairness testing (Section 9.3) and ongoing production monitoring.

Adversarial attack:Hostile actors manipulate model inputs to produce desired (incorrect) outputs. Mitigated by adversarial testing during validation (Section 9.3) and runtime input sanitization.

Shadow AI:Departments deploy AI outside the program's governance perimeter. Mitigated by quarterly architecture reviews and CoE authority to fold in or defer non-compliant initiatives (RAIDD R-10).

## 13. Procurement & Vendor Management Plan

### 13.1 Vendor Landscape

Project Catalyst relies on three categories of external vendors:

Hyperscaler Cloud Provider(s):AWS, GCP, and/or Azure for compute, storage, and managed AI/ML services. Multi-cloud strategy adopted (Change Control CN-003) to reduce single-vendor lock-in.

LLM / AI Model Provider(s):OpenAI, Anthropic, or comparable provider for foundation model access (inference and fine-tuning). BAA required; data residency requirements apply.

SaaS Tooling Vendors:Governance, compliance monitoring, test automation, and MLOps tooling. Evaluated during Phase 0; contracts executed with standard SLAs.

### 13.2 Vendor Governance

Vendor Manager (L. Park, Pulaski):Owns day-to-day vendor relationships, SLA tracking, and escalation. Reports vendor performance monthly to Program Director.

Vendor Performance Reviews:Monthly for hyperscaler and LLM providers; quarterly for SaaS tooling. Reviews cover: uptime vs. SLA, support ticket resolution time, cost vs. forecast, and contract compliance.

BAA Requirements:All vendors handling PHI must execute a Business Associate Agreement before accessing any program data. BAA status tracked by Legal (S. Patel, Vendor Contract Specialist).

Vendor Contingency:For single-source vendors (LLM providers), a documented contingency plan exists identifying alternative providers and the estimated switching cost/timeline. Updated annually or when the vendor landscape changes materially.

### 13.3 Procurement Thresholds

| Procurement Value | Approval Authority |
| --- | --- |
| < $50,000 | Program Director |
| $50,000–$500,000 | Program Director + CFO |
| $500,000–$2,000,000 | Executive Steering Board |
| > $2,000,000 | Executive Sponsor + CFO + Legal |

## 14. Stakeholder Engagement Plan

### 14.1 Stakeholder Identification & Classification

| Stakeholder Group | Influence | Interest | Engagement Strategy |
| --- | --- | --- | --- |
| ACME Board of Directors | High | Medium | Keep satisfied: quarterly briefings, no operational detail |
| Executive Steering Board | High | High | Manage closely: bi-weekly meetings, phase-gate sign-off, budget oversight |
| State Regulators / CMS | High | Medium | Keep satisfied: quarterly compliance briefings, proactive transparency |
| Frontline Operations Staff | Low | High | Keep informed: monthly newsletters, phased rollout, change management support |
| Members / Patients | Low | Medium | Monitor: indirect impact; quality and fairness testing protects their interests |
| IT Operations Team | Medium | High | Manage closely: weekly architecture reviews, platform transition planning |
| Pulaski Consulting Leadership | Medium | High | Manage closely: monthly delivery reviews, SOW performance tracking |

### 14.2 Stakeholder-Specific Risks

Frontline adoption resistance (RAIDD R-07):Operational staff may resist AI tools due to job-displacement concerns, trust issues, or workflow disruption. Mitigated by phased opt-in rollout, change management investment, and internal comms framing AI as augmentation (not replacement).

Executive sponsor turnover (RAIDD R-09):If M. Kavanagh departs mid-program, replacement sponsor may not prioritize AI investment. Mitigated by documented governance charter and phase-gate authority (governance survives individual sponsor changes).

Regulatory relationship:Proactive engagement with state regulators and CMS is preferred over reactive responses. Quarterly briefings (R. Thorne) are designed to build trust and demonstrate governance maturity before any regulatory inquiry.

Part III — AI-Specific Management Plans

## 15. AI Governance & Model Risk Management Plan

This section defines the AI-specific governance and model risk management framework that sits on top of — and is enforced through — the standard program governance structure. It is the single most important differentiator between this program and a conventional IT project: every decision about model design, training data, validation methodology, and production release is governed here.

### 15.1 Two-Line-of-Defense Model Risk Structure

First Line — AI Governance & CoE (S. Khurana, 12 people):Embedded in delivery. Sets enterprise AI standards (NIST AI RMF, ISO/IEC 42001 alignment), reviews model design at JAD sessions, defines fairness and explainability requirements per model type, manages model documentation (model cards, data lineage, training methodology), and operates the shadow-AI prevention process. The CoE is a working team, not a rubber-stamp committee.

Second Line — Independent Model Validation (P. Okafor, 6 people):Deliberately separate from delivery teams. Reports to the AI Governance Board, not to BRD leads. Tests every model against accuracy, fairness, explainability, security, and regulatory compliance criteria before production release. Has formal blocking authority: a model rejected by validation does not go to production regardless of schedule pressure.

Why two lines?A single team that both designs and validates AI models has an inherent conflict of interest — schedule pressure incentivizes passing models that should be held for further work. The deliberate separation between CoE (first line, advisory, embedded) and Validation (second line, independent, blocking) eliminates this conflict. This structure is modeled on financial services regulatory practice (OCC model risk guidance) adapted for healthcare AI.

### 15.2 Model Lifecycle Governance

Every AI model on this program follows a governed lifecycle with defined checkpoints:

Concept & Design (Phase 1):Model concept reviewed at JAD sessions. CoE reviews model type selection, training data assumptions, fairness criteria, and human-override protocol design. Output: approved model design document.

Development & Training (Phase 2):Model developed by BRD delivery team using approved design. CoE conducts interim reviews of training data quality, feature engineering decisions, and preliminary accuracy metrics. Output: trained model ready for validation.

Independent Validation (Phase 3):Model submitted to Independent Model Validation. Validation runs the five-criteria assessment defined in Section 9.3. Output: validation report with findings classified as Critical/High/Medium/Low. Critical or uncorrected High findings = model rejected.

Pilot Deployment (Phase 3):Validated model deployed to controlled pilot environment with limited user group. Pilot duration: minimum 4 weeks. Monitored for accuracy drift, fairness drift, and operational workflow integration. Output: pilot results report.

Production Release (Phase 4):Model deployed to full production with ongoing monitoring. Retraining triggers defined (accuracy drift >X%, fairness deviation >Y%, data distribution shift >Z%). Output: production model with monitoring dashboard.

Ongoing Monitoring & Retraining (Year 2–3):Production models monitored continuously. If retraining trigger is hit, model re-enters the validation cycle at step 3 — no production model is updated without re-validation. CoE reviews retraining cadence quarterly.

### 15.3 Responsible AI Standards

Transparency:Every model decision must be explainable in human-readable terms. For PA decisions: the system must produce a plain-language explanation of the factors that drove the approval or denial. For underwriting: the system must identify the top 5 risk factors and their relative weight.

Human-in-the-Loop:Mandatory human review for all adverse PA determinations (BRD-01). Mandatory human review for underwriting decisions that fall within defined edge-case bands (BRD-03). Human escalation path for member chatbot (BRD-02) when confidence score falls below threshold.

Audit Trail:Every model decision is logged with: timestamp, input data hash, model version, output decision, confidence score, and (for PA decisions) whether human review was triggered. Logs retained per ACME's data retention policy (minimum 7 years for healthcare records).

Regulatory Anchors:CMS-0057-F (prior-auth interoperability, Jan 2027), NIST AI RMF 1.0, ISO/IEC 42001, NAIC Model AI Bulletin, state AI-in-insurance statutes. CoE maintains a regulatory tracker updated quarterly.

### 15.4 Shadow AI Prevention

The AI CoE conducts a quarterly architecture review to identify AI or ML initiatives operating outside the program's governance perimeter (RAIDD R-10).

Identified initiatives are evaluated within 10 business days. Disposition options: fold into program governance (with resource and scope adjustment), defer to post-program, or reject (with documentation of why).

Persistent non-compliance after notification is escalated to the Executive Sponsor. The CoE has authority to recommend that non-compliant projects be suspended until governance alignment is achieved.

## 16. Data Governance & Privacy Management Plan

### 16.1 Data Classification & Handling

PHI (Protected Health Information):Claims data, member health records, PA decisions, clinical notes. Handled exclusively in onshore US environments. Offshore resources do not access PHI — this is a design constraint, not an operational workaround (RAIDD R-08).

PII (Personally Identifiable Information):Member name, address, DOB, contact information. Encrypted at rest and in transit. Access restricted by role-based access control (RBAC).

Model Training Data:De-identified and anonymized per HIPAA Safe Harbor or Expert Determination method before use in model training. Data Privacy Office (E. Sato) reviews de-identification methodology before any dataset is approved for model training.

Model Output Data:PA decisions, member interactions, underwriting scores. Subject to the same retention and audit requirements as the input data that drove them.

### 16.2 Data Residency Architecture

All PHI-containing data resides exclusively in US-based cloud regions. No PHI is stored, processed, or accessible in non-US jurisdictions.

Offshore development teams work with synthetic/anonymized datasets for model training and testing. Real PHI is never exposed to offshore environments.

Data residency architecture is reviewed and approved by the Enterprise Architecture Board (D. Chen) and Chief Privacy Officer (E. Sato) at Phase 0 and re-validated at each annual review.

### 16.3 Privacy Impact Assessment

A Privacy Impact Assessment (PIA) is conducted for each BRD before model development begins. The PIA evaluates: data elements used, consent basis, de-identification adequacy, access controls, retention period, and breach notification obligations.

PIA is owned by the Data Privacy Office, reviewed by Legal, and approved by the AI Governance Board.

Material changes to data handling (new data elements, new use cases, new vendor access) trigger a PIA update.

## 17. Regulatory Compliance Management Plan

### 17.1 Regulatory Landscape

| Regulation / Standard | Applicability | Compliance Owner |
| --- | --- | --- |
| CMS-0057-F (Prior Auth Interoperability) | BRD-01 directly; program-wide indirectly | J. Martinez (VP Compliance) |
| NIST AI RMF 1.0 | All BRDs — voluntary framework adopted as enterprise standard | S. Khurana (AI Gov Director) |
| ISO/IEC 42001 | AI CoE organizational alignment | S. Khurana |
| NAIC Model AI Bulletin | BRD-03 (underwriting) — state-level applicability varies | R. Thorne (General Counsel) |
| State AI-in-Insurance Statutes | BRD-01/03 — Colorado, Connecticut, others emerging | R. Thorne |
| HIPAA / HITECH | All PHI-handling workstreams | E. Sato (CPO) |
| SOX (Financial Controls) | Claims-payment and financial-reporting items | K. Williams (VP Internal Audit) |

### 17.2 Compliance Monitoring & Reporting

Compliance Officer (J. Martinez) maintains a regulatory tracker updated quarterly. Each regulation is mapped to: applicable BRD(s), compliance status (compliant/gap identified/remediation in progress), compliance evidence, and next review date.

Regulatory developments that could impact the program (new mandates, enforcement actions against peer companies, CMS guidance changes) are flagged to the AI Governance Board within 10 business days of identification.

Annual compliance audit conducted by Internal Audit (K. Williams) with findings reported to Executive Steering Board.

Part IV — Governance & Decision Authority

## 18. Governance Structure & Decision Rights

Full governance structure is defined in theProgram Governance Model. This section summarizes the decision-rights framework as it applies to day-to-day program execution.

### 18.1 Decision Authority Matrix

| Decision Type | Authority | Approval Process |
| --- | --- | --- |
| Sprint-level technical decisions | BRD Lead | Team decision, no formal approval needed |
| Cross-BRD technical dependency resolution | Program Director | Scrum-of-Scrums resolution; escalate if unresolved in 48 hrs |
| Model design approval | AI Governance Board | Reviewed at JAD; approved in Governance Board meeting |
| Architecture approval | EARB | Architecture review meeting; EARB sign-off required |
| Model production release | AI Governance Board + Independent Validation | Validation report clean → Board approval → release |
| Phase-gate advancement | All 3 Boards (concurrent) | Phase-gate procedure (Section 4.2) |
| Budget change >$500K | Executive Steering Board | Change control (Section 21) |
| Contingency drawdown >$1M | Executive Sponsor | Formal presentation + CFO concurrence |
| Scope change (any size) | Varies by impact — see Section 5.3 | Change control (Section 21) |
| Vendor contract >$500K | Executive Steering Board | Procurement threshold (Section 13.3) |
| Regulatory compliance interpretation | VP Compliance (J. Martinez) | Consulted with General Counsel; AI Governance Board informed |

## 19. Meeting Cadence & Reporting Framework

The meeting cadence is designed to provide sufficient oversight without consuming delivery capacity. Every meeting has a defined owner, duration, and expected output. Meetings that consistently run without actionable output are candidates for frequency reduction at the next quarterly governance review.

### 19.1 Standing Meetings

| Meeting | Frequency | Duration | Owner | Required Output |
| --- | --- | --- | --- | --- |
| Daily Standup (per BRD team) | Daily | 15 min | Scrum Master | Blocker identification |
| Scrum-of-Scrums | 2×/week | 15 min | C. Tyrrell | Cross-team dependency status |
| Sprint Planning (per BRD) | Bi-weekly (Day 1) | 90 min | BRD Lead + SM | Sprint backlog committed |
| Sprint Review/Demo | Bi-weekly (last day) | 45 min | BRD Lead | Increment demonstrated |
| Sprint Retrospective | Bi-weekly (last day) | 45 min | Scrum Master | Improvement actions identified |
| Backlog Refinement | Weekly (mid-sprint) | 60 min | Product Manager | Stories refined to "Ready" |
| Program Status Sync | Weekly | 60 min | C. Tyrrell | Status summary + blockers |
| Executive Steering Board | Bi-weekly | 90 min | M. Kavanagh | Scorecard + decisions |
| AI Governance Board | Bi-weekly | 60 min | S. Khurana | Model risk status + decisions |
| Enterprise Architecture Review | Weekly (build phases) | 60 min | D. Chen | Architecture decisions logged |
| Monthly Status Report | Monthly | Written (no meeting) | C. Tyrrell | 10-page report + dashboard |
| Quarterly Risk Review | Quarterly | 120 min | All 3 boards | RAIDD Log fully refreshed |

## 20. Escalation Framework

### 20.1 Standard Escalation Path

Escalation is expected and healthy — it means the governance structure is functioning. The following path applies to any issue that cannot be resolved at its originating level:

Level 1 — Team Level (0–24 hours):Team Lead or Scrum Master attempts resolution within the team. If resolved, log resolution in RAIDD Issues section.

Level 2 — Program Director (24–48 hours):If unresolved at team level, escalated to Program Director. Director convenes a working group (affected team leads, relevant board lead, functional manager). Most issues resolve here.

Level 3 — Board Level (48 hours–5 business days):If the working group cannot resolve, escalated to the relevant board: AI Governance Board (model-risk issues), EARB (technical issues), Executive Steering Board (scope/budget/schedule issues). Board provides direction within 5 business days.

Level 4 — Executive Sponsor (5+ business days):If board deadlocks or the issue exceeds board authority (e.g., requires >$1M contingency drawdown, regulatory escalation, program viability question), escalated to Executive Sponsor (M. Kavanagh). Sponsor makes final decision or escalates to CFO/CIO.

### 20.2 Emergency Escalation (Bypasses Standard Path)

| Trigger | Direct Escalation To | Timeline |
| --- | --- | --- |
| Security breach or data exposure (confirmed) | CISO + Executive Sponsor + General Counsel | Within 4 hours |
| AI model produces harmful output in production | AI Governance Board + Executive Sponsor | Within 24 hours; production paused immediately |
| Regulatory enforcement action received | General Counsel + Executive Steering Board | Immediately upon receipt |
| Team lead or key resource unplanned departure | Program Director + HR (C. Johnson) | Within 24 hours |

Part V — Program Execution & Control

## 21. Change Management & Configuration Control

### 21.1 What Requires Formal Change Control

Scope change: any addition, removal, or material alteration of a BRD deliverable or cross-cutting capability

Schedule change: >2 weeks on any BRD phase or program milestone

Budget change: >$500K in any cost category

Resource change: >5 FTEs or >2 team lead replacements

Model governance change: alteration to validation criteria, fairness thresholds, or human-override protocols

Risk materialization: any anticipated risk (R-01 through R-10) that materializes, requiring mitigation plan adjustment

### 21.2 Change Control Process

Submission:Change request submitted to Program Director using the standard form (inChange Control Log). Requestor documents: what is changing, why, impact on scope/schedule/budget/quality, alternatives considered, and recommended action.

Impact Assessment (5 business days):Program Director assesses impact across all dimensions. Consults with affected team leads, Program Finance, and relevant board chairs as needed.

Routing:Based on impact assessment, the change request is routed to the appropriate approval authority: Program Director (Tier 1, within standing authority), relevant Board (Tier 2, exceeds standing authority), or Executive Sponsor (Tier 3, exceeds Board authority).

Review & Decision (within 2 weeks of submission):Approver reviews impact assessment and makes decision: Approve, Approve with Conditions, Defer, or Reject. Decision documented.

Implementation:Approved changes are entered into the Change Control Log with effective date, baseline adjustment (if applicable), and owner accountability. All affected artifacts (WBS, RAIDD Log, Resource Plan, Budget) updated within 5 business days of approval.

### 21.3 Configuration Management

All program artifacts (plans, requirements documents, model documentation, test reports, governance records) are maintained in the project portal with version control.

Baseline documents (Charter, PMP, BRD requirements, SOWs) are stored as immutable versions. Updates create new versions; prior versions are retained for audit trail.

Model artifacts (trained models, training datasets, validation reports) follow a separate configuration management process defined by the AI CoE, with version tagging that links every production model to its training data, validation report, and approval record.

## 22. Performance Measurement & Earned Value

### 22.1 Performance Metrics

| Metric | Formula | Frequency | Green | Yellow | Red |
| --- | --- | --- | --- | --- | --- |
| Schedule Performance Index (SPI) | EV / PV | Monthly | ≥ 0.95 | 0.85–0.94 | < 0.85 |
| Cost Performance Index (CPI) | EV / AC | Monthly | ≥ 0.95 | 0.85–0.94 | < 0.85 |
| Estimate at Completion (EAC) | BAC / CPI | Quarterly | ≤ $99M | $99M–$103M | > $103M |
| Sprint Velocity (per BRD team) | Story points completed / sprint | Per sprint | Within ±10% of 3-sprint avg | ±10–20% | > ±20% |
| Defect Escape Rate | Post-sprint defects / stories | Per sprint | < 5% | 5–10% | > 10% |
| RAIDD Log Health | % of risks updated in last 14 days | Weekly | 100% | 80–99% | < 80% |

### 22.2 Program Dashboard

The Program Dashboard (separate artifact, updated weekly) provides a visual summary of all performance metrics. Dashboard sections: Overall Program Health (RAG), Schedule Health (SPI + milestone tracker), Budget Health (CPI + spend vs. forecast), Risk Health (active risk count by quadrant), Quality Health (defect trends + validation status), Staffing Health (actual vs. planned headcount). Dashboard reviewed at every Program Status Sync and presented to Executive Steering Board bi-weekly.

## 23. Benefits Realization Management

### 23.1 Benefits Framework

Benefits are tracked against baselines established during Phase 0 (AI Readiness Assessment). TheCost-Benefit Analysisdefines the expected benefit drivers; this section defines how realization is measured.

| Benefit | Metric | Baseline (Phase 0) | Target (Year 3) | Measurement Owner |
| --- | --- | --- | --- | --- |
| PA Cycle Time Reduction | Average days from PA submission to decision | Measured Phase 0 | 50% reduction | F. Bennett (BRD-01) |
| PA Automation Rate | % of PAs auto-adjudicated (no human touch) | 0% (current manual process) | 60–70% | F. Bennett |
| Call-Center Handle Time | Average handle time per member interaction | Measured Phase 0 | 30% reduction | X. Garcia (BRD-02) |
| Underwriting Consistency | Inter-rater reliability score | Measured Phase 0 | 20% improvement | Z. Thompson (BRD-03) |
| Claims Fraud Detection | Annual fraud-identified amount | Current baseline | $2.4M/yr increase | F. Bennett |

### 23.2 Benefits Tracking Cadence

Phase 0:Baseline measurement. Current-state metrics captured for all benefit categories.

Phase 4 (post-production):Initial measurement. Compare actual production metrics against baseline.

Quarterly (Year 2–3):Benefits realization update included in quarterly risk review and monthly status reports.

Program Closeout:Final benefits-realization audit comparing actuals against CBA projections. Results documented in Closeout Report and presented to Executive Steering Board.

## 24. Knowledge Transfer & Transition Planning

### 24.1 Transition Scope

At program closeout (August 2029), the following capabilities transition from Pulaski Advisory Group consulting delivery to permanent ACME Highland Health operations:

AI Governance & CoE:Enterprise AI standards, model governance processes, shadow-AI prevention, regulatory tracking. Transferred to a permanent ACME AI Governance function.

Independent Model Validation:Validation methodology, testing protocols, and tooling. Transferred to ACME's internal audit or risk management function.

Platform Operations:Data & Cloud AI Platform Foundation, MLOps pipelines, FinOps controls. Transferred to ACME IT Operations (H. Nakamura).

Model Monitoring & Retraining:Production model monitoring dashboards, retraining triggers and processes. Transferred to ACME data science function (to be established).

### 24.2 Knowledge Transfer Process

Knowledge transfer begins 6 months before program closeout (February 2029) with a formal KT plan approved by the Executive Steering Board.

Each transferring capability has a named Pulaski transferor and a named ACME receiver. KT progress tracked weekly by PMO.

KT completion criteria: ACME receiver can operate the capability independently for 4 consecutive weeks without Pulaski support. Verified by the Program Director and signed off by the relevant board.

Runbooks, process documentation, and operational playbooks are delivered as KT artifacts and archived in the ACME knowledge management system.

Part VI — Baselines, Assumptions & Reference

## 25. Assumptions, Constraints & Dependencies

### 25.1 Assumptions

ACME member volume and PA case mix remain stable: approximately 4 million members, 800,000 annual PA cases. Material volume changes (>10%) would require re-baselining model training data and capacity planning.

State regulatory environment remains stable within current risk envelope. New AI-in-insurance mandates or CMS guidance changes are absorbed through CoE standards updates, not model redesigns (unless mandated).

Cloud/LLM vendor ecosystem remains viable and accessible through program duration. No major platform discontinuations, pricing shocks, or access restrictions that would require platform migration.

ACME executive commitment to the program (budget, staffing, governance participation) remains through all three years. Budget re-authorization for Years 2 and 3 proceeds as planned at the respective Phase 4 gates.

Offshore labor market conditions remain stable for the duration. Offshore billing rates escalate per contractual terms (typically 3–5% annually) without requiring renegotiation.

### 25.2 Constraints

Budget ceiling:$99M total authorization. No mechanism for additional funding without ACME Board-level approval.

PHI data residency:All PHI must remain onshore US. This constraint limits offshore team scope to non-PHI platform work, synthetic-data model training, and general engineering tasks.

Regulatory timeline:CMS-0057-F mandate effective January 2027. While baseline compliance is a separate project, Project Catalyst's BRD-01 must demonstrate governance maturity by that date.

Model validation independence:The Independent Model Validation team cannot be combined with or report to BRD delivery teams. This is a structural constraint, not a preference.

### 25.3 External Dependencies

DEP-01:CMS-0057-F mandate (external regulatory driver). Dependency: ACME's separate baseline compliance project must deliver independently.

DEP-02:AI Governance & CoE Charter completion (Phase 0) is prerequisite for BRD-01 JAD sessions (Phase 1).

DEP-03:Data & Cloud Platform Foundation must go live before BRD-01 model build accelerates (Phase 2).

DEP-04:Hyperscaler vendor infrastructure provisioning must meet Phase 0 timelines.

DEP-05:LLM provider API access and terms must remain stable through Year 1 (BRD-01 model development).

## 26. Baselines Summary

| Baseline | Established | Document | Change Authority |
| --- | --- | --- | --- |
| Scope Baseline | Phase 1 Gate (per BRD) | BRD Requirements Document + WBS | Executive Steering Board |
| Schedule Baseline | Program Kickoff | Program Plan Console / WBS | Program Director (< 2 weeks); ESB (> 2 weeks) |
| Cost Baseline | Charter Approval | Program Charter Section 10 + SOWs | Executive Steering Board |
| Quality Baseline | Phase 1 Gate | Quality Metrics (Section 9.4) + Model Validation Criteria | AI Governance Board |
| Resource Baseline | Phase 0 Gate | Resource Plan (262-person roster) | Program Director (< 5 FTEs); ESB (> 5 FTEs) |

## 27. Process Improvement & Lessons Learned

Sprint retrospectives (bi-weekly, per BRD team) are the primary mechanism for continuous process improvement at the team level. Action items from retrospectives are tracked by the Scrum Master and reviewed at the next retrospective.

Program-level lessons learned are captured at each phase gate by the PMO Lead. Lessons are classified as: process improvement (change how we work), governance improvement (change how decisions are made), or technical improvement (change how we build).

A consolidated Lessons Learned Register (separate artifact) is published at program closeout and presented to the Executive Steering Board. Key lessons are incorporated into ACME's organizational process assets for future programs.

The Program Director conducts a mid-program retrospective (end of Year 1) to assess whether the hybrid delivery methodology, governance structure, and communication cadence are working as designed — and adjusts if not.

## 28. Document Control & Approvals

### 28.1 Document Control

| Field | Value |
| --- | --- |
| Document Title | Program Management Plan (PMP) |
| Program | Project Catalyst — AI Transformation Program |
| Version | 1.0 |
| Date | 17 August 2026 |
| Classification | ACME Internal — Restricted Distribution |
| Retention | Program lifecycle + 7 years per ACME retention policy |

### 28.2 Approval Signatures

| Role | Name | Approval |
| --- | --- | --- |
| Program Director | C. Tyrrell (Pulaski Advisory Group) | Approved — 17 Aug 2026 |
| Executive Sponsor | M. Kavanagh (ACME COO) | Approved — 17 Aug 2026 |
| PMO Lead | T. Valdez (ACME) | Approved — 17 Aug 2026 |
| AI Governance Director | S. Khurana (Pulaski) | Approved — 17 Aug 2026 |
| Chief Enterprise Architect | D. Chen (ACME) | Approved — 17 Aug 2026 |

## 29. Appendices & Cross-References

Appendix A:Program Charter— authorizing document

Appendix B:Program Governance Model— decision rights and board composition

Appendix C:RAIDD Log— risk, assumption, issue, dependency, and decision register

Appendix D:Resource Plan— complete 262-person named roster

Appendix E:Organization Chart— full reporting structure

Appendix F:RACI Matrix— responsibility assignments

Appendix G:Change Control Log— formal change record

Appendix H:Communications Plan— full communication matrix

Appendix I:AI Governance & JAD Session Charter— CoE mandate and JAD structure

Appendix J:Cost-Benefit Analysis— benefits framework and NPV analysis

Appendix K:Total Cost of Ownership— 10-year cost comparison

Appendix L:SOW-01, SOW-02, SOW-03 — contractual scope and fee schedules

Illustrative program data — created to demonstrate large-scale AI program management practice.