WEEKLY STATUS REPORT

Program Controls · Weekly Status — Project Catalyst, AI Transformation Program

ACME Highland Health  |  Pulaski Advisory Group  |  $99M · 262 people · 36.5 months

## Weekly Status — At a Glance

## Accomplishments This Week

AI Readiness Assessment fieldwork on track: data-source inventory and legacy claims data profiling substantially underway ahead of the 25 Sep report.

Platform/cloud vendor evaluation advanced to shortlist; security and BAA requirements issued to finalists via the Vendor/Procurement lead.

AI Governance Board and Enterprise Architecture Review Board charters drafted and circulated for the Phase-0 gate; first joint session scheduled.

BRD-01 (Claims & Prior Authorization AI) requirements preparation begun with Utilization Management SMEs ahead of the December JAD sign-off.

EVM reporting cadence confirmed with Program Finance; Week-4 baseline metrics captured (SPI/CPI 1.00).

## Planned for Next Week

Complete legacy claims data-quality profiling and draft the remediation-scope input for the AI Readiness Report.

Hold the inaugural joint AI Governance Board / EARB working session; ratify board operating cadence.

Receive vendor finalist responses; begin scoring against the platform selection criteria.

Finalize the AI Readiness Assessment Report draft for 25 Sep milestone review.

Stand up the RAIDD review cadence and confirm mitigation owners for the top anticipated risks.

## Risks & Issues Requiring Attention

| ID | Item | Type | Exposure | Status & Action |
| --- | --- | --- | --- | --- |
| RSK-01 | Legacy claims data fragmentation could pressure the BRD-01 timeline | Risk | High (inherent) | Profiling underway in Phase 0; remediation scope to feed the Readiness Report. Owner: Data & Cloud Platform lead. |
| RSK-02 | GenAI compute / token cost overrun at scale | Risk | Med-High | FinOps guardrails to be designed into platform build; watch item for Year 2. Owner: Program Finance / Platform lead. |
| RSK-03 | Member chatbot hallucination / liability (Air Canada precedent) | Risk | High (inherent) | Human-in-the-loop and disclaimer controls being designed into BRD-02 scope now. Owner: AI Governance Director. |
| DEP-01 | CMS-0057-F baseline compliance handled by a separate project | Dependency | External | Interface confirmed; coordination point logged. No action required this week. |

No open issues this week. All items above are anticipated risks/dependencies under active monitoring; none has been realized. Full detail on the RAIDD Log.

## Upcoming Milestones

| Milestone | Target Date | Owner | Status |
| --- | --- | --- | --- |
| AI Readiness Assessment Report | 25 Sep 2026 | Program Director | In progress |
| Phase 0 Gate — CoE Charter, Governance Framework, Platform Vendor | 06 Nov 2026 | All 3 Boards | On plan |
| BRD-01 Requirements Sign-off (JAD complete) | 18 Dec 2026 | AI Governance Board | On plan |
| Platform Foundation Go-Live | 12 Mar 2027 | EARB | On plan |

## Decisions & Approvals Needed

| Item | Needed From | By |
| --- | --- | --- |
| Ratify AI Governance Board & EARB operating cadence | Executive Steering Board | Phase 0 Gate prep |
| Confirm platform vendor shortlist for final scoring | EARB | Next reporting period |

Distribution: Executive Steering Board · AI Governance Board · Enterprise Architecture Review Board · PMO · Program Finance. Next report: Week 5, ending 18 Sep 2026.

Illustrative program data for a fictional engagement (ACME Highland Health / Pulaski Advisory Group), created to demonstrate program-management practice. Status reflects a modeled Week-4 / Phase-0 position as of 11 September 2026. Cross-references: Program Dashboard · RAIDD Log · Program Budget.