## Slide 1
STEERING REVIEW · STEERING REVIEW · FOUNDATION GATE
Project Catalyst
Steering committee review — Project Catalyst is at its Phase-0 (Foundation) gate, reading Amber as real foundation findings surface, with the platform cost overrun contained and BRD-01 design next.
Phase-0 Gate
Foundation Complete
● Amber
Overall Health
262
Program Team (ramping)
$99.0M
Program Budget

## Slide 2
AGENDA
Today's Steering Review
1
Program Health Snapshot
2
Where We Stand — Status
3
Objectives Status
4
Scope & Change Log
5
The Program Team
6
Governance & Decision Rights
7
Schedule Status
8
Budget Forecast
9
How We Stay in Sync
10
Risk Register — Aged
11
Issues — Raised & Resolved
12
Decisions & Look-Ahead
2

## Slide 3
PROGRAM HEALTH
Where We Stand — Phase-0 Gate
Project Catalyst reaches its Phase-0 gate reading Amber — the foundation work is complete, but it surfaced real findings that pressure the BRD-01 timeline.
The AI Readiness Assessment, the AI Center-of-Excellence charter and governance framework, and platform/cloud vendor selection are all complete, and the AI Governance and Enterprise Architecture Review Boards are operational. The gate reads Amber because Foundation did its job — it surfaced the real constraints: legacy claims data quality nearing its trigger threshold, an unstructured medical-policy corpus, and a two-week talent slip. The platform cost overrun is already contained via a multi-cloud strategy. The get-to-Green lever is closing these findings before BRD-01 design sign-off in December.
● Amber
Overall health
Phase 0
At the Foundation gate
Dec
BRD-01 design sign-off
3

## Slide 4
PROGRAM STATUS
Amber on Foundation Findings; Budget Contained
Amber on foundation findings that pressure the BRD-01 timeline; budget is contained and schedule baseline is intact.
Budget is Green: the initial hyperscaler quote ran 17% over the platform allocation, but a multi-cloud strategy brought it back within baseline (I-02, resolved). Schedule reads Amber: legacy claims data quality is at ~12% against a 15% remediation trigger (R-01), the medical-policy corpus needs an unscoped conversion for NLP/RAG (I-04), and two BRD-01 ML-engineer offers were declined (I-03). None has breached the baseline yet — the committee's focus is closing them before BRD-01 design sign-off.
KEY FACTS
Schedule
● Amber — BRD-01 timeline pressure
Budget
● Green — multi-cloud contained the overrun
Governance
● Green — both boards operational
Scope
● Amber — policy-conversion (I-04) to scope
4

## Slide 5
OBJECTIVES
How We're Tracking to Plan
1
✓ AI Readiness Assessment delivered; the enterprise AI baseline established
2
✓ AI Center of Excellence charter and governance framework stood up; both boards operational
3
✓ Platform / cloud vendor selection complete — multi-cloud strategy adopted, cost within baseline
4
AT RISK — legacy claims data quality at ~12% against the 15% remediation trigger (R-01)
5
On track — BRD-01 (Claims & Prior-Auth AI) requirements prepared ahead of December design sign-off
5

## Slide 6
SCOPE & CHANGE
What's Changed Since Kickoff
IN SCOPE
✓
Multi-cloud platform strategy
Adopted to contain the 17%-over hyperscaler quote (I-02) — within the $26.9M allocation
✓
Data-remediation rules scoped
Identifier-mapping remediation for the ~12% of claims records nearing the R-01 trigger
✓
Policy-corpus conversion — pending
Structured conversion of PDF medical policies for NLP/RAG (I-04) — a scope decision this review
OUT OF SCOPE (CANDIDATE BACKLOG)
✕
Program baseline intact
$99.0M and the 36.5-month schedule unchanged at the Phase-0 gate
✕
BRD scope unchanged
Still BRD-01, BRD-02, BRD-03 as chartered; no new use cases added
✕
CMS-0057-F scope held
The prior-authorization interoperability driver remains as baselined for BRD-01
6

## Slide 7
TEAMS
The Program Team — Ramping to 262
262 people across the program, ramping through Foundation into Phase 1. Two BRD-01 ML-engineer offers were declined (I-03) and are being re-sourced — a two-week ramp slip, not a headcount reduction. Full roster in the Resource Plan.
18
Program Leadership & PMO
Lead: C. Tyrrell (Program Director); PMO, RAIDD, EVM
24
AI Center of Excellence & Governance
AI CoE, model governance, both review boards operational
60
BRD-01 · Claims & Prior-Auth AI
The lead use case ahead of the CMS-0057-F driver
44
BRD-02 · Member Experience / Chatbot
Human-in-the-loop, confidence thresholds (RSK-03)
70
Platform, Data & MLOps
Multi-cloud platform, data pipelines, MLOps
46
Enterprise Integration, Security & Change
Integration, security, and organizational change management
7

## Slide 8
GOVERNANCE
Who Decides What
Governance runs on three tiers of authority. The Program Director holds standing authority for minor changes; anything beyond it goes to the relevant board — the Executive Steering Board, the AI Governance Board, or the Enterprise Architecture Review Board; and program-viability or contingency calls above $1M escalate to the Executive Sponsor and CFO.
Tier 1
Schedule ≤2 wks, resource <5 FTEs, budget reallocation <$500K, no scope change
Program Director (C. Tyrrell)
Tier 2
Any scope change; schedule >2 wks; budget >$500K; model-governance change
Relevant Board — ESB / AI Governance / EARB
Tier 3
Contingency >$1M, program viability, regulatory escalation, Charter re-baseline
Executive Sponsor (M. Kavanagh) + CFO
Model governance
AI model risk, human-in-the-loop, bias and safety review
AI Governance Board
8

## Slide 9
TIMELINE
Phase-0 Gate — Foundation Complete, BRD-01 Next
The 12-week Foundation leg is at its gate; AI Readiness, the CoE, and platform selection are done, with BRD-01 design sign-off (Dec) the next milestone.
Phase 0 · Foundation
At the gate ◆ · Aug–Nov '26
Phase 1 · BRD-01 Claims AI
Design next (Dec) · Dec '26–'27
Phase 2 · BRD-02 Member AI
Upcoming · 2027–28
Phase 3 · BRD-03 Underwriting
Upcoming · 2028
Phase 4 · Scale & Sustain
Upcoming · 2028–29
KEY MILESTONES
✓ 25 Sep '26
AI Readiness Assessment Report delivered
✓ Oct '26
AI CoE + governance boards operational
◆ Now — Phase-0 Gate
Foundation complete; findings in remediation
Dec '26
BRD-01 design sign-off
Jan '27
CMS-0057-F prior-authorization driver
'27–'29
BRD-01 → BRD-03 build and scale
9

## Slide 10
TIMELINE · DETAIL
Project Phases — Detailed View
The program as a work view — bars show when each workstream runs and where they overlap.
'26 H2
'27 H1
'27 H2
'28 H1
'28 H2
'29
Prog.
Foundation ◆
Phase 0 — readiness, CoE, platform
BRD-01 design sign-off
BRD-01 & BRD-02
BRD-01 — Claims & Prior-Auth AI
BRD-02 — Member chatbot
BRD-03 & Scale
BRD-03 — Underwriting risk
Scale & sustain
10

## Slide 11
BUDGET
Budget Status
TOTAL PROGRAM BUDGET $99.0M
Labor — 262-Person Program (36.5 months)
$68,400,000
Six workstreams across four delivery phases
Cloud / Platform (multi-cloud)
$26,900,000
Contained within allocation after the multi-cloud strategy (I-02)
AI/ML Tooling, Models & Licensing
$1,200,000
MLOps, model, and platform tooling licenses
Data Remediation & Conversion
$900,000
Claims-data identifier mapping + policy-corpus conversion (I-01, I-04)
Independent Model Risk & Security Review
$700,000
External model-governance and security assurance
Program Contingency
$900,000
Held against R-01 and the anticipated risk register
Program budget of $99.0M over 36.5 months. The initial hyperscaler quote ran 17% over the $26.9M platform allocation; a multi-cloud strategy brought it back within baseline, so cost health is Green at the Phase-0 gate with roughly $9M drawn to date.
11

## Slide 12
BUDGET FORECAST
Budget Forecast — On Baseline; Platform Cost Contained via Multi-Cloud
Cost is Green at the Phase-0 gate — a multi-cloud strategy contained the platform overrun, and cumulative cost tracks on baseline against the $99.0M program value.
On earned value at the Phase-0 gate (~Month 3), cost performance is on baseline (CPI ~0.99) and schedule just under (SPI ~0.98) reflecting the talent and data findings. The initial hyperscaler quote threatened a 17% overrun on the $26.9M platform allocation; adopting a multi-cloud strategy brought it within baseline. The forecast at completion holds at roughly $97.5M, a small favorable margin, with the $900K contingency intact against the data-quality risk.
● ON TRACK
CUMULATIVE SPEND — PLAN vs. ACTUAL / FORECAST ($M)
Chart: 
| M0 | M3 | M9 | M18 | M24 | M30 | M37
Planned | 0 | 9.5 | 22 | 48 | 70 | 88 | 99
Actual + Forecast | 0 | 9 | 20.5 | 45.5 | 67 | 85 | 97.5
$99.0M
Program budget (BAC)
~$97.5M
Forecast at completion (EAC)
0.99 / 0.98
CPI / SPI
12

## Slide 13
WORKING TOGETHER
How We Stay in Sync
CADENCE
FORUM
PURPOSE
Weekly
Program Status & RAIDD
Delivery status, risk/issue tracking, workstream sync
Bi-weekly
AI Governance & Architecture Boards
Model governance, architecture, and scope/budget decisions
Monthly
Executive Steering Board
Program health, gate decisions, and major risk acceptance
Per gate
Phase-Gate Reviews
Formal phase-gate go/no-go — Foundation, then each BRD
13

## Slide 14
RISKS
Risks and Mitigation
The full register at a glance — each risk with its mitigation, likelihood, and impact; detailed cards follow.
IDENTIFIED RISKS
MITIGATION STRATEGY
LIKELIHOOD
IMPACT
01
Legacy claims data fragmentation
✓
Remediation rules scoped before Build to hold under 15%
High
High
02
Member chatbot hallucination / liability
✓
Human-in-the-loop + confidence thresholds in BRD-02
High
High
03
Unstructured policy corpus
✓
Policy-conversion scope change brought to this review
Medium
High
04
AI/ML talent availability
✓
Recruiting re-sourcing + pre-cleared pipeline
Medium
Medium
14

## Slide 15
RISK REGISTER
Risk Register (1 of 2)
R-01
Legacy claims data fragmentation
LIKELIHOOD HIGH
IMPACT HIGH
Historical claims data quality could pressure the BRD-01 timeline; profiling shows ~12% of records need identifier-mapping remediation, approaching the 15% trigger.
OWNER T. Valdez
STATUS Watch — nearing trigger
Mitigation: Data profiling completed in Phase 0; remediation rules are scoped now, ahead of Build, to keep the figure under the 15% threshold.
RSK-03
Member chatbot hallucination / liability
LIKELIHOOD HIGH
IMPACT HIGH
An AI chatbot giving members incorrect coverage guidance carries real liability (the Moffatt v. Air Canada precedent).
OWNER F. Bennet
STATUS Monitoring — design control
Mitigation: Human-in-the-loop review, scoped disclaimers, and confidence thresholds are being designed into BRD-02 from the outset.
15

## Slide 16
RISK REGISTER
Risk Register (2 of 2)
R-04
Unstructured policy corpus
LIKELIHOOD MEDIUM
IMPACT HIGH
ACME's medical policies are PDF-only; BRD-01 and BRD-02 need them structured for NLP/RAG, an effort not originally scoped (I-04).
OWNER F. Bennet
STATUS Watch — scope decision pending
Mitigation: A structured-conversion scope change is being brought to this review so the effort is funded before BRD-01 build.
R-06
AI/ML talent availability
LIKELIHOOD MEDIUM
IMPACT MEDIUM
Competition for AI/ML engineers could slow team ramp; two BRD-01 offers were already declined (I-03).
OWNER C. Tyrrell
STATUS Monitoring — re-sourcing
Mitigation: The Pulaski recruiting team is re-sourcing the two roles; a pre-cleared candidate pipeline reduces future single-threading.
16

## Slide 17
ISSUES
Issues — Raised & Resolved
Issues that arose during execution and how each was dispositioned — the record of what actually happened, not just what we watched for.
IDENTIFIED ISSUES
ACTION / RESOLUTION
OWNER
STATUS
01
Phase-0 data profiling found ~12% of legacy claims records need identifier-mapping remediation, approaching the 15% trigger threshold for R-01
✓
Remediation rules scoped and sequenced ahead of BRD-01 Build; profiling continues to hold the figure
T. Valdez
In Progress
02
The initial hyperscaler platform quote ($31.4M) exceeded the $26.9M cloud allocation by 17%
✓
A multi-cloud strategy was adopted, bringing platform cost back within the allocation
W. Kumar
Resolved
03
Two BRD-01 ML-engineer candidates (offshore) declined offers, a two-week slip to team ramp
✓
The Pulaski recruiting team is re-sourcing both roles against a pre-cleared pipeline
C. Tyrrell
In Progress
04
ACME's medical policy documents are PDF-only, but BRD-01 and BRD-02 need them structured for NLP/RAG — conversion was not originally scoped
✓
A structured-conversion scope change is being brought to the Steering Board this review
F. Bennet
Open
17

## Slide 18
DECISIONS & CHANGES
Decisions & Changes Since Kickoff
The Phase-0 gate surfaced real foundation issues; the platform cost is resolved, and one scope decision is on the table for this review.
I-02 · Multi-cloud
Adopted a multi-cloud platform strategy to contain the 17%-over hyperscaler quote within the $26.9M allocation — cost back on baseline
Enterprise Architecture Review Board Ratified at the gate
Phase-0 Gate
Foundation deliverables accepted — AI Readiness, CoE charter, governance boards, and platform selection all complete
Executive Steering Board This review
Needed
Approve the structured policy-corpus conversion scope change (I-04) so the effort is funded before BRD-01 build begins
Executive Steering Board This review
18

## Slide 19
NEXT STEPS
The Look-Ahead
1
Now → Dec
Close the Phase-0 findings and lock BRD-01 design ahead of the December sign-off
2
Dec '26
BRD-01 design sign-off — the gate into Phase 1 build
3
Jan '27
CMS-0057-F prior-authorization driver lands — BRD-01 is sequenced to meet it
19

## Slide 20
QUESTIONS?
Let's build something that sets the gold standard.
C. Tyrrell · Program Director
Project Catalyst — Enterprise AI Transformation
All program artifacts available at ct-pm.pages.dev/ai-transformation/