MULTI-YEAR WBS CONSOLE

Program Controls · Work Breakdown Structure — Project Catalyst, AI Transformation Program

ACME Highland Health  |  Pulaski Advisory Group  |  $99M · 262 people · 36.5 months

Status as of Friday, 11 September 2026 — Week 4, Phase 0 (Foundation)

The Work Breakdown Structure is the program's scope backbone — every dollar, deliverable, and dependency traces to a WBS element. This dictionary decomposes Project Catalyst into 7 top-level elements and 64 work packages across the five delivery/cross-cutting workstreams and three years. Element 1.0 Program Management is the PMI-standard management element; elements 2.0–6.0 are the five workstreams defined in the Program Management Plan; element 7.0 is the Year-3 optimization, benefits, and closeout leg. Budget rolls up to the three annual Statement-of-Work envelopes exactly — $27.72M (Year 1), $41.58M (Year 2), and $29.70M (Year 3), totaling $99.0M. This is the static companion to the interactive WBS Console; the live console adds filtering, expand/collapse, and dynamic rollups.

Program budget $99,000,000 · 7 elements · 64 work packages · 262 people / 25 teams · 2.0% budget-weighted complete · 12 in progress / 52 not started / 0 complete

Budget Rollup Matrix — Workstream × Year

| WBS Element | Year 1 | Year 2 | Year 3 | Program Total |
| --- | --- | --- | --- | --- |
| 1.0 Program Management & PMO | $3,600,000 | $4,800,000 | $4,200,000 | $12,600,000 |
| 2.0 Data & Cloud AI Platform | $8,900,000 | $6,500,000 | $5,300,000 | $20,700,000 |
| 3.0 AI Governance & Center of Excellence | $4,200,000 | $4,600,000 | $4,400,000 | $13,200,000 |
| 4.0 BRD-01 · Claims & Prior Authorization AI | $11,020,000 | — | — | $11,020,000 |
| 5.0 BRD-02 · Member & Provider Experience AI | — | $13,200,000 | — | $13,200,000 |
| 6.0 BRD-03 · Underwriting & Risk AI | — | $12,480,000 | — | $12,480,000 |
| 7.0 Optimization, Benefits & Closeout | — | — | $15,800,000 | $15,800,000 |
| PROGRAM TOTAL | $27,720,000 | $41,580,000 | $29,700,000 | $99,000,000 |
| SOW ENVELOPE | $27,720,000 | $41,580,000 | $29,700,000 | $99,000,000 |
| VARIANCE | $0 | $0 | $0 | $0 |

Budget reconciles exactly to all three annual SOW envelopes and to the $99.0M program total — variance $0 in every year.

Work Package Dictionary

1.0  Program Management & PMO

Management workstream · $12,600,000 total

| WBS ID | Work Package | Owner | Phase / Window | Budget | Status | % |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 Governance & Board Operations |  |  |  |  |  |  |
| 1.1.1 | Program governance & board operations | C. Tyrrell | Ph 0–4 · Y1 · Aug 2026 – Sep 2027 | $1,000,000 | In Progress | 8% |
| 1.1.2 | Program governance & board operations | C. Tyrrell | Y2 · Oct 2027 – Dec 2028 | $1,350,000 | Not Started | 0% |
| 1.1.3 | Program governance & board operations | C. Tyrrell | Y3 · Jan 2029 – Aug 2029 | $1,200,000 | Not Started | 0% |
| 1.2 Planning, Schedule & Cost Control (EVM) |  |  |  |  |  |  |
| 1.2.1 | Schedule & cost baseline, EVM control | M. Torres | Y1 · Aug 2026 – Sep 2027 | $900,000 | In Progress | 12% |
| 1.2.2 | Schedule & cost control | M. Torres | Y2 · Oct 2027 – Dec 2028 | $1,200,000 | Not Started | 0% |
| 1.2.3 | Schedule & cost control | M. Torres | Y3 · Jan 2029 – Aug 2029 | $1,050,000 | Not Started | 0% |
| 1.3 Risk, Issue & Change Control |  |  |  |  |  |  |
| 1.3.1 | RAIDD log & change control operations | T. Valdez | Y1 · Aug 2026 – Sep 2027 | $850,000 | In Progress | 10% |
| 1.3.2 | RAIDD log & change control operations | T. Valdez | Y2 · Oct 2027 – Dec 2028 | $1,150,000 | Not Started | 0% |
| 1.3.3 | RAIDD log & change control operations | T. Valdez | Y3 · Jan 2029 – Aug 2029 | $1,000,000 | Not Started | 0% |
| 1.4 Financials, Reporting & Stakeholder Comms |  |  |  |  |  |  |
| 1.4.1 | Program finance, status reporting & comms | A. Rodriguez | Y1 · Aug 2026 – Sep 2027 | $850,000 | In Progress | 9% |
| 1.4.2 | Program finance, status reporting & comms | A. Rodriguez | Y2 · Oct 2027 – Dec 2028 | $1,100,000 | Not Started | 0% |
| 1.4.3 | Program finance, status reporting & comms | A. Rodriguez | Y3 · Jan 2029 – Aug 2029 | $950,000 | Not Started | 0% |

2.0  Data & Cloud AI Platform

Cross-cutting workstream · $20,700,000 total

| WBS ID | Work Package | Owner | Phase / Window | Budget | Status | % |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1 Architecture & Vendor Selection |  |  |  |  |  |  |
| 2.1.1 | Platform architecture & vendor selection | D. Chen | Phase 0 · Aug 2026 – Nov 2026 | $1,400,000 | In Progress | 35% |
| 2.2 Cloud Foundation & Security |  |  |  |  |  |  |
| 2.2.1 | Cloud foundation build — landing zone, network, security | Platform Lead | Ph 1–2 · Nov 2026 – Mar 2027 | $3,200,000 | Not Started | 0% |
| 2.3 MLOps Pipeline & Model Registry |  |  |  |  |  |  |
| 2.3.1 | MLOps pipeline & model registry v1 | Platform Lead | Ph 1–2 · Dec 2026 – Jun 2027 | $2,100,000 | Not Started | 0% |
| 2.3.2 | MLOps pipeline enhancements | Platform Lead | Y2 · Oct 2027 – Sep 2028 | $1,700,000 | Not Started | 0% |
| 2.4 Data Governance & Feature Store |  |  |  |  |  |  |
| 2.4.1 | Data governance & feature store v1 | Data Lead | Ph 1–2 · Dec 2026 – Jun 2027 | $1,600,000 | Not Started | 0% |
| 2.4.2 | Data governance & feature store expansion | Data Lead | Y2 · Oct 2027 – Sep 2028 | $1,500,000 | Not Started | 0% |
| 2.5 FinOps & Cost Controls |  |  |  |  |  |  |
| 2.5.1 | FinOps & cloud cost controls | A. Rodriguez | Y1 · Nov 2026 – Sep 2027 | $600,000 | Not Started | 0% |
| 2.5.2 | FinOps & cloud cost controls | A. Rodriguez | Y2 · Oct 2027 – Dec 2028 | $700,000 | Not Started | 0% |
| 2.5.3 | FinOps & cloud cost controls | A. Rodriguez | Y3 · Jan 2029 – Aug 2029 | $1,100,000 | Not Started | 0% |
| 2.6 Multi-BRD Platform Scale |  |  |  |  |  |  |
| 2.6.1 | Platform scale & multi-BRD enablement | Platform Lead | Y2 · Oct 2027 – Jun 2028 | $2,600,000 | Not Started | 0% |
| 2.7 Enterprise Integration & MLOps Maturity |  |  |  |  |  |  |
| 2.7.1 | Enterprise integration certification (all 3 BRDs) | Platform Lead | Y3 · Jan 2029 – Apr 2029 | $2,300,000 | Not Started | 0% |
| 2.7.2 | MLOps maturity assessment & uplift | Platform Lead | Y3 · Apr 2029 – Jun 2029 | $1,900,000 | Not Started | 0% |

3.0  AI Governance & Center of Excellence

Cross-cutting workstream · $13,200,000 total

| WBS ID | Work Package | Owner | Phase / Window | Budget | Status | % |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1 CoE Standup & Framework |  |  |  |  |  |  |
| 3.1.1 | AI readiness assessment | S. Khurana | Phase 0 · Aug 2026 – Sep 2026 | $700,000 | In Progress | 70% |
| 3.1.2 | CoE charter & governance framework v1 | S. Khurana | Phase 0 · Aug 2026 – Nov 2026 | $800,000 | In Progress | 30% |
| 3.2 Standards & Regulatory Alignment |  |  |  |  |  |  |
| 3.2.1 | NIST AI RMF + ISO/IEC 42001 alignment | S. Khurana | Ph 0–1 · Sep 2026 – Feb 2027 | $700,000 | In Progress | 15% |
| 3.2.2 | AI standards, model inventory & shadow-AI controls | AI CoE | Ph 0–2 · Sep 2026 – Jun 2027 | $600,000 | In Progress | 5% |
| 3.3 Independent Model Validation Function |  |  |  |  |  |  |
| 3.3.1 | IMV function standup (2nd line of defense) | P. Okafor | Ph 0–1 · Sep 2026 – Feb 2027 | $1,000,000 | In Progress | 20% |
| 3.3.2 | IMV — BRD-02/03 validation cycle | P. Okafor | Y2 · Jan 2028 – Apr 2028 | $1,500,000 | Not Started | 0% |
| 3.3.3 | Full IMV re-certification (all 3 BRDs) | P. Okafor | Y3 · Apr 2029 – Jun 2029 | $1,600,000 | Not Started | 0% |
| 3.4 Responsible AI |  |  |  |  |  |  |
| 3.4.1 | Responsible AI: fairness, bias & transparency framework | AI CoE | Ph 0–1 · Sep 2026 – Feb 2027 | $400,000 | In Progress | 5% |
| 3.4.2 | Responsible AI audits — BRD-02/03 fairness | AI CoE | Y2 · Jan 2028 – Apr 2028 | $900,000 | Not Started | 0% |
| 3.5 Governance Operations & Transition |  |  |  |  |  |  |
| 3.5.1 | Governance operations & board support | S. Khurana | Y2 · Oct 2027 – Dec 2028 | $1,200,000 | Not Started | 0% |
| 3.5.2 | Model inventory & shadow-AI program | AI CoE | Y2 · Oct 2027 – Dec 2028 | $1,000,000 | Not Started | 0% |
| 3.5.3 | Governance operations | S. Khurana | Y3 · Jan 2029 – Aug 2029 | $1,100,000 | Not Started | 0% |
| 3.5.4 | CoE steady-state transition plan & formal handover | S. Khurana | Y3 · May 2029 – Aug 2029 | $1,700,000 | Not Started | 0% |

4.0  BRD-01 · Claims & Prior Authorization AI

Delivery · Y1 workstream · $11,020,000 total

| WBS ID | Work Package | Owner | Phase / Window | Budget | Status | % |
| --- | --- | --- | --- | --- | --- | --- |
| 4.1 Requirements & Design (Phase 1) |  |  |  |  |  |  |
| 4.1.1 | JAD sessions & requirements package | BRD-01 Lead | Phase 1 · Nov 2026 – Dec 2026 | $1,300,000 | In Progress | 5% |
| 4.1.2 | Solution & model design | BRD-01 Lead | Phase 1 · Dec 2026 – Feb 2027 | $1,200,000 | Not Started | 0% |
| 4.2 Build & Test (Phase 2) |  |  |  |  |  |  |
| 4.2.1 | Model development & training (sprints) | BRD-01 Team | Phase 2 · Feb 2027 – May 2027 | $3,400,000 | Not Started | 0% |
| 4.2.2 | Integration & system testing | BRD-01 Team | Phase 2 · Apr 2027 – Jun 2027 | $1,600,000 | Not Started | 0% |
| 4.3 Validation & Pilot (Phase 3) |  |  |  |  |  |  |
| 4.3.1 | Independent model validation — pre-pilot certification | P. Okafor | Ph 2–3 · May 2027 – May 2027 | $900,000 | Not Started | 0% |
| 4.3.2 | Pilot go-live & pilot UAT | BRD-01 Lead | Phase 3 · Jun 2027 – Aug 2027 | $1,320,000 | Not Started | 0% |
| 4.4 Production Scale (Phase 4) |  |  |  |  |  |  |
| 4.4.1 | Full production scale | BRD-01 Lead | Phase 4 · Sep 2027 – Sep 2027 | $1,000,000 | Not Started | 0% |
| 4.4.2 | Hypercare & benefits baseline | BRD-01 Lead | Phase 4 · Sep 2027 – Sep 2027 | $300,000 | Not Started | 0% |

5.0  BRD-02 · Member & Provider Experience AI

Delivery · Y2 workstream · $13,200,000 total

| WBS ID | Work Package | Owner | Phase / Window | Budget | Status | % |
| --- | --- | --- | --- | --- | --- | --- |
| 5.1 Requirements & Design |  |  |  |  |  |  |
| 5.1.1 | JAD & requirements package | BRD-02 Lead | Y2 · Oct 2027 – Jan 2028 | $1,500,000 | Not Started | 0% |
| 5.1.2 | Conversational AI solution & model design | BRD-02 Lead | Y2 · Jan 2028 – Mar 2028 | $1,500,000 | Not Started | 0% |
| 5.2 Build & Test |  |  |  |  |  |  |
| 5.2.1 | Model development & training (sprints) | BRD-02 Team | Y2 · Feb 2028 – May 2028 | $4,000,000 | Not Started | 0% |
| 5.2.2 | Integration & system testing | BRD-02 Team | Y2 · Apr 2028 – Jun 2028 | $1,900,000 | Not Started | 0% |
| 5.3 Validation & Pilot |  |  |  |  |  |  |
| 5.3.1 | Independent model validation — pre-pilot certification | P. Okafor | Y2 · Apr 2028 – Apr 2028 | $1,100,000 | Not Started | 0% |
| 5.3.2 | Pilot go-live & pilot UAT | BRD-02 Lead | Y2 · Jun 2028 – Sep 2028 | $1,600,000 | Not Started | 0% |
| 5.4 Production Scale |  |  |  |  |  |  |
| 5.4.1 | Full production scale & hypercare | BRD-02 Lead | Y2 · Oct 2028 – Dec 2028 | $1,600,000 | Not Started | 0% |

6.0  BRD-03 · Underwriting & Risk AI

Delivery · Y2 workstream · $12,480,000 total

| WBS ID | Work Package | Owner | Phase / Window | Budget | Status | % |
| --- | --- | --- | --- | --- | --- | --- |
| 6.1 Requirements & Design |  |  |  |  |  |  |
| 6.1.1 | JAD & requirements package | BRD-03 Lead | Y2 · Oct 2027 – Jan 2028 | $1,400,000 | Not Started | 0% |
| 6.1.2 | Risk-scoring solution & model design | BRD-03 Lead | Y2 · Jan 2028 – Mar 2028 | $1,400,000 | Not Started | 0% |
| 6.2 Build & Test |  |  |  |  |  |  |
| 6.2.1 | Model development & training (sprints) | BRD-03 Team | Y2 · Feb 2028 – May 2028 | $3,600,000 | Not Started | 0% |
| 6.2.2 | Fairness / disparate-impact testing | BRD-03 Team + CoE | Y2 · Mar 2028 – Jun 2028 | $1,280,000 | Not Started | 0% |
| 6.3 Validation & Pilot |  |  |  |  |  |  |
| 6.3.1 | Independent model validation — pre-pilot cert (incl. fairness/bias audit) | P. Okafor | Y2 · Apr 2028 – Apr 2028 | $1,200,000 | Not Started | 0% |
| 6.3.2 | Pilot go-live & pilot UAT | BRD-03 Lead | Y2 · Jun 2028 – Sep 2028 | $1,500,000 | Not Started | 0% |
| 6.4 Production Scale |  |  |  |  |  |  |
| 6.4.1 | Full production scale & hypercare | BRD-03 Lead | Y2 · Oct 2028 – Dec 2028 | $2,100,000 | Not Started | 0% |

7.0  Optimization, Benefits & Closeout

Sustain · Y3 workstream · $15,800,000 total

| WBS ID | Work Package | Owner | Phase / Window | Budget | Status | % |
| --- | --- | --- | --- | --- | --- | --- |
| 7.1 Optimization & Sustain |  |  |  |  |  |  |
| 7.1.1 | Cross-BRD optimization & model tuning | Delivery Leads | Y3 · Jan 2029 – Jun 2029 | $4,200,000 | Not Started | 0% |
| 7.1.2 | Production sustain & hypercare (all 3 BRDs) | Delivery + CoE | Y3 · Jan 2029 – Aug 2029 | $3,600,000 | Not Started | 0% |
| 7.1.3 | Sustain-mode operating model & knowledge transfer | CoE + Delivery | Y3 · Apr 2029 – Aug 2029 | $3,000,000 | Not Started | 0% |
| 7.2 Benefits & Closeout |  |  |  |  |  |  |
| 7.2.1 | Benefits realization measurement & report | A. Rodriguez / PMO | Y3 · May 2029 – Jul 2029 | $2,800,000 | Not Started | 0% |
| 7.2.2 | Program closeout report & lessons-learned register | C. Tyrrell / T. Valdez | Y3 · Aug 2029 – Aug 2029 | $2,200,000 | Not Started | 0% |

Milestone Schedule

| Date | Milestone | Gate / Type | Status |
| --- | --- | --- | --- |
| 17 Aug 2026 | Program start / kickoff | Kickoff | Complete |
| 25 Sep 2026 | AI Readiness Assessment Report | Deliverable | Upcoming |
| 06 Nov 2026 | Phase 0 Gate — CoE Charter, Governance Framework v1, platform vendor signed | Phase Gate | Upcoming |
| 18 Dec 2026 | BRD-01 requirements sign-off (JAD complete) | Phase Gate | Upcoming |
| 12 Mar 2027 | Data & Cloud Platform Foundation go-live | Deliverable | Upcoming |
| 28 May 2027 | BRD-01 model validation certification (pre-pilot) | Validation | Upcoming |
| 25 Jun 2027 | BRD-01 pilot go-live | Go-Live | Upcoming |
| 30 Sep 2027 | BRD-01 full production scale | Go-Live | Upcoming |
| 01 Oct 2027 | Year 2 kickoff (BRD-02 / BRD-03) | Kickoff | Upcoming |
| 15 Jan 2028 | BRD-02 & BRD-03 requirements sign-off | Phase Gate | Upcoming |
| 15 Apr 2028 | BRD-02 & BRD-03 model validation certification | Validation | Upcoming |
| 30 Jun 2028 | BRD-02 & BRD-03 pilot go-live | Go-Live | Upcoming |
| 15 Dec 2028 | BRD-02 & BRD-03 full production scale | Go-Live | Upcoming |
| 15 Apr 2029 | Enterprise integration certification (all 3 BRDs) | Validation | Upcoming |
| 30 Jun 2029 | MLOps maturity uplift + full IMV re-certification | Validation | Upcoming |
| 31 Jul 2029 | Benefits Realization Report | Deliverable | Upcoming |
| 15 Aug 2029 | CoE steady-state transition & formal handover | Transition | Upcoming |
| 29 Aug 2029 | Program closeout & lessons learned | Closeout | Upcoming |

Illustrative program data for portfolio demonstration. Project Catalyst, ACME Highland Health AI Transformation Program. Prepared by Pulaski Advisory Group. Budget figures reconcile to the program cost baseline and annual SOW envelopes.