ATO Package — System Security Plan & POA&M

BenefitConnect Portal Modernization — Security authorization gate

The Authority to Operate (ATO) is the formal security sign-off required before BenefitConnect can go live in production. Owned by T. Abernathy (ISSO), reviewed by M. Whitcombe (COR), and formally granted by the agency's Authorizing Official.

## System Security Plan (SSP) — Summary

| Field | Value |
| --- | --- |
| System Categorization | Moderate (FIPS 199) — handles applicant PII but not classified data |
| Security Control Baseline | NIST SP 800-53 Moderate baseline |
| Assessment Method | Independent Security Control Assessment (SCA) by third-party assessor |
| Target ATO Date | Month 7 (Milestone Gate 1) |

## POA&M — Plan of Action & Milestones (Open Findings)

| Finding | Severity | Remediation Owner | Target Close | Status |
| --- | --- | --- | --- | --- |
| Session timeout exceeds moderate-baseline threshold | High | K. Lindqvist | Month 6 | Open |
| Audit logging gap on legacy data import path | Moderate | K. Lindqvist | Month 6 | Open |
| MFA not yet enforced for admin console | High | T. Abernathy | Month 5 | Closed |

## Why This Gate Matters for the Schedule

Every open High-severity POA&M finding is a direct risk to Milestone Gate 1. A federal PM's job here isn't to do the security work itself — it's to actively track POA&M burn-down against the schedule and escalate early if remediation is slipping, since an ATO delay is a hard go-live blocker, not a negotiable one.