## CDRL
BenefitConnect Portal Modernization — Contract Data Requirements List
CDRL # | Deliverable | Format | Due | Acceptance Authority | Status
A001 | Project Management Plan | PDF | Task Order + 30 days | COR | Accepted
A002 | Integrated Master Schedule (IMS) | MS Project / PDF | Task Order + 30 days | COR | Accepted
A003 | Risk Management Plan (RAIDD Log baseline) | PDF | Task Order + 30 days | COR | Accepted
A004 | Section 508 Test Plan | PDF | Task Order + 60 days | COR | Pending
A005 | System Security Plan (SSP) | PDF | Task Order + 90 days | ISSO / COR | Pending
A006 | Section 508 / VPAT Compliance Test Report | PDF + VPAT | Task Order + 180 days | COR | Pending
A007 | Authority to Operate (ATO) Package | PDF Package | Task Order + 210 days | Agency Authorizing Official | Pending
A008 | Monthly Status Report | PDF, monthly | 5th of each month | COR | Recurring — current
A009 | Data Migration Plan & Validation Report | PDF | Task Order + 150 days | COR | Pending
A010 | Task Order Closeout Report | PDF | End of Period of Performance | COR / CO | Pending
Total CDRL Items | 10
Accepted Count | 3