# Contract Modification Forms — All 10 Mods

Full modification document for each of the 10 contract mods on the BenefitConnect Portal Modernization Task Order.

## P00001 — Add Independent Section 508 Auditor to CDRL Process

| Field | Value |
| --- | --- |
| Type | Administrative / Scope Clarification |
| Requested By | M. Whitcombe (COR) |
| Date Submitted | 14 Feb 2026 |
| Date Decided | 21 Feb 2026 |
| Cost Impact | +$28,000 |
| Schedule Impact | None |
| CO Decision | Approved |

Description: Adds an independent, third-party Section 508 auditor to the CDRL A004 (Section 508/VPAT Compliance Test Report) and A006 (ATO Package) review process, at the COR's direction, to provide an accessibility opinion independent of Acme Federal Systems' own P. Duvall.

Justification: FOPBA's accessibility program office requested an independent second opinion on Section 508 conformance for any citizen-facing federal system, standard practice for public-facing portals of this size.

## P00002 — Extend Legacy Data Read-Access Dependency Window

| Field | Value |
| --- | --- |
| Type | Schedule Adjustment |
| Requested By | C. Tyrrell (Task Order PM) |
| Date Submitted | 03 Apr 2026 |
| Date Decided | 08 Apr 2026 |
| Cost Impact | $0 |
| Schedule Impact | +15 days to Milestone Gate 1 |
| CO Decision | Approved |

Description: Extends the dependency window for read-only access to the legacy CareLink-style database by 15 days, after FOPBA's internal IT team was delayed granting credentials to Acme's data migration team.

Justification: Without extended access, the data migration and validation tasks tied to Milestone Gate 1 could not start on schedule through no fault of the contractor team.

## P00003 — Align CDRL A007 Monthly Status Report Format

| Field | Value |
| --- | --- |
| Type | Administrative |
| Requested By | M. Whitcombe (COR) |
| Date Submitted | 22 May 2026 |
| Date Decided | 29 May 2026 |
| Cost Impact | $0 |
| Schedule Impact | None |
| CO Decision | Approved |

Description: Updates the format of CDRL A007 (Monthly Status Report) to match FOPBA's newly adopted agency-wide status reporting template, replacing the original task-order-specific format.

Justification: FOPBA standardized status reporting across all active IDIQ task orders; no change to reporting content or frequency, only the template.

## P00004 — Add Multi-Factor Authentication to Citizen Portal Login

| Field | Value |
| --- | --- |
| Type | Scope Addition (Security) |
| Requested By | T. Abernathy (ISSO) |
| Date Submitted | 10 Jun 2026 |
| Date Decided | 19 Jun 2026 |
| Cost Impact | +$45,000 |
| Schedule Impact | +5 days to ATO gate |
| CO Decision | Approved |

Description: Adds a Multi-Factor Authentication (MFA) requirement to the citizen-facing portal's login flow, following an updated OMB identity-assurance memo issued after contract award.

Justification: The updated OMB memo raises the required identity-assurance level for any federal system handling applicant PII — this Task Order's ATO could not be granted without it.

## P00005 — Extend ATO Authorization Bridge

| Field | Value |
| --- | --- |
| Type | Schedule Adjustment |
| Requested By | T. Abernathy (ISSO) |
| Date Submitted | 02 Jul 2026 |
| Date Decided | 09 Jul 2026 |
| Cost Impact | $0 |
| Schedule Impact | +30 days to go-live |
| CO Decision | Approved |

Description: Extends the interim authorization bridge by 30 days while the Authorizing Official completes final review of the ATO package (SSP + POA&M), pushing the planned go-live date.

Justification: The Authorizing Official's review queue was delayed by an unrelated agency-wide security incident response, outside the Task Order's control.

## P00006 — Add Automated Accessibility Regression Testing

| Field | Value |
| --- | --- |
| Type | Scope Addition (Section 508) |
| Requested By | P. Duvall (508 Lead) |
| Date Submitted | 18 Jul 2026 |
| Date Decided | 24 Jul 2026 |
| Cost Impact | +$18,000 |
| Schedule Impact | None |
| CO Decision | Approved |

Description: Adds an automated accessibility regression-testing tool license to run alongside manual VPAT testing on every release, rather than manual testing alone.

Justification: Manual-only testing could not keep pace once the front-end development team grew to two developers shipping more frequent UI changes — automated regression catches accessibility defects between manual test passes.

## P00007 — Reduce Data Migration Tooling Scope

| Field | Value |
| --- | --- |
| Type | Cost Decrease |
| Requested By | H. Ibrahim (Back-End Developer) |
| Date Submitted | 05 Aug 2026 |
| Date Decided | 12 Aug 2026 |
| Cost Impact | -$12,000 |
| Schedule Impact | None |
| CO Decision | Approved |

Description: Reduces the planned Data Migration Tooling spend after the legacy vendor provided a cleaner, better-structured data export than originally scoped, requiring less custom transformation tooling.

Justification: Passing a genuine cost savings back to the government rather than retaining the original tooling budget for work that turned out to be unnecessary.

## P00008 — Add Disaster Recovery / COOP Testing

| Field | Value |
| --- | --- |
| Type | Scope Addition |
| Requested By | S. Vance (DevOps / Cloud Engineer) |
| Date Submitted | 20 Aug 2026 |
| Date Decided | 27 Aug 2026 |
| Cost Impact | +$35,000 |
| Schedule Impact | None |
| CO Decision | Approved |

Description: Adds a Disaster Recovery / Continuity of Operations (COOP) test to the Cloud Hosting line, verifying the portal can fail over to a secondary region within FOPBA's required recovery time objective.

Justification: COOP testing was implied but not explicitly priced in the original PWS; FOPBA's COR asked for it to be made explicit and billed rather than absorbed informally.

## P00009 — Correct Business Analyst Labor Category Title

| Field | Value |
| --- | --- |
| Type | Administrative |
| Requested By | A. Reyes (Contracting Officer) |
| Date Submitted | 03 Sep 2026 |
| Date Decided | 10 Sep 2026 |
| Cost Impact | $0 |
| Schedule Impact | None |
| CO Decision | Approved |

Description: Corrects J. Okonkwo's labor category title from "Business Analyst" to FOPBA's standard labor category taxonomy term, "Requirements Analyst II," to match the IDIQ's labor category schedule exactly.

Justification: A labor-category audit found the Task Order's invoicing used an informal title not present on the HSS-IDIQ labor category schedule — corrected for invoicing consistency, no change to role, rate, or duties.

## P00010 — Exercise Option Period

| Field | Value |
| --- | --- |
| Type | Option Exercise |
| Requested By | A. Reyes (Contracting Officer) |
| Date Submitted | 15 Sep 2026 |
| Date Decided | 22 Sep 2026 |
| Cost Impact | $0 (pre-priced at award) |
| Schedule Impact | +6 months period of performance |
| CO Decision | Approved |

Description: Formally exercises the Task Order's 6-month Option Period, pre-priced at contract award, extending the period of performance and continuing the delivery team's sustainment and Continuous ATO Monitoring support.

Justification: FOPBA elected to exercise the pre-priced option rather than recompete, based on satisfactory Base Period performance documented in CDRL deliverable acceptances.