## Slide 1
TASK ORDER KICKOFF · DAY 1
BenefitConnect Portal
Modernization
Eighteen months. One ATO. A citizen-facing portal that finally meets Section 508 — here's how we get there.
May 18, 2026
Kickoff Date
C. Tyrrell
Task Order PM
13
Team Members
1

## Slide 2
AGENDA
What We'll Cover Today
1
Welcome & Task Order Context
2
Why This Task Order Matters
3
Objectives & Success Criteria
4
Scope: In and Out
5
The Delivery Team
6
Milestone Timeline
7
Budget Overview
8
How We'll Work Together
9
Risks We're Watching
10
Next Steps & Q&A
2

## Slide 3
WELCOME
Glad You're Here
Thirteen people, one contracting officer, and eighteen months to get a citizen-facing system to ATO.
Acme Federal Systems' delivery team and FOPBA's Program Office are aligning today on scope, the ATO and Section 508 compliance strategy, and working cadence before requirements work begins. Quick round of introductions: name, role, and what you're most excited (or nervous) about.
13
NAMED TEAM MEMBERS
18
MONTHS, BASE + OPTION
100%
ONSHORE STAFFING
3

## Slide 4
THE BUSINESS CASE
Why We're Doing This
The legacy portal's compensating security and accessibility controls cost more every year than fixing the platform once.
FOPBA's legacy benefits enrollment portal runs on an unsupported COTS platform that can't meet Section 508 or federal ATO requirements without significant remediation. This Task Order modernizes BenefitConnect: legacy data migration, a Section 508/WCAG-conformant rebuild, and a full ATO package — full detail in the Task Order Charter.
$3.55M
APPROVED BASELINE (FFP)
Month 8
TARGET GO-LIVE
4

## Slide 5
OBJECTIVES
What Success Looks Like
1
Full Section 508/VPAT conformance before Milestone Gate 1
2
ATO with zero open Critical/High security findings at Gate 1
3
Legacy data migrated with full field-level validation before cutover
4
Completed within the FFP baseline and approved Period of Performance
5
Satisfactory-or-better CPARS rating to justify the Option Period
5

## Slide 6
SCOPE
Where the Lines Are
IN SCOPE
Legacy applicant/enrollment data migration and validation
Section 508/WCAG-conformant portal rebuild
Full ATO package: SSP, SCA, POA&M, supporting CDRLs
Cloud hosting/infrastructure, incl. DR/COOP testing
MFA and identity-assurance controls per current OMB guidance
OUT OF SCOPE
Any FOPBA system outside the BenefitConnect portal
Ongoing O&M beyond the Option Period absent a follow-on Task Order
Policy or eligibility-rules changes not required by the modernization
6

## Slide 7
THE DELIVERY TEAM
Everyone Who's Building This
C. Tyrrell
Task Order PM
D. Ferris
Deputy Task Order PM
K. Lindqvist
Solutions Architect / Tech Lead
COMPLIANCE & SECURITY
T. Abernathy
ISSO (ATO Owner)
P. Duvall
Section 508 Lead
N. Castellano
QA Lead
DEVELOPMENT
E. Marston
Front-End Developer
R. Colville
Front-End Developer
H. Ibrahim
Back-End Developer
G. Petrov
Back-End Developer
DELIVERY SUPPORT
J. Okonkwo
Business Analyst
S. Vance
DevOps / Cloud Engineer
A. Byrne
QA Tester
All 13, 100% onshore per the PII/ATO requirement — same roster as the Resource Plan and Org Chart.
7

## Slide 8
TIMELINE
The Road to Go-Live
Kickoff
May 18
System Security Plan
Month 3
508/VPAT Testing
Month 6
ATO Milestone Gate
Month 7
Production Go-Live
Month 8
Task Order Closeout
Month 18
Full CDRL-by-CDRL schedule: CDRL Schedule
8

## Slide 9
BUDGET
Where the Money Goes
Chart: 
| Labor — Delivery Team (13) | Cloud Hosting / Infrastructure | Independent 508 Audit | Security Assessment / MFA / Tooling
Budget | 3070 | 225 | 85 | 170
$3.55M
FFP BASELINE
Every dollar above baseline requires a signed Contract Modification — no verbal or informal scope changes are recognized on this Task Order.
Full detail and the 13-person rate card: Resource Plan
9

## Slide 10
WORKING TOGETHER
How We'll Stay in Sync
Cadence | Forum | Purpose
Weekly | Delivery Standup | Internal, contractor-only — status & blockers
Bi-weekly | COR Sync | CDRL status, open issues, upcoming deliverables
Monthly | Status Report (CDRL A007) | Formal written deliverable to the COR
Quarterly | Program Review | Mission-outcome and business-case check-in
Full governance model and Contract Modification process: Program Governance Model
10

## Slide 11
EYES OPEN
Risks We're Watching From Day One
!
ATO assessment could surface a finding that delays Milestone Gate 1
Highest-rated risk at Charter approval
!
Legacy applicant data has known formatting inconsistencies
Could complicate migration validation
!
All-onshore staffing limits surge capacity if a resource attrites
No offshore substitution permitted, regardless of severity
!
Contract modification growth could mask scope creep if not tracked
Watched against the original PWS baseline
Full risk register: RAIDD Log
11

## Slide 12
NEXT STEPS
What Happens Next
1
PMP and IMS Baseline (CDRL A001/A002) due within Month 1
2
Legacy system read-access request submitted to FOPBA IT
3
Pre-assessment ATO scan planning begins now, ahead of the Month 7 gate
12

## Slide 13
Let's Get This to ATO, Together.
C. Tyrrell, Task Order PM
BenefitConnect Portal Modernization
13