Lessons Learned Register

BenefitConnect Portal Modernization · FOPBA · HSS-IDIQ Task Order 3 · Acme Federal Systems

| Lessons Captured | 10 (8 Improvement, 2 Positive Practice) |
| --- | --- |
| Recommendations Implemented | 10 of 10 |
| Maintained By | C. Tyrrell, Task Order PM |
| Purpose | Living register maintained through Task Order performance, summarized in the Task Order Closeout Report |

Each entry separates what happened (factual, blame-free) from root cause from recommendation, adapted for federal-specific dynamics: ATO/RMF timing, Section 508 conformance, CDRL acceptance cycles, and IDIQ Task Order modification practice.

LL-01 — ATO / Security Authorization

Phase: Planning   ·   Owner: T. Abernathy   ·   Status: Implemented

What Happened: The Independent Security Control Assessment (SCA) needed for the ATO package was not scheduled until after substantial development, compressing the remediation window before planned cutover.

Root Cause: The IMS treated ATO/RMF authorization as a single late-stage milestone rather than a parallel workstream needing its own lead time.

Impact: Contributed to R-01 on the RAIDD Log; SCA vendor's earliest slot left only six weeks before go-live for remediation.

Recommendation: Schedule the SCA as its own IMS workstream from kickoff, independent of the development schedule.

LL-02 — Section 508 Compliance

Phase: Execution (Build)   ·   Owner: P. Duvall   ·   Status: Implemented

What Happened: Automated accessibility scanning missed keyboard-navigation and screen-reader defects in custom UI components, caught only during late manual assistive-technology testing.

Root Cause: Section 508 test planning assumed automated scanning gave sufficient coverage; manual AT testing was scoped as a final pass, not continuous alongside development.

Impact: About two weeks of rework on custom form components, absorbed within Testing phase float.

Recommendation: Require manual assistive-technology testing at the point each custom component is built, not only in a final accessibility pass.

LL-03 — CDRL / Deliverable Acceptance

Phase: Execution   ·   Owner: D. Ferris   ·   Status: Implemented

What Happened: Two early CDRL submissions (A002, A005) were returned by the COR for revision — wrong format and missing version control metadata.

Root Cause: The team read the CDRL Format column informally rather than as a literal, binding requirement; no internal check compared drafts to CDRL specs before submission.

Impact: Each resubmission cycle took about one week, consumed from schedule float with no contract impact.

Recommendation: Add a deliverable quality-check step against the CDRL's exact Format and content requirements before any COR submission.

LL-04 — Contract Modifications

Phase: Execution   ·   Owner: C. Tyrrell   ·   Status: Implemented

What Happened: Modification P00001 took longer than expected because the CO required a fully costed, FAR-compliant proposal before beginning review.

Root Cause: The team expected a scope change to move quickly once verbally agreed; federal modifications require a fully documented, costed proposal regardless of informal agreement.

Impact: Added about ten days to P00001's execution timeline; no overall Task Order schedule impact.

Recommendation: Prepare the full costed modification proposal package before treating informal government agreement as sufficient to begin work.

LL-05 — Governance / COR-CO Roles

Phase: Initiation   ·   Owner: C. Tyrrell   ·   Status: Implemented

What Happened: A proposed scope clarification was routed directly to the CO rather than the COR, assuming any government contact could address it.

Root Cause: Onboarding did not include explicit guidance on the COR/CO distinction.

Impact: The CO redirected the request to the COR, adding about three days versus a same-day clarification; no cost impact.

Recommendation: Include an explicit COR-vs-CO routing guide in Task Order kickoff onboarding, with concrete examples.

LL-06 — Staffing Compliance   ★ Positive Practice

Phase: Planning   ·   Owner: T. Abernathy   ·   Status: Implemented

What Happened: The team proactively confirmed with the ISSO that FOPBA data-handling and ATO requirements mandate an all-onshore, US-person delivery team before any staffing decisions were made.

Root Cause: The PM applied a lesson from prior programs — verify compliance-driven staffing constraints during planning, not after commitments are made.

Impact: Positive — avoided unwinding an offshore staffing decision mid-Task-Order, which would have required contract and clearance rework.

Recommendation: Confirm onshore/US-person staffing requirements with the ISSO during Resource Plan drafting, before any staffing commitments.

LL-07 — Status Reporting

Phase: Execution   ·   Owner: D. Ferris   ·   Status: Implemented

What Happened: The first two Monthly Status Reports used commercial terminology (“sprint,” “burndown”) that did not map to the COR's expectations for federal reporting.

Root Cause: The Status Report template was adapted from the Agile suite's format without confirming what the COR's office actually expected.

Impact: The COR requested a revised format aligned to CDRL milestones and PWS deliverables; no schedule or cost impact, one extra review cycle.

Recommendation: Confirm the government stakeholder's expected reporting format and terminology during Communications Plan development.

LL-08 — Risk Management   ★ Positive Practice

Phase: Planning   ·   Owner: C. Tyrrell   ·   Status: Implemented

What Happened: The team pre-identified Section 508 conformance testing as a High risk during Planning and pre-negotiated a dedicated QASP surveillance checkpoint for it.

Root Cause: P. Duvall's early involvement in Planning let the team treat accessibility as a named governance risk from the start.

Impact: Positive — the dedicated surveillance checkpoint caught the LL-02 defects early enough that no modification or schedule slip resulted.

Recommendation: For any Task Order with a named compliance differentiator, name a specific QASP surveillance checkpoint during Planning and involve the compliance lead from kickoff.

LL-09 — Data Quality / Legacy Migration

Phase: Planning   ·   Owner: K. Lindqvist   ·   Status: Implemented

What Happened: Legacy applicant data was found to have inconsistent formatting that complicated migration validation planning, identified as R-02 on the RAIDD Log during Planning rather than earlier in proposal development.

Root Cause: The proposal-stage estimate for CDRL A009 (Data Migration Cutover) assumed the legacy system's documentation was representative of actual production data, without profiling a real sample before the Task Order was priced.

Impact: Extends the CDRL A009 timeline and carries data-quality rework risk during Build; tracked as R-02.

Recommendation: Profile a representative sample of actual production data during proposal development, before pricing and scheduling the migration CDRL.

LL-10 — COR Review Turnaround

Phase: Execution   ·   Owner: C. Tyrrell   ·   Status: Implemented

What Happened: COR review turnaround on CDRL A001 (Project Management Plan) ran five business days over the cadence implied by the QASP, tracked as I-01 on the RAIDD Log.

Root Cause: The QASP describes expected review effort and inspection method per CDRL item but does not commit the COR's office to a specific turnaround-time service level.

Impact: Minor schedule compression on downstream deliverables tied to CDRL A001 sign-off; no cost impact, absorbed within schedule float.

Recommendation: Raise expected CDRL review cadence explicitly with the COR during Communications Plan development, and build a modest schedule buffer around early CDRL submissions.