## WBS
BenefitConnect Portal Modernization — Work Breakdown Structure
Full export from the program schedule — 48 line items across 8 phases, 13 named assignees.
WBS ID | Task Name | Start | Finish | Duration (d) | % Complete | Assigned To | Milestone
1 | 1.0 Task Order Kickoff & Mobilization | 2026-02-02 | 2026-02-17 | 0 | 100
1.1 | Contract kickoff meeting | 2026-02-02 | 2026-02-02 | 1 | 100 | C. Tyrrell, D. Ferris
1.2 | Staffing onboarding (all 13 roles) | 2026-02-03 | 2026-02-09 | 5 | 100 | D. Ferris
1.3 | Project Management Plan (CDRL A001) | 2026-02-10 | 2026-02-16 | 5 | 100 | C. Tyrrell
1.4 | IMS Baseline (CDRL A002) | 2026-02-10 | 2026-02-12 | 3 | 100 | D. Ferris
1.5 | Milestone: Kickoff & Baseline Complete | 2026-02-17 | 2026-02-17 | 0 | 100 | C. Tyrrell | Yes
2 | 2.0 Requirements & Solution Architecture | 2026-02-18 | 2026-04-15 | 0 | 100
2.1 | Requirements gathering workshops | 2026-02-18 | 2026-03-09 | 14 | 100 | J. Okonkwo
2.2 | Solution architecture design | 2026-03-10 | 2026-04-02 | 18 | 100 | K. Lindqvist
2.3 | ATO-compliant cloud environment provisioning | 2026-04-03 | 2026-04-13 | 7 | 100 | S. Vance
2.4 | Section 508 Test Plan (CDRL A004) | 2026-04-03 | 2026-04-09 | 5 | 100 | P. Duvall
2.5 | UI/UX wireframes and design system | 2026-04-03 | 2026-04-14 | 8 | 100 | E. Marston
2.6 | Milestone: Architecture & Environment Ready | 2026-04-15 | 2026-04-15 | 0 | 100 | K. Lindqvist | Yes
3 | 3.0 Development & Data Migration Build | 2026-04-03 | 2026-07-31 | 0 | 52
3.1 | Front-end component library build | 2026-04-16 | 2026-05-06 | 15 | 60 | E. Marston
3.2 | Front-end citizen portal UI build | 2026-05-07 | 2026-06-17 | 30 | 60 | R. Colville
3.3 | Back-end API development | 2026-04-16 | 2026-06-03 | 35 | 60 | H. Ibrahim
3.4 | Back-end data migration pipeline | 2026-06-04 | 2026-07-08 | 25 | 60 | G. Petrov
3.5 | CI/CD pipeline setup | 2026-04-14 | 2026-04-21 | 6 | 100 | S. Vance
3.6 | System Security Plan / SSP (CDRL A005) | 2026-04-03 | 2026-04-30 | 20 | 60 | T. Abernathy
3.7 | Developer unit testing (front-end + back-end) | 2026-07-09 | 2026-07-20 | 8 | 60 | E. Marston, H. Ibrahim
3.8 | Functional test case development | 2026-04-10 | 2026-04-17 | 6 | 60 | N. Castellano
3.9 | Functional test execution | 2026-07-21 | 2026-07-30 | 8 | 0 | A. Byrne
3.10 | Milestone: Build Complete | 2026-07-31 | 2026-07-31 | 0 | 0 | C. Tyrrell | Yes
4 | 4.0 Section 508 / VPAT Testing (CDRL A006) | 2026-08-03 | 2026-08-18 | 0 | 0
4.1 | Automated accessibility regression testing | 2026-08-03 | 2026-08-06 | 4 | 0 | A. Byrne
4.2 | Manual VPAT testing | 2026-08-03 | 2026-08-10 | 6 | 0 | P. Duvall
4.3 | Independent 508 audit remediation (Mod P00001) | 2026-08-11 | 2026-08-17 | 5 | 0 | E. Marston
4.4 | Milestone: Section 508 Conformance Accepted | 2026-08-18 | 2026-08-18 | 0 | 0 | P. Duvall | Yes
5 | 5.0 ATO Security Assessment & Package (CDRL A007) | 2026-05-01 | 2026-08-19 | 0 | 0
5.1 | Security Assessment Report | 2026-05-01 | 2026-05-21 | 15 | 0 | T. Abernathy
5.2 | POA&M development | 2026-05-22 | 2026-06-02 | 8 | 0 | T. Abernathy
5.3 | ATO package submission | 2026-06-03 | 2026-06-05 | 3 | 0 | T. Abernathy
5.4 | Milestone Gate: ATO Granted | 2026-08-19 | 2026-08-19 | 0 | 0 | T. Abernathy | Yes
6 | 6.0 Data Migration Cutover (CDRL A009) | 2026-08-20 | 2026-09-15 | 0 | 0
6.1 | Data migration validation | 2026-08-20 | 2026-09-02 | 10 | 0 | G. Petrov
6.2 | Regression testing (full suite) | 2026-09-03 | 2026-09-10 | 6 | 0 | N. Castellano, A. Byrne
6.3 | Cutover execution | 2026-09-11 | 2026-09-14 | 2 | 0 | S. Vance
6.4 | Milestone Gate: Production Go-Live | 2026-09-15 | 2026-09-15 | 0 | 0 | C. Tyrrell | Yes
7 | 7.0 Stabilization Support (Option Period) | 2026-09-16 | 2027-07-22 | 0 | 0
7.1 | Sustainment development support | 2026-09-16 | 2027-07-13 | 215 | 0 | E. Marston, H. Ibrahim
7.2 | Continuous ATO monitoring | 2026-09-16 | 2027-07-22 | 222 | 0 | T. Abernathy
7.3 | Regression support testing | 2026-09-16 | 2027-07-13 | 215 | 0 | N. Castellano, A. Byrne
7.4 | Infrastructure sustainment | 2026-09-16 | 2027-07-22 | 222 | 0 | S. Vance
8 | 8.0 Task Order Closeout (CDRL A010) | 2027-07-23 | 2027-08-02 | 0 | 0
8.1 | Final CDRL reconciliation & acceptance | 2027-07-23 | 2027-07-27 | 3 | 0 | D. Ferris
8.2 | Closeout Report & Lessons Learned | 2027-07-28 | 2027-07-30 | 3 | 0 | C. Tyrrell
8.3 | Milestone: Task Order Closed | 2027-08-02 | 2027-08-02 | 0 | 0 | C. Tyrrell | Yes