# Task Order Resource Plan

Named delivery-team roster for the BenefitConnect Portal Modernization Task Order, showing FTE
  allocation, location, blended hourly rate, and period labor cost — reconciled line-for-line to the Task Order Budget 's Labor — Delivery Team figures
  for both the Base and Option periods.

All-onshore staffing is a compliance requirement here, not a cost choice: FOPBA
  applicant PII and the system's ATO/RMF security authorization require every delivery-team member to be a
  US person working onshore. Unlike the Agile suite's commercial team, there is no offshore allocation on this
  Task Order.

## Base Period (12 months)

| Name | Role | Location | FTE % | Base Hours | Blended Rate | Base Cost |
| --- | --- | --- | --- | --- | --- | --- |
| C. Tyrrell | Task Order PM | Onshore (US) | 100% | 2,080 | $112.98 | $235,000 |
| D. Ferris | Deputy PM | Onshore (US) | 100% | 2,080 | $98.56 | $205,000 |
| K. Lindqvist | Solutions Architect / Tech Lead | Onshore (US) | 100% | 2,080 | $108.17 | $225,000 |
| T. Abernathy | ISSO (ATO Package Owner) | Onshore (US) | 100% | 2,080 | $93.75 | $195,000 |
| P. Duvall Base only | Section 508 / Accessibility Compliance Lead | Onshore (US) | 60% | 1,248 | $84.13 | $105,000 |
| N. Castellano | QA Lead | Onshore (US) | 80% | 1,664 | $93.15 | $155,000 |
| J. Okonkwo Base only | Business Analyst | Onshore (US) | 75% | 1,560 | $76.92 | $120,000 |
| E. Marston | Front-End Developer | Onshore (US) | 100% | 2,080 | $91.35 | $190,000 |
| R. Colville Base only | Front-End Developer | Onshore (US) | 100% | 2,080 | $86.54 | $180,000 |
| H. Ibrahim | Back-End Developer | Onshore (US) | 100% | 2,080 | $96.15 | $200,000 |
| G. Petrov Base only | Back-End Developer | Onshore (US) | 100% | 2,080 | $91.35 | $190,000 |
| S. Vance | DevOps / Cloud Engineer | Onshore (US) | 80% | 1,664 | $90.14 | $150,000 |
| A. Byrne | QA Tester (Manual/Regression) | Onshore (US) | 100% | 2,080 | $67.31 | $140,000 |
| Total Base Period Labor | $2,290,000 |

## Option Period (6 months)

| Name | Role | Location | FTE % | Option Hours | Blended Rate | Option Cost |
| --- | --- | --- | --- | --- | --- | --- |
| C. Tyrrell | Task Order PM | Onshore (US) | 100% | 1,040 | $125.00 | $130,000 |
| D. Ferris | Deputy PM | Onshore (US) | 50% | 520 | $105.77 | $55,000 |
| K. Lindqvist | Solutions Architect / Tech Lead | Onshore (US) | 50% | 520 | $115.38 | $60,000 |
| T. Abernathy | ISSO (Continuous Monitoring) | Onshore (US) | 100% | 1,040 | $96.15 | $100,000 |
| N. Castellano | QA Lead (Regression Support) | Onshore (US) | 50% | 520 | $144.23 | $75,000 |
| E. Marston | Front-End Developer (Sustainment) | Onshore (US) | 50% | 520 | $173.08 | $90,000 |
| H. Ibrahim | Back-End Developer (Sustainment) | Onshore (US) | 50% | 520 | $192.31 | $100,000 |
| S. Vance | DevOps / Cloud Engineer (Sustainment) | Onshore (US) | 50% | 520 | $182.69 | $95,000 |
| A. Byrne | QA Tester (Regression Support) | Onshore (US) | 50% | 520 | $144.23 | $75,000 |
| Total Option Period Labor | $780,000 |

## Reconciliation to Task Order Budget

| Period | Resource Plan Total | Task Order Budget | Variance |
| --- | --- | --- | --- |
| Base Period (12 mo.) | $2,290,000 | $2,290,000 | $0 |
| Option Period (6 mo.) | $780,000 | $780,000 | $0 |
| Total (Base + Option) | $3,070,000 | $3,070,000 | $0 |

Blended Hourly Rate is a fully loaded internal cost-recovery rate — salary, fringe,
  overhead, and G&A — not a billing rate to the government. This roster grew from an earlier 7-person
  leadership-only plan to 13 people once realistic build/test capacity was worked through: the original
  plan had a Solutions Architect, an ISSO, a 508 Lead, a QA Lead, and a BA, but no developers at all to
  actually build the portal. Front-end (E. Marston, R. Colville), back-end (H. Ibrahim, G. Petrov), a
  DevOps/Cloud Engineer (S. Vance), and a second QA Tester (A. Byrne) were added to reflect the team a
  build of this size genuinely requires. R. Colville and G. Petrov roll off at the end of Base once initial
  build and data migration are complete; the remaining developers continue at reduced allocation through
  the Option period for sustainment and defect-fix support.