## Resource Plan
BenefitConnect Portal Modernization — Task Order Resource Plan | [7 empty] | Base Period Hours (12 mo x 2,080 hrs, 100% FTE): | 2080
FOPBA · HSS-IDIQ Task Order 3 · Acme Federal Systems · Firm-Fixed-Price | [7 empty] | Option Period Hours (6 mo x 1,040 hrs, 100% FTE): | 1040
Period | Name | Role | Location | FTE % | Period Hours | Blended Hourly Rate ($) | Period Cost ($)
Base Period (12 mo.) | C. Tyrrell | Task Order PM | Onshore (US) | 100% | 2080 | 112.9808 | 235000
Base Period (12 mo.) | D. Ferris | Deputy PM | Onshore (US) | 100% | 2080 | 98.5577 | 205000
Base Period (12 mo.) | K. Lindqvist | Solutions Architect / Tech Lead | Onshore (US) | 100% | 2080 | 108.1731 | 225000
Base Period (12 mo.) | T. Abernathy | ISSO (ATO Package Owner) | Onshore (US) | 100% | 2080 | 93.75 | 195000
Base Period (12 mo.) | P. Duvall | Section 508 / Accessibility Compliance Lead | Onshore (US) | 60% | 1248 | 84.1346 | 105000
Base Period (12 mo.) | N. Castellano | QA Lead | Onshore (US) | 80% | 1664 | 93.149 | 155000
Base Period (12 mo.) | J. Okonkwo | Business Analyst | Onshore (US) | 75% | 1560 | 76.9231 | 120000
Option Period (6 mo.) | C. Tyrrell | Task Order PM | Onshore (US) | 100% | 1040 | 125 | 130000
Option Period (6 mo.) | D. Ferris | Deputy PM | Onshore (US) | 50% | 520 | 105.7692 | 55000
Option Period (6 mo.) | K. Lindqvist | Solutions Architect / Tech Lead | Onshore (US) | 50% | 520 | 115.3846 | 60000
Option Period (6 mo.) | T. Abernathy | ISSO (Continuous Monitoring) | Onshore (US) | 100% | 1040 | 96.1538 | 100000
Option Period (6 mo.) | N. Castellano | QA Lead (Regression Support) | Onshore (US) | 50% | 520 | 144.2308 | 75000
Reconciliation to Task Order Budget (Labor — Delivery Team)
Period | Resource Plan Total ($) | Task Order Budget ($) | Variance ($)
Base Period (12 mo.) | 1240000 | 1240000 | 0
Option Period (6 mo.) | 420000 | 420000 | 0
Total Reconciled Labor (Base + Option) | 1660000 | 1660000
Note: Blended Hourly Rate is a fully loaded internal cost-recovery rate (salary, fringe, overhead, and fee), consistent with the Labor — Delivery Team line in the Task Order Budget. No offshore labor is used on this Task Order: FOPBA applicant PII handling and ATO/RMF security authorization require an all-onshore (US-person) delivery team. P. Duvall and J. Okonkwo roll off at the end of the Base Period once Section 508 certification and requirements baselining are complete. Figures are illustrative for portfolio demonstration purposes.