## Slide 1
SLIDE 1 — PROGRAM SNAPSHOT
BenefitConnect Portal Modernization — Steering Update
Agency: FOPBA
Contractor: Acme Federal Systems
Vehicle: HSS-IDIQ, Task Order 3
Status: Amber

## Slide 2
SLIDE 2 — STATUS SUMMARY
Where We Stand
3 of 10 CDRLs accepted. Budget tracking Green (Firm-Fixed-Price). Schedule Amber, driven by an open ATO security finding tracked as Risk R-01. Section 508 accessibility testing on track.

## Slide 3
SLIDE 3 — RISKS REQUIRING SPONSOR AWARENESS
Top Risks
R-01: ATO security finding may delay Milestone Gate 1 (Authority to Operate)
R-02: Legacy applicant data quality may extend migration validation effort

## Slide 4
SLIDE 4 — FINANCIALS
Budget & Contract Actions
Total Firm-Fixed-Price value: $2,140,000. One contract modification processed (P00001, +$28,000, COR-directed scope clarification for independent Section 508 auditing). No cost growth beyond approved mods.

## Slide 5
SLIDE 5 — PATH TO GO-LIVE
Upcoming Milestones
Milestone Gate 1 — Authority to Operate Granted: Month 7
Milestone Gate 2 — Production Go-Live: Month 8
Option Period exercise decision: Month 12