# Resource-Loaded WBS

This is the resource-loaded view of the Task Order's Work Breakdown Structure. Every work package carries its named effort and cost, every hour traces to a named person on the Resource Plan, and — because this is a federal task order — effort is split by contractual period: the 12-month Base Period and the 6-month Option Period are priced, funded and reported separately, so loading them as one undifferentiated pool would misrepresent the contract.

225 WBS line items

194 Loaded work packages

35 Named resources

351 Assignments

74,984 Total effort (h)

$6,960,000 Total labor

# 1. How this WBS is loaded

Each work package names one accountable owner plus any named contributors. The distinction is not cosmetic: on a task order where the Government surveils performance through the QASP, a package with three names and no single answerable owner is a package with no one to hold to the standard.

The loading is allocation-aware. Each person's hours come from their Resource Plan line, which already carries their FTE percentage — and on this Task Order those vary widely (100%, 80%, 75%, 60%, 50%, 25%). A resource at 50% FTE is loaded at 50% capacity, not quietly modelled as though they were full-time. Hours are then distributed across the packages they work on in proportion to package duration.

Cost is distributed, not recomputed. Blended rates in the Resource Plan are rounded for presentation (2,080 hours at $112.98 is $234,998.40, but the line reads $235,000). Recomputing cost from rate × hours would therefore drift from the contract by a few dollars per person and by thousands across the roster. Each person's stated cost is allocated instead, so the total ties to the penny.

# 2. Effort & cost by contractual period

| Period | Duration | Resources | Packages | Effort (h) | Labor cost |
| --- | --- | --- | --- | --- | --- |
| Base Period | 12 months | 35 | 164 | 66,144 | $5,750,000 |
| Option Period | 6 months | 17 | 30 | 8,840 | $1,210,000 |
| Total | 18 months | 35 | 194 | 74,984 | $6,960,000 |

The Option Period is deliberately smaller and differently shaped: it covers post-launch stabilization, so it draws 17 of the 35 resources rather than the full team, and its packages sit in the cutover, stabilization and closeout phases. Several people carry a lower FTE in the Option Period than in the Base Period — the ramp-down is priced into the contract, and this view shows it rather than assuming a flat team.

# 3. Reconciliation

| Check | Value | Result |
| --- | --- | --- |
| Base Period distributed effort / cost | 66,144 h / $5,750,000 | = Resource Plan Base total ✓ |
| Option Period distributed effort / cost | 8,840 h / $1,210,000 | = Resource Plan Option total ✓ |
| Combined | 74,984 h / $6,960,000 | = Task Order Budget labor, $0 variance ✓ |
| Per-resource, per-period | 35 of 35 | each equals that person's roster line exactly ✓ |

These are assertions the generator evaluates, not totals typed into a table — it refuses to emit this page if any of them fails. The $0 variance shown in the Resource Plan's own reconciliation table is reproduced here from the opposite direction: that table compares plan to budget, this one rebuilds the plan from the work packages up.

# 4. Effort & cost by phase

| WBS | Phase | Packages | Effort (h) | Labor cost | % of total |
| --- | --- | --- | --- | --- | --- |
| 1 | Task Order Kickoff & Mobilization | 28 | 4,866 | $492,612 | 7.1% |
| 2 | Requirements & Solution Architecture | 46 | 8,934 | $789,971 | 11.4% |
| 3 | Development & Data Migration Build | 50 | 35,017 | $3,017,101 | 43.3% |
| 3B | Documentation & Training Materials | 4 | 2,872 | $225,700 | 3.2% |
| 4 | Section 508 / VPAT Testing (CDRL A006) | 12 | 4,586 | $364,106 | 5.2% |
| 5 | ATO Security Assessment & Package (CDRL A007) | 14 | 5,930 | $518,966 | 7.5% |
| 6 | Data Migration Cutover (CDRL A009) | 15 | 3,971 | $346,061 | 5.0% |
| 7 | Stabilization Support (Option Period) | 19 | 8,205 | $1,140,027 | 16.4% |
| 8 | Task Order Closeout (CDRL A010) | 6 | 603 | $65,456 | 0.9% |
| — | Task Order total | 194 | 74,984 | $6,960,000 | 100.0% |

# 5. Resource loading by person

| Resource | Role | FTE % | Periods | Hours | Cost | Packages |
| --- | --- | --- | --- | --- | --- | --- |
| C. Tyrrell | Task Order PM | 100% / 100% | Base+Option | 3,120 | $365,000 | 18 |
| H. Ibrahim | Back-End Developer | 100% / 50% | Base+Option | 2,600 | $300,000 | 5 |
| S. Larsen | Back-End Developer (Eligibility API) | 100% / 50% | Base+Option | 2,600 | $300,000 | 5 |
| T. Abernathy | ISSO (ATO Package Owner) | 100% / 100% | Base+Option | 3,120 | $295,000 | 17 |
| K. Lindqvist | Solutions Architect / Tech Lead | 100% / 50% | Base+Option | 2,600 | $285,000 | 17 |
| E. Marston | Front-End Developer | 100% / 50% | Base+Option | 2,600 | $280,000 | 7 |
| P. Manning | QA Automation Engineer | 100% / 50% | Base+Option | 2,600 | $276,000 | 4 |
| R. Nakashima | Front-End Developer (Mobile Redesign) | 100% / 50% | Base+Option | 2,600 | $275,000 | 4 |
| D. Ferris | Deputy PM | 100% / 50% | Base+Option | 2,600 | $260,000 | 18 |
| D. Vasquez | Security Engineer (API Integration Review) | 100% / 50% | Base+Option | 2,600 | $250,000 | 4 |
| S. Vance | DevOps / Cloud Engineer | 80% / 50% | Base+Option | 2,184 | $245,000 | 11 |
| N. Castellano | QA Lead | 80% / 50% | Base+Option | 2,184 | $230,000 | 4 |
| A. Byrne | QA Tester (Manual/Regression) | 100% / 50% | Base+Option | 2,600 | $215,000 | 13 |
| G. Petrov | Back-End Developer | 100% | Base only | 2,080 | $190,000 | 4 |
| P. Ochieng | Data Migration Specialist (Eligibility Data) | 100% | Base only | 2,080 | $190,000 | 3 |
| R. Talbot | Database / ETL Engineer | 100% | Base only | 2,080 | $190,000 | 4 |
| T. Halloway | Back-End Developer (Eligibility API) | 100% | Base only | 2,080 | $190,000 | 4 |
| N. Beaumont | QA Automation Engineer | 100% | Base only | 2,080 | $186,000 | 3 |
| A. Beaumont | Back-End Developer | 100% | Base only | 2,080 | $180,000 | 15 |
| Q. Redmond | Back-End Developer | 100% | Base only | 2,080 | $180,000 | 15 |
| R. Colville | Front-End Developer | 100% | Base only | 2,080 | $180,000 | 4 |
| J. Winfield | Front-End Developer (Mobile Redesign) | 100% | Base only | 2,080 | $175,000 | 2 |
| L. Anders | UX / Accessibility Designer | 100% | Base only | 2,080 | $175,000 | 30 |
| V. Prescott | Front-End Developer (Accessibility Remediation) | 100% | Base only | 2,080 | $175,000 | 5 |
| R. Fontenot | Business Analyst (Eligibility API) | 100% | Base only | 2,080 | $160,000 | 23 |
| A. Brennan | DevOps / Cloud Engineer | 80% | Base only | 1,664 | $150,000 | 2 |
| L. Sorenson | QA Tester (Manual) | 100% | Base only | 2,080 | $140,000 | 3 |
| M. Delvecchio | QA Tester (Manual) | 100% | Base only | 2,080 | $140,000 | 3 |
| J. Okonkwo | Business Analyst | 75% | Base only | 1,560 | $120,000 | 20 |
| K. Marchetti | Business Analyst (Mobile Redesign) | 75% | Base only | 1,560 | $120,000 | 14 |
| B. Holloway | Release / Configuration Manager | 60% / 25% | Base+Option | 1,508 | $115,000 | 7 |
| C. Whitworth | Schedule / PMO Analyst | 60% / 25% | Base+Option | 1,508 | $115,000 | 41 |
| K. Ashworth | Compliance / Privacy Analyst | 50% / 25% | Base+Option | 1,300 | $105,000 | 2 |
| P. Duvall | Section 508 / Accessibility Compliance Lead | 60% | Base only | 1,248 | $105,000 | 10 |
| E. Marchand | Technical Writer / Documentation Specialist | 60% / 25% | Base+Option | 1,508 | $103,000 | 10 |
| Total — 35 resources | 74,984 | $6,960,000 | 351 |  |  |  |

# 6. Loaded work packages

All 194 loaded work packages with owner, contributors, period, effort and cost. Effort is carried at work-package level only, so nothing is double-counted in the rollups above.

| WBS | Work package | Accountable owner | Contributors | Period | Effort (h) | Cost |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1.1 | Contract kickoff meeting with COR/CO | C. Tyrrell | C. Whitworth | Base | 175 | $19,201 |
| 1.1.2 | Issue offer letters — leadership roles (PM, Deputy PM, Architect, ISSO) | D. Ferris | — | Base | 109 | $10,789 |
| 1.1.3 | Issue offer letters — 508 Lead, QA Lead, BA | D. Ferris | L. Anders | Base | 144 | $13,806 |
| 1.1.4 | Issue offer letters — Front-End Developers (2) | D. Ferris | — | Base | 109 | $10,789 |
| 1.1.5 | Issue offer letters — Back-End Developers (2) | D. Ferris | A. Beaumont, Q. Redmond | Base | 207 | $19,359 |
| 1.1.6 | Issue offer letters — DevOps Engineer & QA Tester | D. Ferris | — | Base | 109 | $10,789 |
| 1.1.7 | Badge/facility access provisioning | D. Ferris | — | Base | 227 | $21,587 |
| 1.1.8 | System/network access provisioning — dev team | S. Vance | — | Base | 175 | $15,789 |
| 1.1.9 | New-hire security briefing (PHI/PII handling) | T. Abernathy | — | Base | 54 | $5,064 |
| 1.1.10 | New-hire Section 508 awareness briefing | P. Duvall | L. Anders | Base | 89 | $7,582 |
| 1.1.11 | Tooling/license procurement — IDE, design, ticketing | D. Ferris | L. Anders | Base | 289 | $27,612 |
| 1.1.12 | Establish team communication channels & shared drives | D. Ferris | — | Base | 109 | $10,789 |
| 1.2.1 | Draft Project Management Plan outline | C. Tyrrell | C. Whitworth | Base | 175 | $19,201 |
| 1.2.2 | PM Plan — scope & schedule management sections | C. Tyrrell | C. Whitworth | Base | 175 | $19,201 |
| 1.2.3 | PM Plan — cost & quality management sections | D. Ferris | C. Whitworth | Base | 124 | $11,914 |
| 1.2.4 | PM Plan — risk & communications management sections | C. Tyrrell | C. Whitworth | Base | 175 | $19,201 |
| 1.2.5 | PM Plan — staffing & change management sections | D. Ferris | C. Whitworth | Base | 124 | $11,914 |
| 1.2.6 | PM Plan internal review | D. Ferris | C. Whitworth | Base | 124 | $11,914 |
| 1.2.7 | Submit PM Plan (CDRL A001) to COR | C. Tyrrell | C. Whitworth | Base | 175 | $19,201 |
| 1.2.8 | Draft IMS baseline — Base Period milestones | D. Ferris | C. Whitworth | Base | 249 | $23,828 |
| 1.2.9 | Draft IMS baseline — Option Period milestones | D. Ferris | C. Whitworth | Base | 124 | $11,914 |
| 1.2.10 | IMS baseline internal review | C. Tyrrell | C. Whitworth | Base | 175 | $19,201 |
| 1.2.11 | Submit IMS (CDRL A002) to COR | D. Ferris | C. Whitworth | Base | 124 | $11,914 |
| 1.3.1 | Draft Communications Plan | D. Ferris | C. Whitworth | Base | 249 | $23,828 |
| 1.3.2 | Establish weekly delivery standup cadence | C. Tyrrell | — | Base | 160 | $18,076 |
| 1.3.3 | Establish bi-weekly COR sync cadence | C. Tyrrell | — | Base | 160 | $18,076 |
| 1.3.4 | Establish Quality Review Board cadence | N. Castellano | — | Base | 277 | $25,833 |
| 1.3.5 | Draft RAIDD Log & initial risk identification workshop | C. Tyrrell | — | Base | 480 | $54,240 |
| 2.1.1 | Stakeholder interview — COR & FOPBA Program Office | J. Okonkwo | — | Base | 67 | $5,217 |
| 2.1.2 | Stakeholder interview — Sponsor & mission owner | J. Okonkwo | — | Base | 67 | $5,217 |
| 2.1.3 | Stakeholder interview — end applicants (representative panel) | J. Okonkwo | — | Base | 151 | $10,443 |
| 2.1.4 | Stakeholder interview — 508/accessibility advocacy reviewers | J. Okonkwo | L. Anders | Base | 102 | $8,234 |
| 2.1.5 | Stakeholder interview — legacy platform SMEs | J. Okonkwo | — | Base | 67 | $5,217 |
| 2.1.5B | Stakeholder interview — help desk / call center staff | J. Okonkwo | — | Base | 67 | $5,217 |
| 2.1.6 | Draft functional requirements — account & identity | J. Okonkwo | K. Marchetti, R. Fontenot | Base | 202 | $15,692 |
| 2.1.6B | Draft functional requirements — MFA/identity-assurance | J. Okonkwo | K. Marchetti, R. Fontenot | Base | 202 | $15,692 |
| 2.1.7 | Draft functional requirements — benefits application intake | J. Okonkwo | K. Marchetti, R. Fontenot | Base | 202 | $15,692 |
| 2.1.7B | Draft functional requirements — eligibility pre-screening | J. Okonkwo | A. Beaumont, K. Marchetti, Q. Redmond, R. Fontenot | Base | 300 | $24,262 |
| 2.1.8 | Draft functional requirements — status tracking & document upload | J. Okonkwo | C. Whitworth, K. Marchetti, R. Fontenot | Base | 217 | $16,817 |
| 2.1.8B | Draft functional requirements — document format & size validation | J. Okonkwo | K. Marchetti, R. Fontenot | Base | 202 | $15,692 |
| 2.1.9 | Draft functional requirements — notifications & reminders | J. Okonkwo | K. Marchetti, R. Fontenot | Base | 202 | $15,692 |
| 2.1.9B | Draft functional requirements — help desk/call-center handoff | J. Okonkwo | K. Marchetti, R. Fontenot | Base | 202 | $15,692 |
| 2.1.10 | Draft non-functional requirements — security & privacy | J. Okonkwo | K. Marchetti, R. Fontenot | Base | 202 | $15,692 |
| 2.1.11 | Draft non-functional requirements — performance & availability | J. Okonkwo | K. Marchetti, R. Fontenot | Base | 202 | $15,692 |
| 2.1.12 | Draft non-functional requirements — accessibility (508/WCAG) | J. Okonkwo | K. Marchetti, L. Anders, R. Fontenot | Base | 237 | $18,709 |
| 2.1.13 | Requirements traceability matrix — build | J. Okonkwo | K. Marchetti, R. Fontenot | Base | 407 | $31,386 |
| 2.1.14 | Requirements sign-off with COR | J. Okonkwo | K. Marchetti, R. Fontenot | Base | 407 | $31,386 |
| 2.2.1 | Application architecture — front-end framework selection | K. Lindqvist | — | Base | 184 | $20,000 |
| 2.2.2 | Application architecture — back-end/API framework selection | K. Lindqvist | A. Beaumont, Q. Redmond, R. Fontenot | Base | 481 | $44,761 |
| 2.2.3 | Application architecture — front-end/back-end integration design | K. Lindqvist | A. Beaumont, L. Anders, Q. Redmond | Base | 225 | $21,587 |
| 2.2.4 | Architecture Decision Records — framework & platform choices | K. Lindqvist | — | Base | 184 | $20,000 |
| 2.2.5 | Data architecture — schema design for applicant records | K. Lindqvist | L. Anders | Base | 255 | $26,034 |
| 2.2.6 | Data architecture — legacy integration/extraction design | K. Lindqvist | L. Anders | Base | 393 | $39,051 |
| 2.2.7 | Data architecture — retention & archival design | K. Lindqvist | L. Anders | Base | 127 | $13,017 |
| 2.2.8 | Security architecture — identity & MFA design | K. Lindqvist | L. Anders | Base | 255 | $26,034 |
| 2.2.9 | Security architecture — encryption at rest & in transit | K. Lindqvist | — | Base | 92 | $10,000 |
| 2.2.10 | Security architecture — network segmentation & boundary protection | K. Lindqvist | — | Base | 92 | $10,000 |
| 2.2.11 | Threat modeling workshop (STRIDE walkthrough) | T. Abernathy | — | Base | 108 | $10,129 |
| 2.3.1 | ARB pre-read package assembly (ADRs, diagrams, threat model) | K. Lindqvist | — | Base | 184 | $20,000 |
| 2.3.2 | ARB internal walkthrough — application & data architecture | K. Lindqvist | — | Base | 92 | $10,000 |
| 2.3.3 | ARB internal walkthrough — security architecture & threat model | T. Abernathy | — | Base | 54 | $5,064 |
| 2.3.4 | ARB findings remediation (design revisions) | K. Lindqvist | L. Anders | Base | 127 | $13,017 |
| 2.3.5 | ARB COR briefing & sign-off | K. Lindqvist | — | Base | 92 | $10,000 |
| 2.3.6 | Milestone Gate: Architecture Approved for Build | K. Lindqvist | — | Base | 46 | $5,000 |
| 2.4.1 | ATO-compliant cloud landing zone — network setup | S. Vance | — | Base | 175 | $15,789 |
| 2.4.2 | ATO-compliant cloud landing zone — IAM & least-privilege roles | S. Vance | — | Base | 175 | $15,789 |
| 2.4.3 | ATO-compliant cloud landing zone — logging & monitoring baseline | S. Vance | C. Whitworth | Base | 102 | $9,019 |
| 2.4.4 | CI/CD pipeline scaffolding — build stage | S. Vance | — | Base | 87 | $7,894 |
| 2.4.5 | CI/CD pipeline scaffolding — automated test/security-scan stage | S. Vance | — | Base | 175 | $15,789 |
| 2.4.6 | Section 508 Test Plan (CDRL A004) — draft | P. Duvall | C. Whitworth, L. Anders | Base | 210 | $17,414 |
| 2.4.7 | Section 508 Test Plan (CDRL A004) — submit to COR | P. Duvall | C. Whitworth, L. Anders | Base | 210 | $17,414 |
| 2.4.8 | UI/UX wireframes — account & login flows | E. Marston | L. Anders | Base | 368 | $33,176 |
| 2.4.9 | UI/UX wireframes — application intake flow | E. Marston | L. Anders | Base | 368 | $33,176 |
| 2.4.10 | UI/UX design system — component library spec | E. Marston | L. Anders | Base | 368 | $33,176 |
| 3.1.1 | Component library — buttons & form controls | R. Nakashima | — | Base | 892 | $79,286 |
| 3.1.2 | Component library — accessible form controls (508) | J. Winfield | L. Anders | Base | 887 | $74,676 |
| 3.1.3 | Component library — navigation & layout shell | E. Marston | — | Base | 297 | $27,142 |
| 3.1.4 | Component library — data tables & status indicators | R. Nakashima | C. Whitworth | Base | 625 | $55,107 |
| 3.2.1 | Citizen portal UI — account creation flow | V. Prescott | — | Base | 346 | $29,166 |
| 3.2.2 | Citizen portal UI — login & MFA flow | R. Colville | — | Base | 462 | $40,000 |
| 3.2.3 | Citizen portal UI — password reset flow | V. Prescott | — | Base | 346 | $29,166 |
| 3.2.4 | Citizen portal UI — benefits application form (part 1 of 2) | R. Colville | — | Base | 462 | $40,000 |
| 3.2.5 | Citizen portal UI — benefits application form (part 2 of 2) | V. Prescott | — | Base | 346 | $29,166 |
| 3.3.1 | Citizen portal UI — document upload flow | R. Colville | — | Base | 694 | $60,000 |
| 3.3.2 | Citizen portal UI — application status tracker | V. Prescott | C. Whitworth | Base | 568 | $47,127 |
| 3.3.3 | Front-end code review — Sprints A-C | E. Marston | — | Base | 297 | $27,142 |
| 3.3.4 | Front-end accessibility self-check pass (pre-508-audit) | R. Nakashima | L. Anders | Base | 665 | $58,891 |
| 3.4 | Front-end unit testing — full regression | J. Winfield | — | Base | 1,300 | $109,375 |
| 3.4B.1 | Front-end — notification preference center UI | V. Prescott | — | Base | 520 | $43,750 |
| 3.4B.2 | Front-end — in-app notification banner component | R. Colville | — | Base | 462 | $40,000 |
| 3.4B.3 | Back-end — notification scheduling service | H. Ibrahim | A. Beaumont, C. Whitworth, Q. Redmond | Base | 670 | $60,667 |
| 3.4B.4 | Back-end — email/SMS delivery integration | H. Ibrahim | A. Beaumont, Q. Redmond | Base | 624 | $57,292 |
| 3.4B.5 | Notification feature test pass | A. Byrne | — | Base | 892 | $60,000 |
| 3.5.1 | Core API — account & identity endpoints | S. Larsen | A. Beaumont, Q. Redmond, R. Fontenot | Base | 1,526 | $138,419 |
| 3.5.2 | Core API — application intake endpoints | T. Halloway | A. Beaumont, Q. Redmond, R. Fontenot | Base | 1,289 | $112,857 |
| 3.5.3 | Core API — document storage endpoints | H. Ibrahim | A. Beaumont, Q. Redmond, R. Fontenot | Base | 772 | $68,720 |
| 3.5.4 | Core API — status/notification endpoints | S. Larsen | A. Beaumont, C. Whitworth, Q. Redmond, R. Fontenot | Base | 790 | $71,455 |
| 3.5.5 | Core API — MFA/identity-assurance integration (Mod P00004) | T. Halloway | A. Beaumont, Q. Redmond, R. Fontenot | Base | 643 | $56,427 |
| 3.6.1 | Back-end code review — API layer | S. Larsen | A. Beaumont, Q. Redmond, R. Fontenot | Base | 759 | $69,205 |
| 3.6.2 | Core API unit & integration testing | T. Halloway | A. Beaumont, Q. Redmond, R. Fontenot | Base | 643 | $56,427 |
| 3.7.1 | Legacy data extraction tooling — applicant records | P. Ochieng | — | Base | 1,040 | $95,000 |
| 3.7.2 | Legacy data extraction tooling — in-flight application records | R. Talbot | — | Base | 624 | $57,000 |
| 3.7.3 | Legacy data extraction tooling — document archive | G. Petrov | — | Base | 624 | $57,000 |
| 3.8.1 | Data transformation & mapping pipeline — schema mapping | R. Talbot | — | Base | 832 | $76,000 |
| 3.8.2 | Data transformation & mapping pipeline — validation rules | G. Petrov | R. Fontenot | Base | 1,030 | $91,238 |
| 3.8.3 | Reduced-scope tooling savings review (Mod P00007) | G. Petrov | — | Base | 416 | $38,000 |
| 3.9 | Back-end integration testing — full regression | H. Ibrahim | A. Beaumont, Q. Redmond | Base | 2,094 | $190,994 |
| 3.10.1 | System Security Plan — system boundary & inventory | T. Abernathy | C. Whitworth | Base | 348 | $30,949 |
| 3.10.2 | System Security Plan — control implementation narrative | T. Abernathy | C. Whitworth | Base | 573 | $49,532 |
| 3.10.3 | System Security Plan — SSP (CDRL A005) submission | T. Abernathy | C. Whitworth | Base | 139 | $12,379 |
| 3.10.4 | Disaster Recovery / COOP test plan (Mod P00008) | S. Vance | C. Whitworth | Base | 518 | $45,103 |
| 3.11.1 | Functional test case development — account/identity | P. Manning | — | Base | 624 | $55,800 |
| 3.11.2 | Functional test case development — application intake | N. Castellano | — | Base | 833 | $77,501 |
| 3.11.3 | Functional test case development — document & status flows | P. Manning | C. Whitworth | Base | 894 | $78,900 |
| 3.11.4 | Functional test execution — account/identity | L. Sorenson | — | Base | 780 | $52,500 |
| 3.11.5 | Functional test execution — application intake | M. Delvecchio | — | Base | 925 | $62,223 |
| 3.11.6 | Functional test execution — document & status flows | N. Beaumont | C. Whitworth | Base | 1,071 | $95,250 |
| 3.12.1 | Load test scenario design (peak enrollment period) | S. Vance | L. Anders | Base | 246 | $21,823 |
| 3.12.2 | Load test execution — API layer | A. Brennan | A. Beaumont, Q. Redmond, R. Fontenot | Base | 962 | $84,761 |
| 3.12.3 | Load test execution — front-end under concurrent load | S. Vance | — | Base | 175 | $15,789 |
| 3.12.4 | Performance tuning based on load test findings | S. Larsen | — | Base | 231 | $22,222 |
| 3.13.1 | Desktop browser compatibility pass (Chrome, Edge, Firefox, Safari) | L. Sorenson | — | Base | 780 | $52,500 |
| 3.13.2 | Mobile browser compatibility pass (iOS Safari, Android Chrome) | M. Delvecchio | K. Marchetti | Base | 961 | $66,674 |
| 3.13.3 | Screen-reader compatibility spot-check (pre-VPAT) | N. Beaumont | — | Base | 520 | $46,500 |
| 3B.1 | Applicant user guide — account & application flow | E. Marchand | — | Base | 749 | $46,800 |
| 3B.2 | Applicant user guide — accessibility features overview | E. Marchand | L. Anders | Base | 570 | $37,234 |
| 3B.3 | COR/Program Office admin runbook — system operations | A. Brennan | — | Base | 999 | $90,000 |
| 3B.4 | Help desk support script & FAQ (reduces post-launch tickets) | N. Castellano | — | Base | 554 | $51,666 |
| 4.1 | Automated accessibility regression tool licensing & setup (Mod P00006) | A. Byrne | L. Anders | Base | 665 | $46,034 |
| 4.2 | Automated accessibility regression testing — account/identity | L. Sorenson | L. Anders | Base | 591 | $41,034 |
| 4.3 | Automated accessibility regression testing — application flows | M. Delvecchio | L. Anders | Base | 533 | $37,145 |
| 4.4 | Automated accessibility regression testing — document/status flows | N. Beaumont | C. Whitworth, L. Anders | Base | 570 | $50,642 |
| 4.5 | Manual VPAT testing — screen reader compatibility | P. Duvall | — | Base | 162 | $13,695 |
| 4.6 | Manual VPAT testing — keyboard navigation & focus order | P. Duvall | — | Base | 162 | $13,695 |
| 4.7 | Manual VPAT testing — color contrast & text scaling | P. Duvall | L. Anders | Base | 179 | $15,164 |
| 4.8 | Independent 508 audit — vendor onboarding (Mod P00001) | P. Duvall | L. Anders | Base | 179 | $15,164 |
| 4.9 | Independent 508 audit — findings review | P. Duvall | L. Anders | Base | 179 | $15,164 |
| 4.10 | Independent 508 audit remediation — component fixes | E. Marston | L. Anders | Base | 760 | $66,372 |
| 4.11 | Independent 508 audit — re-verification | P. Duvall | L. Anders | Base | 179 | $15,164 |
| 4.12 | Section 508 Test Report (CDRL A006) — draft & submit | P. Duvall | C. Whitworth, L. Anders | Base | 427 | $34,833 |
| 5.1 | Security Assessment Report — automated vulnerability scanning | T. Abernathy | C. Whitworth | Base | 139 | $12,379 |
| 5.2 | Security Assessment Report — manual configuration review | T. Abernathy | B. Holloway, C. Whitworth | Base | 971 | $72,379 |
| 5.3 | Security Assessment Report — penetration test scoping | D. Vasquez | C. Whitworth | Base | 863 | $82,250 |
| 5.4 | Security Assessment Report — penetration test execution (3rd party) | D. Vasquez | C. Whitworth | Base | 1,294 | $123,375 |
| 5.5 | Security Assessment Report — findings triage & severity rating | T. Abernathy | C. Whitworth | Base | 139 | $12,379 |
| 5.6 | Security Assessment Report — findings documentation | T. Abernathy | C. Whitworth | Base | 139 | $12,379 |
| 5.7 | Security Assessment Report — draft & internal review | T. Abernathy | C. Whitworth | Base | 139 | $12,379 |
| 5.8 | POA&M development — open findings prioritization | T. Abernathy | — | Base | 108 | $10,129 |
| 5.9 | POA&M development — remediation timeline & owners | K. Ashworth | — | Base | 1,040 | $80,000 |
| 5.10 | POA&M development — critical finding remediation (pre-ATO) | T. Halloway | — | Base | 693 | $63,333 |
| 5.11 | ATO package assembly (SSP + SAR + POA&M) | T. Abernathy | — | Base | 162 | $15,194 |
| 5.12 | ATO package submission (CDRL A007) | T. Abernathy | — | Base | 54 | $5,064 |
| 5.13 | ATO authorization bridge extension (Mod P00005) | T. Abernathy | — | Base | 162 | $15,194 |
| 5.14 | Milestone Gate: ATO Granted | T. Abernathy | — | Base | 27 | $2,532 |
| 6.1 | Data migration validation — record-count reconciliation | P. Ochieng | — | Base | 520 | $47,500 |
| 6.2 | Data migration validation — field-level accuracy sampling | R. Talbot | — | Base | 416 | $38,000 |
| 6.3 | Data migration validation — orphaned-record detection | G. Petrov | — | Base | 208 | $19,000 |
| 6.4 | Data migration validation report (CDRL A009) — draft | P. Ochieng | C. Whitworth | Base | 551 | $49,750 |
| 6.5 | Data migration validation report (CDRL A009) — submit to COR | R. Talbot | C. Whitworth | Base | 223 | $20,125 |
| 6.6 | Full regression test suite — automated | P. Manning | — | Base | 624 | $55,800 |
| 6.7 | Full regression test suite — manual exploratory | A. Byrne | — | Base | 594 | $40,000 |
| 6.8 | Production Readiness Review — go-live checklist walkthrough | C. Tyrrell | — | Base | 160 | $18,076 |
| 6.9 | Production Readiness Review — COR/Sponsor briefing | C. Tyrrell | — | Base | 160 | $18,076 |
| 6.10 | Cutover communications — applicant notice of maintenance window | J. Okonkwo | B. Holloway | Base | 483 | $35,217 |
| 6.11 | Cutover rehearsal (dry run) | A. Brennan | B. Holloway | Option | 2 | $234 |
| 6.12 | Cutover execution — DNS/traffic cutover | S. Vance | B. Holloway | Option | 6 | $1,121 |
| 6.13 | Cutover execution — legacy platform read-only lockdown | A. Brennan | B. Holloway, D. Vasquez | Option | 6 | $701 |
| 6.14 | Post-cutover smoke test | L. Sorenson | A. Byrne, B. Holloway | Option | 3 | $492 |
| 6.15 | Milestone Gate: Production Go-Live | C. Tyrrell | — | Option | 15 | $1,969 |
| 7.1.1 | Front-end defect-fix sustainment — Month 1-2 | J. Winfield | A. Byrne | Option | 37 | $5,421 |
| 7.1.2 | Front-end defect-fix sustainment — Month 3-4 | E. Marston | A. Byrne | Option | 557 | $95,421 |
| 7.1.3 | Front-end defect-fix sustainment — Month 5-6 | R. Nakashima | A. Byrne | Option | 555 | $95,163 |
| 7.1.4 | Back-end defect-fix sustainment — Month 1-2 | H. Ibrahim | A. Byrne | Option | 557 | $105,421 |
| 7.1.5 | Back-end defect-fix sustainment — Month 3-4 | S. Larsen | A. Byrne | Option | 557 | $105,421 |
| 7.1.6 | Back-end defect-fix sustainment — Month 5-6 | T. Halloway | A. Byrne | Option | 35 | $5,163 |
| 7.2 | Continuous ATO monitoring & POA&M closure tracking | T. Abernathy | D. Vasquez, K. Ashworth | Option | 1,816 | $174,533 |
| 7.3.1 | Regression support testing — monthly pass, Q1 | P. Manning | A. Byrne | Option | 576 | $98,132 |
| 7.3.2 | Regression support testing — monthly pass, Q2 | N. Castellano | A. Byrne | Option | 576 | $83,132 |
| 7.3.3 | Release verification testing — ongoing | M. Delvecchio | A. Byrne, B. Holloway | Option | 441 | $50,532 |
| 7.4 | Infrastructure sustainment & cost optimization | S. Vance | — | Option | 516 | $94,113 |
| 7.5.1 | Status Report — Option Month 1 | C. Whitworth | E. Marchand | Option | 132 | $12,400 |
| 7.5.2 | Status Report — Option Month 2 | C. Tyrrell | E. Marchand | Option | 360 | $43,463 |
| 7.5.3 | Status Report — Option Month 3 | C. Whitworth | E. Marchand | Option | 128 | $12,398 |
| 7.5.4 | Status Report — Option Month 4 | C. Tyrrell | E. Marchand | Option | 357 | $43,458 |
| 7.5.5 | Status Report — Option Month 5 | C. Whitworth | E. Marchand | Option | 128 | $12,398 |
| 7.5.6 | Status Report — Option Month 6 | C. Tyrrell | E. Marchand | Option | 357 | $43,458 |
| 7.6 | Quarterly Architecture Review — post-launch drift check | K. Lindqvist | — | Option | 260 | $30,000 |
| 7.7 | Quarterly Architecture Review — Option Period midpoint | K. Lindqvist | — | Option | 260 | $30,000 |
| 8.1 | Final CDRL reconciliation & acceptance review | D. Ferris | — | Option | 260 | $27,500 |
| 8.2 | Final contract modification reconciliation | D. Ferris | — | Option | 130 | $13,750 |
| 8.3 | Closeout Report — draft | C. Tyrrell | E. Marchand | Option | 35 | $4,345 |
| 8.4 | Lessons Learned Register — compile & finalize | C. Tyrrell | — | Option | 31 | $3,939 |
| 8.5 | CDRL Closeout Certification — submit to COR | D. Ferris | E. Marchand | Option | 132 | $13,953 |
| 8.6 | Milestone: Task Order Closed | C. Tyrrell | — | Option | 15 | $1,969 |