# Weekly Status Report

BenefitConnect Portal Modernization — Report No. WK-11 — Mo. 2, Wk. 3

BenefitConnect Portal Modernization is in Requirements & Design, with the Section 508 Test Plan (CDRL A004) in drafting. The Task Order is currently Amber due to R-01 — the ATO Security Assessment carries a 9 (High/High) risk score, since any finding cascades directly into Milestone Gate 1 (Month 7). This week's focus was standing up the pre-assessment scan infrastructure ahead of the formal 60-day-early submission window. No change to Milestone Gate 1 is being proposed this period. This internal weekly cadence rolls up into the formal Monthly Status Report (CDRL A008) submitted to the COR.

## At a Glance

| Overall Status | Schedule | Budget (FFP) | Open Risks (High) |
| --- | --- | --- | --- |
| Amber | On Track (Mo. 2) | ~12% Spent | 1 |

## Accomplished This Week

Pre-assessment scan tooling stood up — 60 days ahead of formal ATO submission window, per R-01 mitigation plan. Owner: T. Abernathy

Section 508 Test Plan draft (CDRL A004) circulated for internal review ahead of COR submission. Owner: P. Duvall

Field-level data profiling completed on the first legacy applicant data extract (R-02 mitigation). Owner: K. Lindqvist

Onshore bench candidates identified with Acme Federal Systems' staffing team (R-05 contingency). Owner: D. Ferris

## Planned Next Week

Submit Section 508 Test Plan (CDRL A004) to COR for formal acceptance. Owner: P. Duvall

Begin System Security Plan (CDRL A005) drafting ahead of the Month 3 target. Owner: T. Abernathy

Resolve GFE VPN latency issue (I-05) — coordinate with FOPBA internal IT on a permanent fix. Owner: S. Vance

Continue automated cleansing rule development for legacy data formatting (R-02). Owner: K. Lindqvist

## Risks & Issues Requiring Attention

| ID | Description | Owner | Status / Action |
| --- | --- | --- | --- |
| R-01 | ATO assessment surfaces a security finding that delays Milestone Gate 1 (Score 9, High/High) | T. Abernathy | Pre-assessment scan tooling stood up this week; POA&M template pre-staged |
| R-05 | All-onshore staffing constraint limits surge capacity (Score 6, Medium/High) | D. Ferris | Onshore bench candidates identified this week as contingency |
| R-02 | Legacy applicant data formatting complicates migration validation (Score 6, Medium/High) | K. Lindqvist | Field-level profiling complete on first extract; cleansing rules in development |
| I-05 | Intermittent VPN latency to FOPBA's GFE affecting DevOps deployment windows | S. Vance | Status: Open — interim workaround (off-peak deployment scheduling) in place |
| DEP-01 | ATO package (A007) cannot submit until Section 508 report (A006) is accepted | T. Abernathy | Status: At Risk — sequencing tracked, no slip yet |

## Budget Health & Variance (Firm-Fixed-Price)

Status: On Track

| Current Period Variance | Value Growth to Date |
| --- | --- |
| $0 — FFP, FOPBA sees CDRL schedule status, not internal cost variance | +$114,000 (10 mods) — $3,550,000 baseline to $3,664,000 final adjusted value |

Internal Acme cost tracking (not billed line-item to FOPBA): est. ~$440K of $3,664,000 final value consumed at this point in Base Period. No re-baselining is recommended at this time.

## Upcoming Milestones

Task Order Kickoff — Mo. 0 (complete)

PMP + IMS Baseline (A001/A002) — Mo. 1 (complete)

Section 508 Test Plan (A004) — In progress (current)

System Security Plan (A005) — Mo. 3

Section 508 / VPAT Testing (A006) — Mo. 6

ATO Milestone Gate (A007) — Mo. 7

Production Go-Live — Mo. 8

Option Period Decision — Mo. 12

Illustrative program data — created to demonstrate federal task-order management practice, not a real government engagement.