## Slide 1
EXECUTIVE COMMITTEE SESSION
Gate 1 Recycle
Beacon Index Advantage — Lighthouse Financial Services Company
Gate convened 30 April 2026 and did not carry.
Tabled to the Committee 04 May 2026 by C. Tyrrell, NPD Program Manager and Chair of the Gate Review Board.
PLACEHOLDER — cover image to be added
Notes: Gate 1 did not carry. Two criteria came back U — unscoreable. This session exists because the reported return changed, and because CANCEL is a live option.

## Slide 2
PURPOSE
Why this session exists
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
A recycle is a normal gate outcome. It does not by itself require an executive session.
Two things about this one do.
87 bp
Capital charge understated
14.6% → 13.4%
Return, presented → corrected
240 bp
Headroom vs hurdle (was 360 bp)
$11,640,000
Not yet committed
1. The Committee approved a business case. The case it approved is not the case that exists.
2. $11,640,000 has not been committed — so CANCEL is genuinely on the table, and this Board cancelled a predecessor concept at its own Gate 1 last year.
Notes: Lead with the two reasons. Do not open with the options.

## Slide 3
THE FINDING
Gate 1 was not scored
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
The gate did not fail on its mathematics. It was never scored. Two criteria came back U — unscoreable — and under the Framework a U obliges the Chair to table a recycle regardless of what the other criteria show.
The capital-charge error was one of two findings. It was not the mechanism.
Getting this distinction wrong makes every number that follows look like a verdict on the product rather than on the evidence.
Nothing in the package was shown to be wrong. Two things were shown to be unevidenced.
Notes: Expect pushback here. The Committee will hear 'the numbers were wrong'. Correct it immediately.

## Slide 4
FRAMEWORK
A low score and a U are different things
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
 | A low score | A U rating
Records | Disagreement about evidence that exists | That no defensible evidence exists yet
Effect on the average | Pulls it down proportionally | Cannot be averaged at all
Obliges the Chair to | Nothing in particular | Table a RECYCLE recommendation
Had the scale lacked a U, an assessor would have entered a 3 against each — a value that reads as 'adequate' and disappears into a weighted average. The program would have proceeded, and $11,640,000 would have been committed against a capital charge that was wrong.
Notes: This is the slide that justifies the framework design to a skeptical CFO.

## Slide 5
FINDING 1
The capital charge
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
Basis | Capital ratio | Projected IRR | Headroom vs 11.0% hurdle
As presented, first convening | 3.33% | 14.6% | 360 bp
Corrected | 4.2% | 13.4% | 240 bp
Understated by 87 bp. Required capital is held against account value throughout the life of the block, so an error in that ratio compounds across the whole projection rather than affecting a single year.
The corrected case still clears the hurdle — by 240 bp instead of 360 bp.
Notes: Do not soften this. The error was real and it was ours to catch earlier.

## Slide 6
FINDING 1
The return bridge
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
14.6%
Presented
−120 bp
Capital correction
13.4%
Corrected
11.0%
Hurdle
The correction moved the reported return by 120 bp. It did not move it below the hurdle.

## Slide 7
FINDING 2 CONTEXT
How much volume can the case absorb?
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
Volume vs plan | Projected IRR | Verdict
+0% | 13.4% | clears
-5% | 12.9% | clears
-10% | 12.4% | clears
-15% | 11.9% | clears
-20% | 11.4% | clears
-25% | 10.8% | FAILS
-30% | 10.1% | FAILS
The case clears down to a 23% volume shortfall. That tolerance is why Option A is survivable — and it is the currency every other option spends.

## Slide 8
FINDING 2
Distribution evidence
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
The Year 1 volume forecast rested on internal modeling with no written evidence from any channel partner.
Nothing about the forecast was shown to be wrong. It was shown to be unevidenced — a different finding, and the one the U rating exists to record.
Written commitments now stand at $168,000,000 against a Year 1 target of $185,000,000.
The program is already spending its volume tolerance before a policy has been sold. Every option in this deck that buys back return by trading volume is spending the same scarce thing twice.

## Slide 9
CONSEQUENCE
What the loop costs
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
$232,000
Drawn from the gate contingency reserve
6 weeks
Elapsed time
46 → 40
Stage 2 weeks, after compression
unmoved
Launch date
The launch date does not move, so the loop is paid for in schedule float rather than in launch date. Stage 2 compresses from a planned 46 weeks to 40 — removing the float that would have absorbed a later problem.
That is a real cost and it is not visible in any budget line. It shows up later, as an absence of room.

## Slide 10
ACCOUNTABILITY
Root cause
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
Both findings are sequencing failures, and the Chair attributes them to himself.
The capital charge was accepted into the package without the refresh that would have caught it.
The gate was convened before written channel evidence had been requested.
Neither is an analytical failure by Actuarial or by Distribution.
The package was tabled before it was ready. Tabling the package is the Chair's job.

## Slide 11
DECISION
Five options
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
 | Option | In one line
A | Return to Gate 1 on the corrected basis | Close both findings, re-table the package at the second convening, absorb the loop.
B | Re-price to restore the original return | Lower the illustrated cap to widen margin and recover the 120 basis points.
C | Reduce program cost further | Cut build scope to lower the authorized program cost.
D | HOLD pending the annual assumption refresh | Pause the gate until Corporate Actuarial's refresh (DEP-07) lands.
E | CANCEL and return the unspent Stage 1 tranche | End the program now, before the Stage 2 tranche is committed.
CANCEL is presented as a real option with a real analysis. A recycle session that omitted it would be decorative.

## Slide 12
OPTION A
Return to Gate 1 on the corrected basis
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
RECOMMENDED
Close both findings, re-table the package at the second convening, absorb the loop.
FOR
AGAINST
The corrected case still clears the hurdle by 240 basis points (13.4% vs 11.0%).
No repricing, so no competitive exposure on the illustrated cap.
The launch date is preserved; the loop is absorbed by compressing Stage 2.
Distribution evidence is obtainable inside the six-week window.
Costs $232,000 and six weeks.
Stage 2 compresses from 46 weeks to 40, removing the float that would have absorbed a later problem.
Headroom is materially thinner than the Board was originally shown (360bp → 240bp).

## Slide 13
OPTION B
Re-price to restore the original return
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
Lower the illustrated cap to widen margin and recover the 120 basis points.
FOR
AGAINST
Arithmetically effective: 10bp of additional margin returns 14.9%, above the originally presented 14.6%.
Requires no schedule change.
The gain evaporates at a volume cost the program is already exposed to. If the lower cap costs 10% of volume, the return falls back to 13.9% — a net gain of only 49bp over doing nothing.
The cap is 9.25% against a peer 9.00% and a competitive floor of 8.50% fixed at this gate. There is little room to move.
It trades a return problem for a volume problem, and volume is the variable the model says actually moves the answer.

## Slide 14
OPTION C
Reduce program cost further
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
Cut build scope to lower the authorized program cost.
FOR
AGAINST
Arithmetically effective, and more so than expected: removing $2,000,000 of build cost returns 13.91%, 51bp above the corrected case.
The scope reduction has already happened. Two crediting strategies were cut at this same gate under GC-01; there is no comparable slack left.
What remains is people, filing fees, platform configuration and distribution enablement. Cutting the filing footprint or the enablement spend is cutting volume — which routes straight back to Option B's objection.
It treats a governance failure as a budget problem.

## Slide 15
OPTION D
HOLD pending the annual assumption refresh
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
Pause the gate until Corporate Actuarial's refresh (DEP-07) lands.
FOR
AGAINST
Decides once, on better data, rather than twice.
Removes the risk of re-pricing again at Gate 2.
The refresh lands after the launch window this product is aimed at.
HOLD is defined for causes outside the program's control. This cause is inside it — the Chair's own sequencing. Using HOLD here would misuse the outcome and set a precedent for relabeling internal failures as external ones.
Competitor launches are expected in the same quarter (R-07).

## Slide 16
OPTION E
CANCEL and return the unspent Stage 1 tranche
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
End the program now, before the Stage 2 tranche is committed.
FOR
AGAINST
Avoids committing $11,640,000, the largest single tranche.
This Board has done it before and knows how — the predecessor concept was cancelled at its own Gate 1 with the unspent tranche returned to capital.
The error was real and the Committee is entitled to ask whether it is the only one.
The corrected case still clears the hurdle by 240 basis points. Cancelling a case that clears would be an over-correction — punishing the program for the quality of its evidence rather than the quality of its economics.
The shelf-refresh need does not go away; it returns as a later, more expensive program with the same distribution problem.
Stage 1 capability — pricing basis, filing route, platform assessment — is lost and would be rebuilt.

## Slide 17
THE CENTRAL FINDING
Every lever routes back to volume
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
Lever | In isolation | After a 10% volume cost
Option B — lower the cap to widen margin | 14.9% | 13.9%
Option C — remove $2,000,000 of build cost | 13.91% | cuts filing / enablement = cuts volume
Option A — do the work properly | 13.4% | no volume cost
Volume is the only variable that moves the answer, because fixed cost is the only element that does not scale with it. Any option that spends volume tolerance to buy back return is selling the thing the case depends on to fix the thing the case can survive.

## Slide 18
RECOMMENDATION
Option A — return to Gate 1 on the corrected basis
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
13.4%
Corrected return
240 bp
Headroom above hurdle
$232,000
Cost of the loop
6 weeks
Elapsed
The corrected case clears the hurdle on a capital charge that has now been independently checked.
Both findings are closeable inside the six-week window.
Every alternative either spends volume tolerance the program cannot spare, misuses a gate outcome, or cancels a case that clears.
Two conditions proposed for attachment at the second convening: an independent external review of the rider pricing basis, and written re-validation of Year 1 volume with the three largest channel partners.

## Slide 19
THE ASK
What we are asking the Committee to note
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
That the Chair does not vote, and this recommendation is not a decision.
That the gate outcome remains with the Gate Review Board at the second convening on 11 June 2026.
That the Committee's sponsor is asked to confirm continued support for a second attempt — nothing more and nothing less.
That the corrected capital basis is now the program's basis of record, superseding the figure tabled on 30 April 2026.
If the Committee's answer is that the evidence failure is disqualifying rather than correctable, Option E — CANCEL — is available and the Chair will table it without argument.

## Slide 20
APPENDIX
Basis of the mathematics
Lighthouse Financial Services Company | Beacon Index Advantage
Executive Committee | 04 May 2026
Every figure in this deck is produced by the same cash-flow model that backs the program's Cost-Benefit Analysis.
That model reproduces the program's locked return figures to within half a basis point, or it refuses to load.
The capital ratio presented at the first convening (3.33%) is recovered by solving the model backward from the 14.6% that was tabled — it is derived from the record, not reconstructed from memory.
Required capital is held against account value; the volume ladder and the option sensitivities use the same engine.
Prepared by C. Tyrrell, NPD Program Manager and Chair of the Gate Review Board.