## Slide 1
GATE REVIEW BOARD — GATE 2
Gate 2 Review Package
Beacon Index Advantage — Lighthouse Financial Services Company
DRAFT — 167 DAYS BEFORE THE GATE
Gate convenes 01 April 2027. Assembled 16 October 2026, with evidence gaps left visible.
Notes: Open by saying this is a draft and the gaps are deliberate. A package built the week before a gate can only report what happened.

## Slide 2
FRAMING
Assembling this package early is a diagnostic
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
A gate package built the week before the gate can only report what happened.
A package built five months early reports what will be missing if nothing changes.
Every 'awaiting evidence' marker in this deck is a live instruction to somebody.
Nothing in this package is padded to look finished. Not one of the five must-meet criteria is fully evidenced today — which is the expected position 167 days out, and the reason to circulate it now.

## Slide 3
DECISION
What Gate 2 decides
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
$7,450,000
Stage 3 tranche requested
167
Days to the gate
18/41
Stage 2 weeks elapsed
1
Must-meet at risk
Outcome | What it means here
GO | Release the tranche in full. All five must-meets certified, score ≥ 3.50.
GO WITH CONDITIONS | Release with named, dated, owned conditions. Score 3.00–3.49.
RECYCLE | Return the package. Any two members can carry it; mandatory if any criterion is rated U.
HOLD | Pause for a cause outside the program's control. Not available for causes inside it.
CANCEL | End the program, return the unspent tranche. Simple majority only.
Notes: Stress that CANCEL needs only a simple majority — a deliberately lower bar than GO.

## Slide 4
TWO-TIER TEST
Must-meet criteria — evidence state
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
ID | Criterion | Certifies | State
MM-1 | Contract forms complete and cleared by outside counsel | B. Lindqvist | Partial
MM-2 | Pricing signed, supported by the GC-03 external review | N. Adeyemi | Awaiting evidence
MM-3 | Illustration output validated against the filed methodology | E. Kowalczyk | Partial
MM-4 | Hedging readiness plan accepted under GC-05 | J. Whitmore | At risk
MM-5 | All Gate 1 conditions closed or formally re-issued | C. Tyrrell | Partial
A must-meet failure removes GO and GO WITH CONDITIONS from the table regardless of the weighted score. The knockout criteria are evaluated first — which is why a strong score cannot rescue MM-4.

## Slide 5
THE BINDING CONSTRAINT
MM-4 — hedging readiness
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
Depends on two derivatives counterparties. The second has not begun negotiation (DEP-06).
Stage 2 was compressed from 46 weeks to 41 to absorb the Gate 1 recycle, so there is no float left to absorb this.
It sits behind GC-05, the one Gate 1 condition currently at risk.
On current trajectory MM-4 fails. If it cannot be certified by the gate, the Chair will table RECYCLE rather than seek a sixth condition — because that would be the second consecutive gate at which hedging readiness was carried forward instead of closed.

## Slide 6
CARRIED FORWARD
Gate 1 conditions
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
ID | Condition | Status
GC-01 | Reduce launch crediting strategies from five to three | closed
GC-02 | Remove New York from launch scope and issue a deferral memorandum | closed
GC-03 | Independent external actuarial peer review of GLWB rider pricing before Gate 2 | open
GC-04 | Re-validate distribution volume assumptions with the three largest IMO partners | closed
GC-05 | Present a hedging readiness plan with ISDA execution milestones at Gate 2 | at risk
GC-04 was correctly specified, verified and closed — and left the Year 1 volume gap open. Closed is not the same as resolved, and '3 of 5 closed' is not 60% of a problem solved.

## Slide 7
SECOND TIER
Scoring worksheet — deliberately blank
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
Criterion | Weight | Score
Strategic fit and portfolio coherence | 15% | —
Product and technical readiness | 25% | —
Regulatory and compliance readiness | 25% | —
Distribution readiness | 15% | —
Economics still supporting the case | 20% | —
Weighted total | 100% | —
Blank because the gate has not convened. A draft arriving with scores filled in would be the Chair scoring the gate, and the Chair does not vote. The scale is 1–5 plus U — unscoreable — and a single U obliges a recycle.

## Slide 8
BUSINESS CASE
Economics — unchanged since Gate 1
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
13.4%
Base case return
240 bp
Headroom over hurdle
10.1%
Downside — does NOT clear
23%
Volume tolerance to breakeven
The business case is not being re-opened at this gate. It is being checked for whether anything has moved against it.
Nothing has. The exposures below are the ones disclosed at Gate 1 and monitored since.

## Slide 9
EXPOSURE
Top open risks
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
ID | Risk | Score
R-05 | Hedging readiness (ISDA, derivatives ops, daily rebalance) lags launch | 20
R-07 | Distribution partners deprioritize against competitor launches in the same quarter | 16
R-06 | Pricing assumptions (lapse, GLWB utilization) prove unsupportable under external peer review | 15
The two highest are the two that rose since Gate 1, and both sit behind the conditions still open. The risk register and the condition register agreeing from opposite directions is the intended behavior.

## Slide 10
MANDATORY SECTION
The case for CANCEL
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
This section is mandatory and appears even when the Chair expects the gate to carry. The Chair does not vote; the obligation that comes with facilitating rather than deciding is to put the STRONGEST available argument against proceeding in front of the people who do.
Written channel commitments stand at $168,000,000 against a $185,000,000 Year 1 target. GC-04 closed having surfaced the gap and without closing it. The program has consumed roughly two fifths of its volume tolerance before a policy has been sold.
The downside scenario returns 10.1% against an 11.0% hurdle — it does not clear. No other program in the portfolio carries an approved case with a failing scenario in it.

## Slide 11
MANDATORY SECTION
The case for CANCEL (continued)
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
Two assumptions cannot be tested before the gate that depends on them (A-02, A-08). Releasing $7,450,000 at Gate 2 commits money against both.
Stage 2 was compressed from 46 weeks to 41 to absorb the Gate 1 recycle. There is no remaining float to absorb a second problem, and MM-4 is currently a second problem.
The Chair's assessment: serious, and not yet sufficient. The base case clears by 240 bp on an independently checked capital charge, and each argument describes a risk disclosed and monitored rather than one that has materialized. It WOULD become sufficient if MM-4 fails and the response is to re-issue it as a condition rather than fix it.

## Slide 12
REQUIRED
Dissent recorded ahead of the gate
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
Member | Position
R. Castellanos, Head of Distribution | Will not support GO while the Year 1 commitment gap remains open — GC-04 showed the condition mechanism cannot close it. Abstained at Gate 1 for the same reason.
D. Pemberton, CRO (observer, non-voting) | Asks that hedging readiness be presented by the CFO directly rather than summarized by the Chair.
All other members | No position recorded at the time of drafting.
Recording dissent before the gate means a member who intends to vote against is not discovering their own argument in the room.

## Slide 13
ACTION NOW
What the Chair is asking for — 167 days out
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
Ask | Of whom | By when
Begin negotiation with the second derivatives counterparty, or bring a written alternative | CFO / Investments | Immediately
Confirm the rider contract language timetable with outside counsel | General Counsel | Within 30 days
Table the launch-footprint threshold for decision at Gate 3 | Chair, with Distribution | Before the package is finalized
Record any intended dissent in writing | Any voting member | 10 business days before the gate
Only the first item can remove GO from the table. Everything else is recoverable inside the remaining window.

## Slide 14
CLOSE
Where this package stands
DRAFT
Lighthouse Financial Services Company | Beacon Index Advantage
Gate 2 | 01 April 2027 | drafted 16 October 2026
0 of 5
Must-meets fully evidenced
1
Must-meet at risk
3 of 5
Gate 1 conditions closed
167
Days to act
This is the honest position 167 days out, not a problem statement.
The package will be re-issued in final form ten business days before the gate.
If MM-4 cannot be certified by then, the Chair tables RECYCLE.
Notes: Close on the RECYCLE commitment. Stating it now gives the Board five months to change the outcome rather than five minutes.