## Slide 1
PROGRAM KICKOFF · GATE 0 · CONCEPT APPROVED
Beacon Index
Advantage
A new-product development program — building, filing, and launching a fixed indexed annuity through disciplined stage-gates to a March 2028 market launch.
February 5, 2026
Gate 0 — GO, 5-0
C. Tyrrell
NPD Program Manager
90
Full-program team (ramping)
$27.9M
Planned, gated in 4 tranches

## Slide 2
AGENDA
What We'll Cover Today
1
Welcome & Program Context
2
The Product & the Opportunity
3
Objectives & Success Criteria
4
Scope: In and Out
5
Teams & Delivery Model
6
Stage-Gate Governance
7
Gate Roadmap & Schedule
8
Funding — Gated Tranches
9
The Investment Case
10
How We'll Work Together
11
Risks We're Watching
12
Decisions Ratified
13
Next Steps & Q&A
2

## Slide 3
WELCOME
Glad You're Here
Ninety people across actuarial, product, regulatory, systems, investments, and distribution stand up a new-product development program today — gated, and funded one stage at a time.
Beacon Index Advantage is a single-premium deferred fixed indexed annuity headed for a March 2028 market launch. Concept screening cleared Gate 0 with a unanimous GO; from here the program advances through a sequence of gates — each a real decision point with the authority to continue, recycle, hold, or cancel — with the full business case validated at Gate 1. Today orients the team on the product, the stage-gate governance, and the working cadence before Stage 1 begins in earnest.
5
Gates to launch (Gate 0 cleared)
Mar 2028
Target market launch
$27.9M
Planned, gate-authorized
3

## Slide 4
THE BUSINESS CASE
Why We're Doing This
Beacon Index Advantage enters a competitive fixed-indexed-annuity market on the strength of a disciplined, gated build — and a deliberately clean regulatory lane.
The product is a single-premium deferred fixed indexed annuity with an optional Guaranteed Lifetime Withdrawal Benefit rider and three crediting strategies. Structured as a fixed indexed annuity — not a RILA (Decision D-01) — it files with state insurance regulators through the Interstate Compact plus the launch-footprint states, with no SEC or FINRA registration. Preliminary economics support the opportunity; the validated business case is the Gate-1 deliverable.
KEY FACTS
Product
Fixed indexed annuity + optional GLWB rider
Regulatory
State-filed via the Compact — not a RILA (D-01)
Opportunity
~$1.875B 5-yr premium (preliminary)
Discipline
Capital released one gate at a time
4

## Slide 5
SUCCESS METRICS
What Success Looks Like
1
Launch a compliant, competitively priced product on March 6, 2028
2
Pass each gate on validated evidence — pricing, capital, and filing peer-reviewed, not asserted
3
Achieve the launch footprint via the Interstate Compact plus non-Compact states — no New York (D-02)
4
Stand up hedging and derivatives operations before launch, not after
5
Secure distribution commitments — IMO and wholesaler coverage — ahead of launch
5

## Slide 6
SCOPE
Where the Lines Are
IN SCOPE
✓
Product build
Fixed indexed annuity, 3 crediting strategies, optional GLWB rider
✓
Regulatory filing
Interstate Compact + non-Compact launch states (no SEC/FINRA)
✓
Systems & illustration
Cordelane platform, compliant hypothetical illustrations
✓
Hedging & distribution
Derivatives operations + IMO / wholesaler enablement
OUT OF SCOPE (CANDIDATE BACKLOG)
✕
New York
No NY workstream in the launch footprint (Decision D-02)
✕
RILA / registered variants
No SEC/FINRA-registered product in this program (D-01)
✕
Post-launch expansion
New strategies or riders beyond the launch set
✕
In-force block
Existing products are untouched by this launch
6

## Slide 7
TEAMS
Everyone Who's Building This
A 90-person full-program team spanning actuarial, product, regulatory, systems, investments, and distribution — ramping stage by stage as each gate authorizes the next. Full named roster in the Resource Plan.
8
Program Leadership & PMO
Lead: C. Tyrrell (NPD PM — chairs the Gate Review Board)
14
Actuarial & Pricing
Leads: S. Ravichandran (pricing), T. Brennan (reserving)
16
Product, Regulatory & Compliance
Leads: P. Hollingsworth (filing), B. Lindqvist (GC & CCO)
20
Systems & Illustration (Cordelane)
Lead: E. Kowalczyk (illustration); platform build
12
Investments & Hedging Operations
Lead: M. Delacroix (hedging / ISDA / derivatives)
20
Distribution & Advisor Enablement
Leads: R. Castellanos (distribution), H. Kirkpatrick (licensing)
7

## Slide 8
GOVERNANCE
Who Decides What
The program is governed by a Gate Review Board that renders one of five outcomes at each gate — GO, GO WITH CONDITIONS, RECYCLE, HOLD, or CANCEL — on a two-tier test: must-meet knockout criteria first, then a weighted 1–5 score. The board holds five votes; the NPD Program Manager chairs it but does not vote — that asymmetry is the governance model.
Gate Review Board
Renders the gate outcome on a knockout-then-weighted test; Gate-N criteria locked at Gate N−1
6 seats / 5 votes — chaired, no vote, by C. Tyrrell
Sponsor
Business ownership, funding authorization, program continuation
G. Marchetti, Chief Product Officer
Actuarial & Risk
Pricing, reserving, capital and risk sign-off at each gate
N. Adeyemi (Chief Actuary) · D. Pemberton (CRO, observer)
Legal & Compliance
Regulatory filing strategy, product-form compliance, distribution conduct
B. Lindqvist (General Counsel & CCO)
8

## Slide 9
TIMELINE
Gate 0 to a March 2028 Launch
Gate-driven from concept to launch — each stage is funded and authorized only at its gate.
Stage 1 · Concept → Case
Validate the business case · Gate 0 → Gate 1
Stage 2 · Build & File
Product build + regulatory filing · Gate 1 → Gate 2
Stage 3 · Test & Ready
Illustration, hedging, distribution · Gate 2 → Gate 4
Stage 4 · Launch
Bring the product to market · → Launch Mar '28
Post-Launch · Gate 5
Results vs. the Gate-1 forecast · Gate 5 · Sep '28
KEY MILESTONES
Feb 5 '26
Gate 0 — concept approved (GO, 5-0)
Jun '26
Gate 1 — validated business case
2026–27
Gates 2–4 — build, filing, launch readiness
Mar 6 '28
Product launch
Sep 7 '28
Gate 5 — post-launch review vs. forecast
9

## Slide 10
TIMELINE · DETAIL
Project Phases — Detailed View
The program as a work view — bars show when each workstream runs and where they overlap.
'26 H1
'26 H2
'27 H1
'27 H2
'28 H1
Post
Prog.
Product & Actuarial
Business case & pricing
Product design & GLWB rider
Build & File (parallel)
Systems & illustration (Cordelane)
Regulatory filing (Compact + CA/FL)
Ready & Launch
Hedging & derivatives operations
Distribution enablement
Launch → post-launch review
10

## Slide 11
BUDGET
Where the Money Goes
TOTAL PROGRAM BUDGET $27.9M
Stage 1 — Concept & Business Case (released at Gate 0)
$2,180,000
Concept screening → the validated Gate-1 business case
Stage 2 — Build & File (authorized at Gate 1)
$11,640,000
Product build, systems and illustration, regulatory filing
Stage 3 — Test & Launch Prep (authorized at Gate 2)
$7,450,000
Illustration validation, hedging readiness, distribution
Stage 4 — Launch & Stabilize (authorized at Gate 4)
$4,330,000
Market launch and post-launch stabilization
Gate Contingency (9.0%, gate-controlled)
$2,304,000
Released only against realized risk, at a gate
The full $27.904M is planned but authorized one stage at a time — only Stage 1 ($2.18M) is released at Gate 0; each later tranche is authorized at its gate. Labor is $17.98M of the total (90 people, 146,440 hours).
11

## Slide 12
THE INVESTMENT CASE
Preliminary Business Case — Validated at Gate 1
This is a stage-gated investment — capital is released one gate at a time, and the business case is validated at Gate 1, not asserted at kickoff.
Preliminary modelling projects roughly $1.875B in premium over five years at an average case size of $118,000, returning an IRR of about 14.6% against an 11.0% hurdle. These are Gate-0 estimates — the validated business case, with peer-reviewed pricing and capital assumptions, is the Gate-1 deliverable, and each subsequent stage's funding is authorized only at its gate.
$1.875B
5-yr premium (preliminary)
~14.6%
Preliminary IRR vs. 11.0% hurdle
4 tranches
Capital released gate-by-gate
12

## Slide 13
WORKING TOGETHER
How We'll Stay in Sync
CADENCE
FORUM
PURPOSE
Per gate
Gate Review Board
Formal gate outcome — GO / conditions / recycle / hold / cancel; 5 votes, Chair no vote
Weekly
Program Status Review
Cross-workstream status, gate-readiness, RAIDD updates
Monthly
Sponsor / CPO Review
Program health with the sponsor and executive stakeholders
As needed
Gate Conditions Review
Tracking open gate conditions to closure ahead of the next gate
13

## Slide 14
RISKS
Risks and Mitigation
The full register at a glance — each risk with its mitigation, likelihood, and impact; detailed cards follow.
IDENTIFIED RISKS
MITIGATION STRATEGY
LIKELIHOOD
IMPACT
01
Illustration engine timeline
✓
Illustration validated inside the filing window
High
High
02
Hedging / derivatives readiness
✓
Hedging / ISDA readiness sequenced ahead of launch
Medium
High
03
Pricing assumptions hold up
✓
External actuarial peer review of pricing
Medium
High
04
IIPRC review of the rider
✓
IIPRC pre-submission engagement on the rider
Medium
High
14

## Slide 15
RISKS WE'RE WATCHING
Risks We're Watching (1 of 2)
R-08
Illustration engine timeline
LIKELIHOOD HIGH
IMPACT HIGH
The illustration engine may not be able to produce compliant hypothetical illustrations inside the regulatory filing window.
OWNER E. Kowalczyk
STATUS Watch — highest-attention
Mitigation: Illustration scope and validation are sequenced early against the filing window, with compliance validating output before submission.
R-05
Hedging / derivatives readiness
LIKELIHOOD MEDIUM
IMPACT HIGH
Hedging readiness — ISDA agreements, derivatives operations, daily rebalance — could lag the launch date.
OWNER M. Delacroix
STATUS Watch
Mitigation: Hedging operations are stood up and sequenced well ahead of launch rather than treated as a launch-week switch-on.
15

## Slide 16
RISKS WE'RE WATCHING
Risks We're Watching (2 of 2)
R-06
Pricing assumptions hold up
LIKELIHOOD MEDIUM
IMPACT HIGH
Pricing assumptions (lapse, GLWB utilization) could prove unsupportable under external actuarial peer review.
OWNER S. Ravichandran
STATUS Watch
Mitigation: An independent actuarial peer review tests the assumptions before they are locked into the filed product.
R-01
IIPRC review of the rider
LIKELIHOOD MEDIUM
IMPACT HIGH
Interstate Compact (IIPRC) review could extend past the standard clock over the non-standard GLWB rider feature.
OWNER P. Hollingsworth
STATUS Monitoring
Mitigation: Pre-submission engagement with the Compact on the rider feature reduces the chance of a late, clock-extending objection.
16

## Slide 17
DECISIONS RATIFIED
Decisions We're Starting With
Three decisions are already ratified at Gate 0 — captured here so no one has to reconstruct them later.
Gate 0
Concept approved to proceed — GO, unanimous 5-0 (weighted score 3.85) on the two-tier gate test
Gate Review Board 5 Feb 2026
D-01
Product structured as a fixed indexed annuity, NOT a RILA — keeps it state-filed, out of SEC/FINRA registration
Chief Actuary + GC/CCO At Gate 0
D-05
Guaranteed Lifetime Withdrawal Benefit offered as an OPTIONAL rider rather than bundled into the base contract
Product + Actuarial At Gate 0
17

## Slide 18
NEXT STEPS
What Happens Next
1
Stage 1
Build the Gate-1 business case — peer-reviewed pricing, capital, and filing strategy
2
Immediately
Stand up the Gate Review Board and lock the Gate-1 decision criteria
3
Jun '26
Convene Gate 1 for the funding decision on the full program
18

## Slide 19
QUESTIONS?
Let's build something that sets the gold standard.
C. Tyrrell · NPD Program Manager
Beacon Index Advantage
All program artifacts available at ct-pm.pages.dev/lighthouse/