## WBS
Stage | WBS | Work package | Hours | Cost | State
1 |  | Stage 1 - Business Case - Feasibility | 15701 | 2215829 | BASELINED
| 1.1 | Concept definition - product structure | 2198 | 310196 | Baselined
| 1.2 | Preliminary pricing - capital assessment | 4082 | 576079 | Baselined
| 1.3 | Regulatory route assessment | 2041 | 288039 | Baselined
| 1.4 | Platform - illustration feasibility | 2669 | 376667 | Baselined
| 1.5 | Distribution appetite assessment | 1570 | 221569 | Baselined
| 1.6 | Gate 1 package preparation | 1884 | 265883 | Baselined
| 1.7 | Gate 1 recycle remediation | 1257 | 177396 | Baselined
2 |  | Stage 2 - Development | 37483 | 4691986 | BASELINED
| 2.1 | Product specification - contract forms | 5997 | 750683 | Baselined
| 2.2 | Pricing basis - external peer review | 5248 | 656926 | Baselined
| 2.3 | Platform configuration - Cordelane WP-1 | 8996 | 1126087 | Baselined
| 2.4 | Illustration engine build - Brightpath | 5622 | 703742 | Baselined
| 2.5 | Hedging design - ISDA onboarding | 4123 | 516102 | Baselined
| 2.6 | Reinsurance structuring - Halverson Re | 2249 | 281522 | Baselined
| 2.7 | Filing preparation | 3373 | 422220 | Baselined
| 2.8 | Gate 2 package preparation | 1875 | 234706 | Baselined
3 |  | Stage 3 - Testing - Validation | 46810 | 5644649 | PLANNING ENVELOPE - not baselined
| 3.1 | Master test execution | - | - | Not loaded - stage unfunded
| 3.2 | Regulatory filing - response management | - | - | Not loaded - stage unfunded
| 3.3 | Illustration validation | - | - | Not loaded - stage unfunded
| 3.4 | Operations process build | - | - | Not loaded - stage unfunded
| 3.5 | Gate 3 package preparation | - | - | Not loaded - stage unfunded
4 |  | Stage 4 - Launch Readiness | 46446 | 5427536 | PLANNING ENVELOPE - not baselined
| 4.1 | Distribution enablement - advisor training | - | - | Not loaded - stage unfunded
| 4.2 | Operations readiness - cutover | - | - | Not loaded - stage unfunded
| 4.3 | Hedging go-live - shadow book | - | - | Not loaded - stage unfunded
| 4.4 | Launch readiness verification | - | - | Not loaded - stage unfunded
| 4.5 | Gate 4 package preparation | - | - | Not loaded - stage unfunded
TOTAL
Check: total hours must equal the roster's 146,440

## Stage 1 assignments
Team | Code | 1.1 | 1.2 | 1.3 | 1.4 | 1.5 | 1.6 | 1.7 | Total | Check
Product Development PMO | PMO | 503 | 1246 | 380 | 83 | 436 | 1192 | 757
Product Management and Design | PROD | 1493 | 0 | 451 | 0 | 518 | 237 | 0
Actuarial - Pricing and Product Development | ACT-P | 115 | 1693 | 0 | 0 | 0 | 45 | 228
IT - Annuity Administration Platform | IT-PLT | 0 | 0 | 0 | 1634 | 0 | 0 | 0
Legal and Compliance | LEGAL | 0 | 0 | 846 | 0 | 0 | 147 | 0
Finance and Treasury | FIN | 0 | 595 | 0 | 0 | 0 | 0 | 60
Distribution and Wholesaling | DIST | 45 | 0 | 0 | 0 | 394 | 36 | 91
Investments - ALM and Hedging | INV | 0 | 548 | 0 | 0 | 0 | 0 | 0
IT - Illustration and Quoting | IT-ILL | 0 | 0 | 0 | 418 | 0 | 0 | 0
Regulatory Filing and Contract Forms | REG | 0 | 0 | 364 | 0 | 0 | 38 | 0
Gate Review Board (oversight only) | BOARD | 0 | 0 | 0 | 0 | 0 | 189 | 121
Operations - New Business and Policyholder Services | OPS | 0 | 0 | 0 | 275 | 0 | 0 | 0
Marketing and Advisor Enablement | MKTG | 42 | 0 | 0 | 0 | 222 | 0 | 0
Data, Reporting and Analytics | DATA | 0 | 0 | 0 | 259 | 0 | 0 | 0
Work package total
Ties to WBS package hours?

## Stage 2 assignments
Team | Code | 2.1 | 2.2 | 2.3 | 2.4 | 2.5 | 2.6 | 2.7 | 2.8 | Total | Check
IT - Annuity Administration Platform | IT-PLT | 0 | 0 | 6288 | 630 | 0 | 0 | 0 | 0
Product Development PMO | PMO | 582 | 562 | 278 | 168 | 1197 | 586 | 544 | 680
Product Management and Design | PROD | 3160 | 0 | 0 | 367 | 0 | 0 | 593 | 123
Actuarial - Pricing and Product Development | ACT-P | 0 | 3681 | 0 | 367 | 0 | 0 | 0 | 125
IT - Illustration and Quoting | IT-ILL | 0 | 0 | 0 | 3724 | 0 | 0 | 0 | 0
Regulatory Filing and Contract Forms | REG | 664 | 0 | 0 | 0 | 0 | 0 | 1867 | 66
Actuarial - Valuation and Financial Reporting | ACT-V | 0 | 642 | 0 | 0 | 457 | 891 | 0 | 0
Legal and Compliance | LEGAL | 589 | 0 | 0 | 57 | 405 | 395 | 369 | 0
Operations - New Business and Policyholder Services | OPS | 0 | 0 | 1403 | 0 | 0 | 0 | 0 | 284
Finance and Treasury | FIN | 0 | 363 | 0 | 0 | 773 | 377 | 0 | 0
Data, Reporting and Analytics | DATA | 0 | 0 | 1027 | 309 | 0 | 0 | 0 | 0
Investments - ALM and Hedging | INV | 0 | 0 | 0 | 0 | 1291 | 0 | 0 | 0
Distribution and Wholesaling | DIST | 738 | 0 | 0 | 0 | 0 | 0 | 0 | 287
Gate Review Board (oversight only) | BOARD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310
Marketing and Advisor Enablement | MKTG | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Work package total
Ties to WBS package hours?